## Test Cases
General Information | [7 empty] | Priority and Status |  | Tester |  | Issue |  | Development System |  |  | Test System via. Transport + Refresh |  |  |  | Test System via. Transport | S4 |  | ERP
[14 empty] | Sender | Receiver |  | Sender |  | Receiver |  | Sender | Receiver (Maxi) |  | Receiver (Maxi)
Test Case | Goal | Object | Task | Code Value List | Edition | Language | Step | Priority | Status | Previous Tester | Current Tester | Issue No. | Comment | ID1 100 | ID1 400 (LSA) | ID1 400 (DT) | IH1 100 | IH1CLNT100 | IH1 400 (LSA) | IH1 400 (DT) | IH2 100 | IR1 200 (LSA) | IR1 200 (DT) | IR2 200 (LSA) | Spalte1 | IR2 200 (DT)
01.0 RDG |  | ****************************************** | n.A. |  |  |  | n.A. | *********
01.1 | 2511 | Material Group | Change |  |  |  | 3-Step | High | error | Ulla | Maxi | 1060 | 24.09.2025 ME: Retest after new SMT Mapping by me | done | done | done | done | error | error | retest | retest | retest | retest | retest | retest | retest
01.10 |  | Material Group Text | Delete |  |  |  | n.A. | High |  | Thomas
01.2 | 2511 | Material Group | Create |  |  |  | 3-Step | High | error | Ulla | Maxi | 1060 | 24.09.2025 ME: Retest after new SMT Mapping by me | done | done | done | done | error | error | retest | retest | retest | retest | retest | retest | retest
01.4 | 2511 | Material Group | Data Export / Import |  |  |  | General | High |  | Sabine | [6 empty] | done
01.5 | 2511 | Material Group | File Download / Upload |  |  |  | General | High |  | Sabine | [6 empty] | done
01.6 | 2511 | Material Group | Local Customizing |  |  |  | General | Medium |  | Sabine
01.7 |  | Material Group | Language Test |  |  | DE/EN | General | Low |  | Ulla |  |  |  | n/a | n/a | n/a
01.8 |  | Material Group | Language Test |  |  | FR | General | Low |  | Ulla
01.9 |  | Material Group | Language Test |  |  | ES | General | Low |  | Ulla
02.1 | 2510 | Unit of Measure | Change |  |  |  | 1-Step | Medium | open | Maxi
02.2 | 2510 | Unit of Measure | Create |  |  |  | 1-Step | Medium | open | Maxi
02.3 | 2510 | Unit of Measure | File Download / Upload |  |  |  | General | Medium |  | Niklas | [6 empty] | done
02.4 | 2510 | Unit of Measure | Data Export / Import |  |  |  | General | Medium |  | Niklas | [6 empty] | done
02.5 |  | Unit of Measure | Language Test |  |  | DE/EN | General | Low |  | Ulla |  |  |  | n/a | n/a | n/a
02.6 |  | Unit of Measure | Language Test |  |  | FR/ES | General | Low |  | Ulla
02.7 |  | Unit of Measure | Language Test |  |  | ES | General | Low |  | Ulla
03.1 | 2510 | Country | Change |  |  |  | 3-Step | Medium | open | Maxi
03.2 | 2510 | Country | Create |  |  |  | 3-Step | Medium | open | Maxi
03.3 | 2510 | Country | File Download / Upload |  |  |  | General | Medium |  | Niklas | [6 empty] | done
03.4 | 2510 | Country | Data Export / Import |  |  |  | General | Medium |  | Niklas | [6 empty] | done
03.5 |  | Country | Language Test |  |  | DE/EN/FR/ES | General | Low |  | Maxi |  |  |  | n/a | n/a | n/a
03.6 |  | Country | Language Test |  |  | FR/ES | General | Low |  | Ulla
03.7 |  | Country | Language Test |  |  | ES | General | Low |  | Ulla
04.1 | 2510 | Region | Change |  |  |  | 2-Step | Medium | in progress | Maxi | Maxi |  | 24.09.2025 ME: Waiting for SMT Transport - Standing By | done | done | done | retest | retest | retest | retest | retest | retest | retest | retest | retest | retest
04.2 | 2510 | Region | Create |  |  |  | 2-Step | Medium | in progress | Maxi | Maxi |  | 24.09.2025 ME: Waiting for SMT Transport - Standing By | done | done | done | retest | retest | retest | retest | retest | retest | retest | retest | retest | retest
04.3 | 2510 | Region | File Download / Upload |  |  |  | General | Medium |  | Niklas | [6 empty] | done
04.4 | 2510 | Region | Data Export / Import |  |  |  | General | Medium |  | Niklas | [6 empty] | done
04.5 |  | Region | Language Test |  |  | DE/EN | General | Low |  | Maxi |  |  |  | n/a | n/a | n/a
04.6 |  | Region | Language Test |  |  | FR/ES | General | Low |  | Ulla
04.7 |  | Region | Language Test |  |  | ES | General | Low |  | Ulla
05.1 | 2510 | Purchasing Group | Change |  |  |  | 2-Step | Medium | in progress | Sabine | Maxi |  | 24.09.2025 ME: Should be retested once SMT-Mapping TR comes through | done | done | done | retest | retest | retest | retest | retest | retest | retest | retest | retest | retest
05.2 | 2510 | Purchasing Group | Create |  |  |  | 2-Step | Medium | in progress | Sabine | Maxi |  | 24.09.2025 ME: Should be retested once SMT-Mapping TR comes through | done | done | done | retest | retest | retest | retest | retest | retest | retest | retest | retest | retest
05.3 | 2510 | Purchasing Group | File Download / Upload |  |  |  | General | Medium |  | Niklas | [6 empty] | done
05.4 | 2510 | Purchasing Group | Data Export / Import |  |  |  | General | Medium |  | Niklas | [6 empty] | done
05.5 |  | Purchasing Group | Language Test |  |  | DE/EN | General | Low |  | Ulla
05.6 |  | Purchasing Group | Language Test |  |  | FR/ES | General | Low |  | Ulla
05.7 |  | Purchasing Group | Language Test |  |  | ES | General | Low |  | Ulla
06.1 | 2510 | Purchasing Organization | Change |  |  |  | 1-Step | High | in progress | Maxi | Maxi |  | 24.09.2025 ME: Should be retested once SMT-Mapping TR comes through | done | done | done | retest | retest | retest | retest | retest | retest | retest | retest | retest | retest
06.2 | 2510 | Purchasing Organization | Create |  |  |  | 1-Step | High | in progress | Maxi | Maxi |  | 24.09.2025 ME: Should be retested once SMT-Mapping TR comes through | done | done | done | retest | retest | retest | retest | retest | retest | retest | retest | retest | retest
06.3 | 2510 | Purchasing Organization | File Download / Upload |  |  |  | General | High | done | Niklas | [6 empty] | done | n/a | n/a
06.4 | 2510 | Purchasing Organization | Data Export / Import |  |  |  | General | High | done | Niklas | [6 empty] | done | n/a | n/a
06.5 |  | Purchasing Organization | Language Test |  |  | DE/EN | General | Low |  | Ulla
06.6 |  | Purchasing Organization | Language Test |  |  | FR/ES | General | Low |  | Ulla
06.7 |  | Purchasing Organization | Language Test |  |  | ES | General | Low |  | Ulla
07.1 | 2510 | Account Group G/L | Change |  |  |  | 2-Step | High | error | Sabine | Maxi | 1078 | XX.XX.XXXX SS: no staging entires generated in IH1/400; same with G/L account group 24.09.2025 ME: On hold til SMT-Transport is in IH1, then retest by me |  |  |  | done | error | error | retest | retest | retest | retest | retest | retest | retest
07.2 | 2510 | Account Group G/L | Create |  |  |  | 2-Step | High | error | Sabine | Maxi | 1078 | XX.XX.XXXX SS: no staging entires generated in IH1/400; same with G/L account group 24.09.2025 ME: On hold til SMT-Transport is in IH1, then retest by me |  |  |  | done | error | error | retest | retest | retest | retest | retest | retest | retest
07.3 | 2510 | Account Group G/L | File Download / Upload |  |  |  | General | High | done | Niklas | [6 empty] | done | n/a | n/a
07.4 | 2510 | Account Group G/L | Data Export / Import |  |  |  | General | High | done | Niklas | [6 empty] | done | n/a | n/a
07.5 | 2510 | Account Group G/L - Scheduled LSA Subscriber | Change |  |  |  | 2-Step | Medium |  | Gerd
07.6 |  | Account Group GL | Language Test |  |  | DE/EN | General | Low |  | Ulla
07.7 |  | Account Group GL | Language Test |  |  | FR/ES | General | Low |  | Ulla
07.7 |  | Account Group | Language Test |  |  | ES | General | Low |  | Ulla
08.1 | 2510 | Account Group Vendor | Change |  |  |  | 3-Step | High | open | Maxi | [6 empty] | done | done | done
08.2 | 2510 | Account Group Vendor | Create |  |  |  | 3-Step | High | open | Maxi | [6 empty] | done | done | done
08.3 | 2510 | Account Group Vendor | File Download / Upload |  |  |  | General | High | done | Niklas | [6 empty] | done | n/a | n/a
08.4 | 2510 | Account Group Vendor | Data Export / Import |  |  |  | General | High | done | Niklas | [6 empty] | done | n/a | n/a
08.5 |  | Account Group Vendor | Language Test |  |  | DE/EN | General | Low |  | Ulla
08.6 |  | Account Group Vendor | Language Test |  |  | FR/ES | General | Low |  | Ulla
08.7 |  | Vendor Account Group | Language Test |  |  | ES | General | Low |  | Ulla
09.1 | 2510 | Account Group Customer | Change |  |  |  | 2-Step | High | in progress | Sabine | Maxi | 1053, 1078 | XX.XX.XXXX SS: no staging entires generated in IH1/400; same with G/L account group 24.09.2025 ME: On hold til SMT-Transport is in IH1, then retest by me | done | done | done | done | error | error | retest | retest | retest | retest | retest | retest | retest
09.2 | 2510 | Account Group Customer | Create |  |  |  | 2-Step | High | in progress | Sabine | Maxi | 1053, 1078 | XX.XX.XXXX SS: no staging entires generated in IH1/400; same with G/L account group 24.09.2025 ME: On hold til SMT-Transport is in IH1, then retest by me | done | done | done | done | error | error | retest | retest | retest | retest | retest | retest | retest
09.3 | 2510 | Account Group Customer | File Download / Upload |  |  |  | General | High | done | Niklas | [6 empty] | done | n/a | n/a
09.4 | 2510 | Account Group Customer | Data Export / Import |  |  |  | General | High | done | Niklas | [6 empty] | done | n/a | n/a
09.5 |  | Account Group Customer | Language Test |  |  | DE/EN | General | Low |  | Ulla
09.6 |  | Account Group Customer | Language Test |  |  | FR/ES | General | Low |  | Ulla
09.7 |  | Customer Account Group | Language Test |  |  | ES | General | Low |  | Ulla
10.1 | 2510 | Product Hierarchy | Change |  |  |  | 3-Step | Very High | in progress | Sabine | Maxi |  | 1017 List of change nodes |  |  |  | in progress
10.10 | 2510P | Product Hierarchy | Delete Node |  |  |  | General | Very High | done | Gerd
10.11 | 2510P | Product Hierarchy | Move Node |  |  |  | General | Very High | done | Gerd
10.12 | 2510P | Product Hierarchy | Move Node with Subtree |  |  |  | General | Very High | done | Gerd
10.13. | 2510 | Product Hierarchy | ForeignKey Consistency |  |  |  | General | Very High | in progress | Gerd
10.2 | 2510P | Product Hierarchy | Create |  |  |  | 3-Step | Very High | done | Gerd | Maxi
10.3 | 2510 | Product Hierarchy | File Download / Upload |  |  |  | General | Very High | done | Gerd
10.4 | 2510 | Product Hierarchy | Language Test |  |  | DE/EN | General | High |  | Ulla
10.5 | 2511 | Product Hierarchy | Language Test |  |  | FR | General | High |  | Ulla
10.6 | 2511 | Product Hierarchy | Language Test |  |  | ES | General | Medium |  | Michael
10.7 | 2510P | Product Hierarchy | Remove Subnode |  |  |  | General | Very High | done | Gerd
10.8 | 2510P | Product Hierarchy | Remove Node |  |  |  | General | Very High | done | Gerd
10.9 | 2510P | Product Hierarchy | Delete Subnode |  |  |  | General | Very High | done | Gerd
11.1 | 2510 | Company Code | Change |  |  |  | 2-Step | Medium | in progress | Maxi | Maxi |  |  | done | done | done | done | done | done
11.2 | 2510 | Company Code | Create |  |  |  | 2-Step | Medium | in progress | Maxi | Maxi |  |  | done | done | done | done | done | done
11.3 | 2510 | Company Code | File Download / Upload |  |  |  | General | Medium |  | Niklas | [6 empty] | done
11.4 | 2510 | Company Code | Data Export / Import |  |  |  | General | Medium |  | Niklas | [6 empty] | done
11.5 |  | Company Code | Language Test |  |  | DE/EN | General | Low |  | Maxi
11.6 |  | Company Code | Language Test |  |  | EN/DE | General | Low |  | Ulla
11.7 |  | Company code | Language Test |  |  | ES | General | Low |  | Ulla
12.1 | 2510 | Plant | Change |  |  |  | 3-Step | Medium | error | Gerd | Maxi | 1081.1082 | 11.09.2025 GS: Country should be Mandatory - UI Specific 24.09.2025 ME: Retest after SMT Mapping Refresh by me | done | retest | open | retest | retest | retest | retest | retest | retest | retest | retest | retest | retest
12.2 | 2510 | Plant | Create |  |  |  | 3-Step | Medium | error | Gerd | Maxi | 1081.1082 | 11.09.2025 GS: Country should be Mandatory - UI Specific 24.09.2025 ME: Retest after SMT Mapping Refresh by me | done | retest | open | retest | retest | retest | retest | retest | retest | retest | retest | retest | retest
12.3 | 2510 | Plant | File Download / Upload |  |  |  | General | Medium |  | Niklas | [6 empty] | done
12.4 | 2510 | Plant | Data Export / Import |  |  |  | General | Medium |  | Niklas | [6 empty] | done
12.6 |  | Plant | Language Test |  |  | DE/EN | General | Low |  | Ulla |  |  |  | n/a | n/a | n/a
12.7 |  | Plant | Language Test |  |  | FR/ES | General | Low |  | Ulla
12.8 |  | Plant | Language Test |  |  | ES | General | Low |  | Ulla
13.1 | 2510 | Payment Term | Change |  |  |  | 1-Step | Medium | in progress | Ulla | Maxi | 1075 | 08.09. MB: Ticket can be closed, a new one should be created 24.09. ME: Works in ID, we should wait for the SMT Mapping | done | done | done | done | error | error | retest | retest | retest | retest | retest | retest | retest
13.2 | 2510 | Payment Term | Create |  |  |  | 1-Step | Medium | in progress | Ulla | Maxi | 1075 | 08.09. MB: Ticket can be closed, a new one should be created 24.09. ME: Works in ID, we should wait for the SMT Mapping | done | done | done | done | error | error | retest | retest | retest | retest | retest | retest | retest
13.3 | 2510 | Payment Term | File Download / Upload |  |  |  | General | Medium |  | Patrick | [6 empty] | done
13.4 | 2510 | Payment Term | Data Export / Import |  |  |  | General | Medium |  | Niklas | [6 empty] | done
13.5 |  | Payment Term | Language Test |  |  | DE/EN | General | Low |  | Ulla |  |  |  | n/a | n/a | n/a
13.6 |  | Payment Term | Language Test |  |  | FR/ES | General | Low |  | Ulla
13.7 |  | Payment Term | Language Test |  |  | ES | General | Low |  | Ulla
13.8 | 2510 | Payment Term | Create |  |  |  | General | Medium |  | Gerd
14.1 |  | Currency Code | Change |  |  |  | 3-Step | High | in progress | Maxi |  |  |  | done | done | done
14.2 |  | Currency Code | Create |  |  |  | 3-Step | High | in progress | Maxi |  |  |  | done | done | done
14.3 |  | Currency Code | File Download / Upload |  |  |  | General | High | done | Niklas | [6 empty] | done
14.4 |  | Currency Code | Data Export / Import |  |  |  | General | Very High |  | Niklas | [6 empty] | done
14.5 |  | Currency Code | Language Test |  |  | DE/EN | General | Medium |  | Maxi |  |  |  | n/a | n/a | n/a
14.6 |  | Currency Code | Language Test |  |  | FR/ES | General | Medium |  | Ulla
14.7 |  | Currency Code | Language Test |  |  | ES | General | Medium |  | Michael
15.1 | 2510 | Sales Organization | Change |  |  |  | 2-Step | Medium | in progress | Sabine | Maxi | 832, 836, 848, 1079 | XX.XX.XXXX SS: All issues are similiar (ValHelp, Validations) 24.09.2025 ME: Retest Replication after SMT Trasnport comes through | done | done | error | error | done | done | retest | retest | retest | retest | retest | retest | retest
15.2 | 2510 | Sales Organization | Create |  |  |  | 2-Step | Medium | in progress | Sabine | Maxi |  | XX.XX.XXXX SS: All issues are similiar (ValHelp, Validations) 24.09.2025 ME: Retest Replication after SMT Trasnport comes through | done | done | error | error | done | done | retest | retest | retest | retest | retest | retest | retest
15.3 | 2510 | Sales Organization | File Download / Upload |  |  |  | General | Medium |  | Patrick | [6 empty] | done
15.4 | 2510 | Sales Organization | Data Export / Import |  |  |  | General | Medium |  | Niklas | [6 empty] | done
15.5 |  | Sales Organization | Language Test |  |  | DE/EN | General | Low |  | Ulla
15.6 |  | Sales Organization | Language Test |  |  | FR/ES | General | Low |  | Ulla
15.7 |  | Sales Organisation | Language Test |  |  | ES | General | Low |  | Ulla
16.1 | 2510 | Material Type | Change |  |  |  | 2-Step | Medium | error | Ulla | Maxi | 1059 | Change to Current Tester | open | open | open | done | error | error | open | open | open | open | open | open | open
16.2 | 2510 | Material Type | Create |  |  |  | 2-Step | Medium | error | Ulla | Maxi | 1059 | Change to Current Tester | open | open | open | done | error | error | open | open | open | open | open | open | open
16.3 | 2510 | Material Type | File Download / Upload |  |  |  | General | Medium |  | Niklas | [6 empty] | done
16.4 | 2510 | Material Type | Data Export / Import |  |  |  | General | Medium |  | Niklas | [6 empty] | done
16.5 |  | Material Type | Language Test |  |  | DE/EN | General | Low |  | Maxi
16.6 |  | Material Type | Language Test |  |  | FR/ES | General | Low |  | Ulla
16.7 |  | Material Type | Language Test |  |  | ES | General | Low |  | Ulla
17.1 | 2510 | Storage Location | Change |  |  |  | 2-Step | Medium | error | Ulla | Maxi | 1058 | Change to Current Tester | open | open | open | done | error | error | open | open | open | open | open | open | open
17.2 | 2510 | Storage Location | Create |  |  |  | 2-Step | Medium | error | Ulla | Maxi | 1058 | Change to Current Tester | open | open | open | done | error | error | open | open | open | open | open | open | open
17.3 | 2510 | Storage Location | File Download / Upload |  |  |  | General | Medium |  | Niklas | [6 empty] | done
17.4 | 2510 | Storage Location | Data Export / Import |  |  |  | General | Medium |  | Niklas | [6 empty] | done
17.5 |  | Storage Location | Language Test |  |  | DE/EN | General | Low |  | Ulla
17.6 |  | Storage Location | Language Test |  |  | FR/ES | General | Low |  | Ulla
17.7 |  | Storage Location | Language Test |  |  | ES | General | Low |  | Ulla
18.1 | 2510 | Division | Change |  |  |  | 1-Step | High | open | Maxi | [6 empty] | done | done | done
18.2 | 2510 | Division | Create |  |  |  | 1-Step | High | open | Maxi | [6 empty] | done | done | done
18.3 | 2510 | Division | File Download / Upload |  |  |  | 1-Step | High | done | Niklas | [6 empty] | done | n/a | n/a
18.4 | 2510 | Division | Data Export / Import |  |  |  | General | High | done | Niklas | [6 empty] | done | n/a | n/a
18.5 |  | Division | Language Test |  |  | DE/EN | General | Low |  | Ulla |  |  |  | n/a | n/a | n/a | done
18.6 |  | Division | Language Test |  |  | FR/ES | General | Low |  | Ulla
18.7 |  | Division | Language Test |  |  | ES | General | Low |  | Ulla | [6 empty] | done
19.1 |  | Factory Calendar | Change |  |  |  | 2-Step | Very High |  | Maxi
19.2 |  | Factory Calendar | Create |  |  |  | 2-Step | Very High |  | Maxi | [6 empty] | done
19.3 |  | Factory Calendar | File Download / Upload |  |  |  | General | Very High | done | Niklas | [6 empty] | done
19.4 |  | Factory Calendar | Data Export / Import |  |  |  | General | High | done | Niklas | [6 empty] | done
19.5 |  | Factory Calendar | Language Test |  |  | DE/EN | General | Very High |  | Ulla |  |  |  | n/a | n/a | n/a
19.6 |  | Factory Calendar | Language Test |  |  | FR/ES | General | Very High |  | Ulla | [6 empty] | done
19.7 |  | Factory Calendar | Language Test |  |  | ES | General | Medium |  | Michael
20.1 | 2510 | Distribution Channel | Change |  |  |  | 2-Step | Medium | in progress | Sabine | [6 empty] | done | done | done
20.2 | 2510 | Distribution Channel | Create |  |  |  | 2-Step | Medium | in progress | Sabine | [6 empty] | done | done | done
20.3 | 2510 | Distribution Channel | File Download / Upload |  |  |  | General | Medium | error | Niklas |  |  | 08.09. Niklas schaut nochmal |  |  |  | error
20.4 | 2510 | Distribution Channel | Data Export / Import |  |  |  | General | Medium | done | Niklas | [6 empty] | done
20.5 |  | Distribution Channel | Language Test |  |  | DE/EN | General | Low |  | Ulla |  |  |  | n/a | n/a | n/a
20.6 |  | Distribution Channel | Language Test |  |  | FR/ES | General | Low |  | Ulla
20.7 |  | Distribution Channel | Language Test |  |  | ES | General | Low |  | Ulla
21.1 | 2510 | Controlling Area | Change |  |  |  | n.A. | Medium | open | Maxi
21.2 | 2510 | Controlling Area | Create |  |  |  | n.A. | Medium | open | Maxi
21.3 | 2510 | Controlling Area | File Download / Upload |  |  |  | General | Medium |  | Niklas | [6 empty] | done
21.4 | 2510 | Controlling Area | Data Export / Import |  |  |  | General | Medium |  | Niklas | [6 empty] | error
21.5 |  | Controlling Area | Language Test |  |  | DE/EN | General | Low |  | Ulla |  |  |  | n/a | n/a | n/a
21.6 |  | Controlling Area | Language Test |  |  | FR/ES | General | Low |  | Ulla
21.7 |  | Controlling Area | Language Test |  |  | ES | General | Low |  | Ulla
22.1 | 2510 | Material Status | Change |  |  |  | 1-Step | Medium | open | Maxi
22.2 | 2510 | Material Status | Create |  |  |  | 1-Step | Medium | open | Maxi
22.3 | 2510 | Material Status | File Download / Upload |  |  |  | General | Medium |  | Niklas | [6 empty] | done
22.4 | 2510 | Material Status | Data Export / Import |  |  |  | General | Medium |  | Niklas | [6 empty] | done
22.5 |  | Material Status | Language Test |  |  | DE/EN | General | Low |  | Maxi |  |  |  | n/a | n/a | n/a
22.6 |  | Material Status | Language Test |  |  | FR/ES | General | Low |  | Ulla
22.7 |  | Material Status | Language Test |  |  | ES | General | Low |  | Ulla
23.1 |  | Personnel Area | Change |  |  |  | 3-Step | Low |  | Maxi
23.2 |  | Personnel Area | Create |  |  |  | 3-Step | Low |  | Maxi
23.3 | 2510 | Personnel Area | File Download / Upload |  |  |  | General | Low |  | Patrick | [6 empty] | done
23.4 |  | Personnel Area | Data Export / Import |  |  |  | General | Low |  | Niklas | [6 empty] | done
23.5 |  | Personnel Area | Language Test |  |  | DE/EN | General | Low |  | Maxi |  |  |  | n/a | n/a | n/a
23.6 |  | Personnel Area | Language Test |  |  | FR/ES | General | Low |  | Ulla
23.7 |  | Personal Area | Language Test |  |  | ES | General | Medium |  | Michael
24.1 |  | Business Area | Change |  |  |  | 2-Step | High |  | Maxi
24.2 |  | Business Area | Create |  |  |  | 2-Step | High |  | Maxi
24.3 | 2510 | Business Area | File Download / Upload |  |  |  | General | Low |  | Patrick | [6 empty] | done
24.4 | 2510 | Business Area | Data Export / Import |  |  |  | General | Low |  | Patrick
24.5 |  | Business Area | Language Test |  |  | DE/EN | General | Low |  | Maxi |  |  |  | n/a | n/a | n/a
24.6 |  | Business Area | Language Test |  |  | FR/ES | General | Low |  | Ulla
24.7 |  | Business Area | Language Test |  |  | ES | General | Medium |  | Michael
25.1 | 2510 | Functional Area | Change |  |  |  | 1-Step | Medium | error | Ulla | Maxi |  | Change to Current Tester | open | open | open | error | done | done | open | open | open | open | open | open | open
25.2 | 2510 | Functional Area | Create |  |  |  | 1-Step | Medium | error | Ulla | Maxi |  | Change to Current Tester | open | open | open | error | done | done | open | open | open | open | open | open | open
25.3 | 2510 | Functional Area | File Download / Upload |  |  |  | General | Medium |  | Niklas | [6 empty] | done
25.4 | 2510 | Functional Area | Data Export / Import |  |  |  | General | Medium |  | Niklas | [6 empty] | done
25.5 |  | Functional Area | Language Test |  |  | DE/EN | General | Low |  | Maxi |  |  |  | n/a | n/a | n/a
25.6 |  | Functional Area | Language Test |  |  | FR/ES | General | Low |  | Ulla
25.7 |  | Functional Area | Language Test |  |  | ES | General | Low |  | Ulla
26.1 | 2510 | Incoterm | Change |  |  |  | 2-Step | High | open | Maxi | [6 empty] | done | done | done
26.2 | 2510 | Incoterm | Create |  |  |  | 2-Step | High | open | Maxi | [6 empty] | done | done | done
26.3 | 2510 | Incoterm | File Download / Upload |  |  |  | General | High | done | Niklas | [6 empty] | done | n/a | n/a
26.4 | 2510 | Incoterm | Data Export / Import |  |  |  | General | High | done | Niklas | [6 empty] | done | n/a | n/a
26.5 |  | Incoterm | Language Test |  |  | DE/EN | General | Low |  | Maxi |  |  |  | n/a | n/a | n/a
26.6 |  | Incoterm | Language Test |  |  | FR/ES | General | Low |  | Ulla
26.7 |  | Incoterm | Language Test |  |  | ES | General | Low |  | Ulla
27.1 | 2510 | Sales Group | Change |  |  |  | 2-Step | Medium | open | Maxi
27.2 | 2510 | Sales Group | Create |  |  |  | 2-Step | Medium | open | Maxi
27.3 | 2510 | Sales Group | File Download / Upload |  |  |  | General | Medium |  | Patrick | [6 empty] | done
27.4 | 2510 | Sales Group | Data Export / Import |  |  |  | General | Medium |  | Patrick | [6 empty] | done
27.5 |  | Sales Group | Language Test |  |  | DE/EN | General | Low |  | Maxi |  |  |  | n/a | n/a | n/a
27.6 |  | Sales Group | Language Test |  |  | FR/ES | General | Low |  | Ulla
27.7 |  | Sales Group | Language Test |  |  | ES | General | Low |  | Ulla
28.1 | 2510 | Shipping Type | Change |  |  |  | 2-Step | High | open | Maxi | [6 empty] | done | done | done
28.2 | 2510 | Shipping Type | Create |  |  |  | 2-Step | High | open | Maxi | [6 empty] | done | done | done
28.3 | 2510 | Shipping Type | File Download / Upload |  |  |  | General | High | done | Niklas |  | 0 |  |  |  |  | done | n/a | n/a
28.4 | 2510 | Shipping Type | Data Export / Import |  |  |  | General | High | done | Niklas | [6 empty] | done | n/a | n/a
28.5 |  | Shipping Type | Language Test |  |  | DE/EN | General | Low |  | Ulla |  |  |  | n/a | n/a | n/a
28.6 |  | Shipping Type | Language Test |  |  | FR/ES | General | Low |  | Ulla
28.7 |  | Shipping Type | Language Test |  |  | ES | General | Low |  | Ulla
29.1 | 2510 | Shipping Conditions | Change |  |  |  | 1-Step | High | open | Maxi | [6 empty] | done | done | done
29.2 | 2510 | Shipping Conditions | Create |  |  |  | 1-Step | High | open | Maxi | [6 empty] | done | done | done
29.3 | 2510 | Shipping Conditions | File Download / Upload |  |  |  | General | High | done | Niklas | [6 empty] | done | n/a | n/a
29.4 | 2510 | Shipping Conditions | Data Export / Import |  |  |  | General | High | done | Niklas | [6 empty] | done | n/a | n/a
29.5 |  | Shipping Conditions | Language Test |  |  | DE/EN | General | Low |  | Ulla |  |  |  | n/a | n/a | n/a
29.6 |  | Shipping Conditions | Language Test |  |  | FR/ES | General | Low |  | Ulla
29.7 |  | Shipping Conditions | Language Test |  |  | ES | General | Low |  | Ulla
30.1 | 2510 | Lab/office | Change |  |  |  | 3-Step | High | open | Maxi | [6 empty] | done | done | done
30.2 | 2510 | Lab/office | Create |  |  |  | 3-Step | High | open | Maxi | [6 empty] | done | done | done
30.3 | 2510 | Lab/Office | File Download / Upload |  |  |  | General | High | done | Niklas | [6 empty] | done | n/a | n/a
30.4 | 2510 | Lab/Office | Data Export / Import |  |  |  | General | High | done | Niklas | [6 empty] | done | n/a | n/a
30.5 |  | Lab/Office | Language Test |  |  | DE/EN | General | Low |  | Maxi |  |  |  | n/a | n/a | n/a
30.6 |  | Lab/Office | Language Test |  |  | FR/ES | General | Low |  | Ulla
30.7 |  | Lab/Office | Language Test |  |  | ES | General | Low |  | Ulla
31.1 |  | BOM Usage | Change |  |  |  | 3-Step | Low |  | Ulla
31.2 |  | BOM Usage | Create |  |  |  | 3-Step | Low |  | Ulla
31.3 | 2510 | BOM Usage | File Download / Upload |  |  |  | General | Low |  | Patrick | [6 empty] | done
31.4 | 2510 | BOM Usage | Data Export / Import |  |  |  | General | Low |  | Patrick | [6 empty] | done
31.5 |  | BOM Usage | Language Test |  |  | DE/EN | General | Low |  | Ulla |  |  |  | n/a | n/a | n/a
31.6 |  | BOM Usage | Language Test |  |  | FR/ES | General | Low |  | Ulla
31.7 |  | BOM Usage | Language Test |  |  | ES | General | Medium |  | Michael
32.1 | 2510 | Document Type | Create |  |  |  | 2-Step | Medium | open | Maxi
32.2 | 2510 | Document Type | Change |  |  |  | 2-Step | Medium | open | Maxi
32.3 | 2510 | Document Type | File Download / Upload |  |  |  | General | Medium |  | Patrick |  | 1092 |  |  |  |  | error
32.4 | 2510 | Document Type | Data Export / Import |  |  |  | General | Medium |  | Patrick
32.5 |  | Document Type | Language Test |  |  | DE/EN | General | Low |  | Ulla |  |  |  | n/a | n/a | n/a
32.6 |  | Document Type | Language Test |  |  | FR/ES | General | Low |  | Ulla
32.7 |  | Document Type | Language Test |  |  | ES | General | Low |  | Ulla
33.1 | 2510 | Chart of Account | Create |  |  |  | 1-Step | High | open | Maxi | [6 empty] | done | done | done
33.2 | 2510 | Chart of Account | Change |  |  |  | 1-Step | High | open | Maxi | [6 empty] | done | done | done
33.3 | 2510 | Chart of Account | File Download / Upload |  |  |  | General | High | done | Niklas | [6 empty] | done | n/a | n/a
33.4 | 2510 | Chart of Account | Data Export / Import |  |  |  | General | High | done | Niklas | [6 empty] | done | n/a | n/a
33.5 |  | Chart of Account | Language Test |  |  | DE/EN | General | Low |  | Ulla |  |  |  | n/a | n/a | n/a
33.6 |  | Chart of Account | Language Test |  |  | FR | General | Low |  | Ulla
33.7 |  | Chart of Account | Language Test |  |  | ES | General | Low |  | Ulla
34.1 |  | Operating Concern | Create |  |  |  | 3-Step | Low |  | Maxi
34.2 |  | Operating Concern | Change |  |  |  | 3-Step | Low |  | Maxi
34.3. | 2510 | Operating Concern | File Download / Upload |  |  |  | General | Low |  | Patrick | [6 empty] | done
34.4. | 2510 | Operating Concern | Data Export / Import |  |  |  | General | Low |  | Patrick | [6 empty] | done
34.5 |  | Operating Concern | Language Test |  |  | DE/EN | General | Low |  | Maxi
34.6 |  | Operating Concern | Language Test |  |  | FR/ES | General | Low |  | Ulla
34.7 |  | Operating Concern | Language Test |  |  | ES | General | Medium |  | Michael
35.1. |  | Language | Create |  |  |  | 3-Step | Low |  | Maxi
35.2 |  | Language | Change |  |  |  | 3-Step | Low |  | Maxi
35.3 |  | Language | File Download / Upload |  |  |  | General | Very High | done | Niklas | [6 empty] | done
35.4 |  | Language | Data Export / Import |  |  |  | General | Very High | done | Niklas | [6 empty] | done
35.5 |  | Language | Language Test |  |  | DE/EN | General | Low |  | Ulla |  |  |  | n/a | n/a | n/a
35.6 |  | Language | Language Test |  |  | FR | General | Low |  | Ulla
35.7 |  |  | Language Test |  |  | ES | General | Medium |  | Michael
36.1 |  | Location | Change |  |  |  | 2-Step | Medium |  | Maxi
36.2 |  | Location | Create |  |  |  | 2-Step | Medium |  | Maxi
36.3 | 2510 | Location | File Download / Upload |  |  |  | General | Medium |  | Patrick | [6 empty] | done
36.4 | 2510 | Location | Data Export / Import |  |  |  | General | Medium |  | Patrick
36.5 |  | Location | Language Test |  |  | DE/EN | n.A. | Medium |  | Maxi |  |  |  | n/a | n/a | n/a
36.6 |  | Location | Language Test |  |  | FR/ES | General | Medium |  | Ulla
36.7 |  |  | Language Test |  |  | ES | General | Medium |  | Michael
37.1 |  | Exchange Rate | Create |  |  |  | 2-Step | Very High |  | Gerd
37.2 |  | Exchange Rate | Change |  |  |  | 2-Step | Very High |  | Thomas
37.2 |  | Exchange Rate | Change |  |  |  | General | Very High |  | Thomas
37.3 |  | Exchange Rate | Initial Load |  |  |  | General | Very High |  | Thomas
37.4 |  | Data Feed | n.A. |  |  |  | General | Very High |  | Thomas
37.5 |  | Exchange Rate | Language Test |  |  | DE/EN | General | Medium |  | Ulla |  |  |  | n/a | n/a | n/a
37.6 |  | Exchange Rate | Language Test |  |  | FR/ES | General | Medium |  | Ulla
37.7 |  | Exchange Rate | Language Test |  |  | ES | General | Medium |  | Michael
38.1 | 2510 | Characteristic | Change |  |  |  | General | Very High | error | Sabine | [6 empty] | error | done | done
38.2 | 2510 | Characteristic | Create |  |  |  | General | Very High | error | Sabine | [6 empty] | error | done | done
38.3 | 2510 | Characteristic | Copy |  |  |  | General | Very High | error | Sabine | [6 empty] | error | done | done
38.4 |  | Characteristics | File Download / Upload |  |  |  | General | High | done | Niklas | [6 empty] | done
38.5 |  | Characteristics | Load IDoc |  |  |  | General | Low |  | Michael
38.6 |  | Characteristics | Language Test |  |  | DE/EN | General | Very High |  | Ulla
38.7 |  | Characteristics | Language Test |  |  | FR/ES | General | Very High |  | Ulla
38.8 |  | Characteristics | Language Test |  |  | ES | General | Medium |  | Michael
39.1 | 2510 | Class | Change |  |  |  | General | Very High | error | Sabine |  | 1069, 1066 |  |  |  |  | error | done | done
39.2 | 2510 | Class | Create |  |  |  | General | Very High | error | Sabine | [6 empty] | error | done | done
39.3 | 2510 | Class | Copy |  |  |  | General | Very High | done | Sabine |  |  |  | n/a | n/a | n/a | done | done | done | n/a | n/a | n/a | n/a | n/a | n/a | n/a
39.4 | 2511 | Class | File Download / Upload |  |  |  | General | High | error | Niklas |  | 1070 |  |  |  |  | In Progress
39.5 | 2511 | Class | Load IDoc |  |  |  | General | Low |  | Michael
39.6 |  | Classes | Language Test |  |  | DE/EN | General | High |  | Maxi |  |  |  | n/a | n/a | n/a
39.7 |  | Classes | Language Test |  |  | FR/ES | General | Very High |  | Ulla
39.8 |  | Classes | Language Test |  |  | ES | General | Medium |  | Michael
40.1 | 2510 | MRP Type | Change |  |  |  | 2-Step | High | open | Maxi | [6 empty] | done | done | done
40.2 | 2510 | MRP Type | Create |  |  |  | 2-Step | High | open | Maxi | [6 empty] | done | done | done
40.3 | 2510 | MRP Type | File Download / Upload |  |  |  | General | High | done | Niklas | [6 empty] | done | n/a | n/a
40.4 | 2510 | MRP Type | Data Export / Import |  |  |  | General | High | done | Niklas | [6 empty] | error | n/a | n/a
40.5 |  | MRP Type | Language Test |  |  | DE/EN | General | Low |  | Maxi |  |  |  | n/a | n/a | n/a
40.6 |  | MRP Type | Language Test |  |  | FR/ES | General | Low |  | Ulla
40.7 |  | MRP Type | Language Test |  |  | ES | General | Low |  | Ulla
41.1 | 2510 | MRP Profile | Change |  |  |  | 3-Step | Very High | in progress | Ulla | Maxi | [5 empty] | done | done | done
41.2 | 2510 | MRP Profile | Create |  |  |  | 3-Step | Very High | in progress | Ulla | Maxi | [5 empty] | done | done | done
41.3 | 2510 | MRP Profile | File Download / Upload |  |  |  | General | Very High | error | Niklas |  | 822 |  |  |  |  | error
41.4 | 2510 | MRP Profile | Data Export / Import |  |  |  | General | Very High | done | Niklas |  |  | 08.09.: Niklas schaut |  |  |  | done | n/a | n/a
41.5 |  | MRP Profile | Language Test |  |  | DE/EN | General | High |  | Ulla
41.6 |  | MRP Profile | Language Test |  |  | FR | General | Low |  | Ulla
41.7 |  | MRP Profile | Language Test |  |  | ES | General | Low |  | Ulla
42.1 | 2510 | MRP Area | Change |  |  |  | General | High | open | Maxi | [6 empty] | done | done | done
42.2 | 2510 | MRP Area | Create |  |  |  | General | High | open | Maxi | [6 empty] | done | done | done
42.3 | 2510 | MRP Area | File Download / Upload |  |  |  | General | High | error | Niklas |  | 1055, 1056 |  |  |  |  | error
42.4 | 2510 | MRP Area | Data Export / Import |  |  |  | General | High | done | Niklas | [6 empty] | done | n/a | n/a
42.5 |  | MRP Area | Language Test |  |  | DE/EN | General | Low |  | Ulla |  |  |  | n/a | n/a | n/a
42.5 |  | MRP Aree | Language Test |  |  | FR/ES | General | Low |  | Ulla
42.7 |  | MRP Area | Language Test |  |  | ES | General | Low |  | Ulla
43.1 |  | Tax Code | Change |  |  |  | General | Very High |  | Sabine
43.2 |  | Tax Code | Create |  |  |  | General | Very High |  | Sabine
43.3 |  | Tax Code | File Download / Upload |  |  |  | General | High | done | Niklas | [6 empty] | done
43.4 |  | Tax Code | Data Export / Import |  |  |  | General | High | done | Niklas | [6 empty] | done
43.5 |  | Tax Code | Language Test |  |  | DE/EN | General | Medium |  | Maxi |  |  |  | n/a | n/a | n/a
43.6 |  | Tax Code | Language Test |  |  | FR/ES | General | Medium |  | Ulla
43.7 |  | Tax Code | Language Test |  |  | ES | General | Medium |  | Michael
44.1 | 2510 | Valuation Class | Change |  |  |  | 2-Step | Medium | open | Maxi
44.2 | 2510 | Valuation Class | Create |  |  |  | 2-Step | Medium | open | Maxi
44.3 | 2510 | Valuation Class | File Download / Upload |  |  |  | General | Medium |  | Patrick | [6 empty] | done
44.4 | 2510 | Valuation Class | Data Export / Import |  |  |  | General | Medium |  | Patrick | [6 empty] | done
44.5 |  | Valuation Class | Language Test |  |  | DE/EN | General | Low |  | Ulla
44.6 |  | Valuation Class | Language Test |  |  | FR/ES | General | Low |  | Ulla
44.7 |  | Valuation Class | Language Test |  |  | ES | General | Low |  | Ulla
45.1 | 2510 | Sales Office | Change |  |  |  | General | High | error | Ulla | Maxi | 1061 | Change to Current Tester | open | open | open | done | error | error | open | open | open | open | open | open | open
45.2 | 2510 | Sales Office | Create |  |  |  | General | High | open | Maxi | [6 empty] | done | done | done
45.3 | 2510 | Sales Office | File Download / Upload |  |  |  | General | High | error | Niklas |  | 1051 | 08.09.: Niklas ist dran - Mike hat übernommen |  |  |  | error
45.4 | 2510 | Sales Office | Data Export / Import |  |  |  | General | High | done | Niklas | [6 empty] | done | n/a | n/a
45.5 |  | Sales Office | Language Test |  |  | DE/EN | General | Low |  | Ulla
45.6 |  | Sales Office | Language Test |  |  | FR/ES | General | Low |  | Ulla
45.7 |  | Sales Office | Language Test |  |  | ES | General | Low |  | Ulla
46.1 | 2510 | Scope of Planning | Change |  |  |  | General | High | open | Maxi | [6 empty] | done | done | done
46.2 | 2510 | Scope of Planning | Create |  |  |  | General | High | open | Maxi | [6 empty] | done | done | done
46.3 | 2510 | Scope of Planning | File Download / Upload |  |  |  | General | High | done | Niklas | [6 empty] | done | n/a | n/a
46.4 | 2510 | Scope of Planning | Data Export / Import |  |  |  | General | High | done | Niklas | [6 empty] | done
46.5 |  | Scope of Planning | Language Test |  |  | DE/EN | General | Low |  | Ulla
46.6 |  | Scope of Planning | Language Test |  |  | FR/ES | General | Low |  | Ulla
46.7 |  | Scope of Planning for MRP Unit | Language Test |  |  | ES | General | Low |  | Ulla
47.1 | 2510 | MRP Controller | Change |  |  |  | General | High | open | Maxi | [6 empty] | done | done | done
47.2 | 2510 | MRP Controller | Create |  |  |  | General | High | open | Maxi | [6 empty] | done | done | done
47.3 | 2510 | MRP Controller | File Download / Upload |  |  |  | 2-Step | High | error | Niklas |  | 1052 |  |  |  |  | error
47.4 | 2510 | MRP Controller | Data Export / Import |  |  |  | General | High | done | Niklas | [6 empty] | done
47.5 |  | MRP Controller | Language Test |  |  | DE/EN | General | Low |  | Ulla |  |  |  | n/a | n/a | n/a
47.6 |  | MRP Controller | Language Test |  |  | FR/ES | General | Low |  | Ulla
47.7 |  | MRP Controller | Language Test |  |  | ES | General | Low |  | Ulla
48.1 |  | Holiday Calendar | Change |  |  |  | n.A. | Very High |  | Maxi
48.2 |  | Holiday Calendar | Create |  |  |  | n.A. | Very High |  | Maxi
48.3 |  | Holiday Calendar | File Download / Upload |  |  |  | n.A. | Very High | done | Niklas | [6 empty] | done
48.4 |  | Holiday Calendar | Data Export / Import |  |  |  | n.A. | Very High | done | Niklas | [6 empty] | done
48.5 |  | Holiday Calendar | Language Test |  |  | DE/EN/FR/ES | n.A. | Very High |  | Maxi
49.1 |  | Public Holiday | Change |  |  |  | n.A. | Very High |  | Maxi
49.2 |  | Public Holiday | Create |  |  |  | n.A. | Very High |  | Maxi
49.3 |  | Public Holiday | File Download / Upload |  |  |  | n.A. | Very High | done | Niklas | [6 empty] | done
49.4 |  | Public Holiday | Data Export / Import |  |  |  | n.A. | Very High | done | Niklas | [6 empty] | done
49.5 |  | Public Holiday | Language Test |  |  | DE/EN/FR/ES | n.A. | Very High |  | Maxi
50.1 | 2511 | Work Breakdown Structure | Change | [6 empty] | Sabine
50.2 | 2511 | Work Breakdown Structure | Create | [6 empty] | Sabine
50.3 | 2511 | Work Breakdown Structure | File Download / Upload | [6 empty] | Sabine
50.4 | 2511 | Work Breakdown Structure | Data Export / Import | [6 empty] | Sabine
50.5 | 2511 | Work Breakdown Structure | Language Test |  |  | DE/EN/FR/ES |  |  |  | Ulla
50.1 | 2510 | Posting Period Variant | Change |  |  |  |  | Very High | in progress | Sabine |  |  |  | in progress
50.2 | 2510 | Posting Period Variant | Create |  |  |  |  | Very High | in progress | Sabine |  |  |  | in progress
50.3 | 2510 | Posting Period Variant | File Download / Upload |  |  |  |  | Very High | in progress | Niklas |  |  |  | done
50.4 | 2510 | Posting Period Variant | Data Export / Import |  |  |  |  | Very High | in progress | Niklas |  |  |  | done
50.5 | 2510 | Posting Period Variant | Language Test |  |  | DE/EN/FR/ES |  | Very High | in progress | Ulla |  |  |  | in progress
50.1 | 2510 | Company | Change |  |  |  |  | Very High | in progress | Sabine |  |  |  | in progress
50.2 | 2510 | Company | Create |  |  |  |  | Very High | in progress | Sabine |  |  |  | in progress
50.3 | 2510 | Company | File Download / Upload |  |  |  |  | Very High | in progress | Niklas |  |  |  | done
50.4 | 2510 | Company | Data Export / Import |  |  |  |  | Very High | in progress | Niklas |  |  |  | done
50.5 | 2510 | Company | Language Test |  |  | DE/EN/FR/ES |  | Very High | in progress | Ulla |  |  |  | in progress
100.0 RDG Multiobject |  | ******************************************* | n.A. |  |  |  | n.A. | *********
101.1 | 2510 | Posting Period Variant & Company & Company Code | Change |  |  |  |  | Very High | in progress | Sabine |  |  |  | in progress
101.2 | 2510 | Posting Period Variant & Company & Company Code | Create |  |  |  |  | Very High | in progress | Sabine |  |  |  | in progress
102.1 | 2510 | Payment Term & Day Limit | Change |  |  |  |  | High | in progress | Ulla
102.2 | 2510 | Payment Term & Day Limit | Create |  |  |  |  | High | in progress | Ulla
103.1 | 2510 | Plant & MRP Area & Storage Location | Change |  |  |  |  | High | in progress | Ulla
103.2 | 2510 | Plant & MRP Area & Storage Location | Create |  |  |  |  | High | in progress | Ulla
750.0 MDF |  | ******************************************* | n.A. |  |  |  | n.A. | *********
750.1 RULE | 2510 | Configuration | n.A. |  |  |  | General | Medium |  | Ulla
751.1 MDF | 2510 | ValueMapping | n.A. |  |  |  | General | Medium |  | Maxi
752.1 MDF | 2510 | KeyMapping | n.A. |  |  |  | General | Medium |  | Maxi
753.1 MDF |  | Webservice | n.A. |  |  |  | General | Low |  | Michael
754.1 MDF |  | Deletions | n.A. |  |  |  | General | Very High |  | Thomas
755.1 MDF |  | Searchhelps | n.A. |  |  |  | General | Very High |  | Gerd
800.0 RDH |  | ******************************************* | n.A. |  |  |  | n.A. | *********
801 RDH |  | Reference Data Harmonization | Distribution reference data balance sheet structure (Mode=Bundle, Changes in Batchjob) |  |  |  | General | Very High |  | Gerd
802 RDH |  | Reference Data Harmonization | Distribution reference data balance sheet structure (Mode=Bundle, Changes) |  |  |  | General | Medium
803 RDH |  | Reference Data Harmonization | Distribution reference Accounts (Mode=Snapshot) |  |  |  | General | Medium
804 RDH |  | Reference Data Harmonization | Distribution balance sheet structure (Mode=Bundle) |  |  |  | General | Medium
805 RDH |  | Reference Data Harmonization | Distribution balance sheet structure (Mode=Single) |  |  |  | General | Medium
806 RDH |  | Reference Data Harmonization | Distribution Company_ID (Mode=Bundle) |  |  |  | General | Medium
807 RDH |  | Reference Data Harmonization | Distribution Company_Id (Mode=Bundle with Field reduction) |  |  |  | General | Medium
808 RDH |  | Reference Data Harmonization | Distribution Company (Mode=Single) |  |  |  | General | Medium
809 RDH |  | Reference Data Harmonization | Distribution Currency (Mode=SnapShot) |  |  |  | General | Medium
810 RDH |  | Reference Data Harmonization | Customizing Replication |  |  |  | General | Medium
811 RDH | 2510 | Reference Data Harmonization | Select Transport |  |  |  | General | High |  | Gerd
812 RDH | 2510 | Reference Data Harmonization | Foreign data transfer with Excel import |  |  |  | General | High |  | Gerd
850.0 Install & Upgrade |  | ******************************************* | n.A. |  |  |  | n.A. | *********
851.1 INST |  | Install | n.A. |  |  |  | General | Very High |  | Dieter
852.1 OLD Release Check |  | Check Replication to older | n.A. |  |  |  | General | Very High |  | Michael
853.1 UPGR |  | Upgrade | n.A. |  |  |  | General | Very High |  | Dieter
900.0 Special Tests |  | ******************************************* | n.A. |  |  |  | n.A. | *********
901.1 DRF | 2510 | Data Replication | n.A. |  |  |  | General | Medium |  | Maxi
902.1 ENH |  | Enhancements and Upgrade | n.A. |  |  |  | General | Very High |  | Mike
903.1 FR/ES |  | Translation to FR/ES | Language Test |  |  | MDF, RDH, DRF | General | Medium |  | Ulla
904.1 SOLMAN |  | SolManager Tests | n.A. |  |  |  | General | Low |  | Michael
905.1 GTS | 2510 | GTS Tests | n.A. |  |  |  | 1-Step | Medium |  | Michael
99.1 |  | Material Group | UI Testing |  |  |  | General | High | n/a
99.10 |  | Country | UI Testing |  |  |  | General | High | n/a
99.100 |  | Lab/Office | UI Testing |  |  |  | General | High | n/a
99.101 |  | BOM Usage | UI Testing |  |  |  | General | High | n/a
99.102 |  | BOM Usage | UI Testing |  |  |  | General | High | n/a
99.103 |  | BOM Usage | UI Testing |  |  |  | General | High | n/a
99.104 |  | Document Type | UI Testing |  |  |  | General | High | n/a
99.105 |  | Document Type | UI Testing |  |  |  | General | High | n/a
99.106 |  | Document Type | UI Testing |  |  |  | General | High | n/a
99.107 |  | Chart of Account | UI Testing |  |  |  | General | High | n/a
99.108 |  | Chart of Account | UI Testing |  |  |  | General | High | n/a
99.109 |  | Chart of Account | UI Testing |  |  |  | General | High | n/a
99.11 |  | Region | UI Testing |  |  |  | General | High | n/a
99.110 |  | Operating Concern | UI Testing |  |  |  | General | High | n/a
99.111 |  | Operating Concern | UI Testing |  |  |  | General | High | n/a
99.112 |  | Operating Concern | UI Testing |  |  |  | General | High | n/a
99.113 |  | Language | UI Testing |  |  |  | General | High | n/a
99.114 |  | Language | UI Testing |  |  |  | General | High | n/a
99.115 |  |  | UI Testing |  |  |  | General | High | n/a
99.116 |  | Location | UI Testing |  |  |  | General | High | n/a
99.117 |  | Location | UI Testing |  |  |  | General | High | n/a
99.118 |  | Location | UI Testing |  |  |  | General | High | n/a
99.119 |  | Exchange Rate | UI Testing |  |  |  | General | High | n/a
99.12 |  | Region | UI Testing |  |  |  | General | High | n/a
99.120 |  | Data Feed | UI Testing |  |  |  | General | High | n/a
99.121 |  | Exchange Rate | UI Testing |  |  |  | General | High | n/a
99.122 |  | Characteristics | UI Testing |  |  |  | General | High | n/a
99.123 |  | Characteristics | UI Testing |  |  |  | General | High | n/a
99.124 |  | Characteristics | UI Testing |  |  |  | General | High | n/a
99.125 |  | Class | UI Testing |  |  |  | General | High | n/a
99.126 |  | Class | UI Testing |  |  |  | General | High | n/a
99.127 |  | MRP Type | UI Testing |  |  |  | General | High | n/a
99.128 |  | MRP Type | UI Testing |  |  |  | General | High | n/a
99.129 |  | MRP Profile | UI Testing |  |  |  | General | High | n/a
99.13 |  | Region | UI Testing |  |  |  | General | High | n/a
99.130 |  | MRP Profile | UI Testing |  |  |  | General | High | n/a
99.131 |  | MRP Area | UI Testing |  |  |  | General | High | n/a
99.132 |  | MRP Area | UI Testing |  |  |  | General | High | n/a
99.133 |  | MRP Aree | UI Testing |  |  |  | General | High | n/a
99.134 |  | Tax Code | UI Testing |  |  |  | General | High | n/a
99.135 |  | Tax Code | UI Testing |  |  |  | General | High | n/a
99.136 |  | Tax Code | UI Testing |  |  |  | General | High | n/a
99.137 |  | Valuation Class | UI Testing |  |  |  | General | High | n/a
99.138 |  | Valuation Class | UI Testing |  |  |  | General | High | n/a
99.139 |  | Valuation Class | UI Testing |  |  |  | General | High | n/a
99.14 |  | Purchasing Group | UI Testing |  |  |  | General | High | n/a
99.140 |  | Sales Office | UI Testing |  |  |  | General | High | n/a
99.141 |  | Sales Office | UI Testing |  |  |  | General | High | n/a
99.142 |  | Sales Office | UI Testing |  |  |  | General | High | n/a
99.143 |  | Scope of Planning | UI Testing |  |  |  | General | High | n/a
99.144 |  | Scope of Planning | UI Testing |  |  |  | General | High | n/a
99.145 |  | Scope of Planning | UI Testing |  |  |  | General | High | n/a
99.146 |  | Scope of Planning for MRP Unit | UI Testing |  |  |  | General | High | n/a
99.147 |  | MRP Controller | UI Testing |  |  |  | General | High | n/a
99.148 |  | MRP Controller | UI Testing |  |  |  | General | High | n/a
99.149 |  | MRP Controller | UI Testing |  |  |  | General | High | n/a
99.15 |  | Purchasing Group | UI Testing |  |  |  | General | High | n/a
99.150 |  | Holiday Calendar | UI Testing |  |  |  | General | High | n/a
99.151 |  | Holiday Calendar | UI Testing |  |  |  | General | High | n/a
99.152 |  | Holiday Calendar | UI Testing |  |  |  | General | High | n/a
99.153 |  | Public Holiday | UI Testing |  |  |  | General | High | n/a
99.154 |  | Public Holiday | UI Testing |  |  |  | General | High | n/a
99.155 |  | Public Holiday | UI Testing |  |  |  | General | High | n/a
99.156 |  | Work Breakdown Structure | UI Testing |  |  |  | General | High | n/a
99.157 |  | Configuration | UI Testing |  |  |  | General | High | n/a
99.158 |  | ValueMapping | UI Testing |  |  |  | General | High | n/a
99.159 |  | KeyMapping | UI Testing |  |  |  | General | High | n/a
99.16 |  | Purchasing Group | UI Testing |  |  |  | General | High | n/a
99.160 |  | Webservice | UI Testing |  |  |  | General | High | n/a
99.161 |  | Deletions | UI Testing |  |  |  | General | High | n/a
99.162 |  | Searchhelps | UI Testing |  |  |  | General | High | n/a
99.163 |  | Reference Data Harmonization | UI Testing |  |  |  | General | High | n/a
99.164 |  | Install | UI Testing |  |  |  | General | High | n/a
99.165 |  | Check Replication to older | UI Testing |  |  |  | General | High | n/a
99.166 |  | Upgrade | UI Testing |  |  |  | General | High | n/a
99.167 |  | Data Replication | UI Testing |  |  |  | General | High | n/a
99.168 |  | Enhancements and Upgrade | UI Testing |  |  |  | General | High | n/a
99.169 |  | Translation to FR/ES | UI Testing |  |  |  | General | High | n/a
99.17 |  | Purchasing Organization | UI Testing |  |  |  | General | High | n/a
99.170 |  | SolManager Tests | UI Testing |  |  |  | General | High | n/a
99.171 |  | GTS Tests | UI Testing |  |  |  | General | High | n/a
99.18 |  | Purchasing Organization | UI Testing |  |  |  | General | High | n/a
99.19 |  | Purchasing Organization | UI Testing |  |  |  | General | High | n/a
99.2 |  | Material Group | UI Testing |  |  |  | General | High | n/a
99.20 |  | Purchasing Organizsation | UI Testing |  |  |  | General | High | n/a
99.21 |  | Account Group G/L | UI Testing |  |  |  | General | High | n/a
99.22 |  | Account Group G/L | UI Testing |  |  |  | General | High | n/a
99.23 |  | Account Group G/L - Scheduled LSA Subscriber | UI Testing |  |  |  | General | High | n/a
99.24 |  | Account Group GL | UI Testing |  |  |  | General | High | n/a
99.25 |  | Account Group | UI Testing |  |  |  | General | High | n/a
99.26 |  | Account Group Vendor | UI Testing |  |  |  | General | High | n/a
99.27 |  | Account Group Vendor | UI Testing |  |  |  | General | High | n/a
99.28 |  | Account Group Vendor | UI Testing |  |  |  | General | High | n/a
99.29 |  | Vendor Account Group | UI Testing |  |  |  | General | High | n/a
99.3 |  | Material Group | UI Testing |  |  |  | General | High | n/a
99.30 |  | Account Group Customer | UI Testing |  |  |  | General | High | n/a
99.31 |  | Account Group Customer | UI Testing |  |  |  | General | High | n/a
99.32 |  | Account Group Customer | UI Testing |  |  |  | General | High | n/a
99.33 |  | Customer Account Group | UI Testing |  |  |  | General | High | n/a
99.37 |  | Company Code | UI Testing |  |  |  | General | High | n/a
99.38 |  | Company Code | UI Testing |  |  |  | General | High | n/a
99.39 |  | Company Code | UI Testing |  |  |  | General | High | n/a
99.4 |  | Material Group Text | UI Testing |  |  |  | General | High | n/a
99.40 |  | Company code | UI Testing |  |  |  | General | High | n/a
99.41 |  | Plant | UI Testing |  |  |  | General | High | n/a
99.42 |  | Plant | UI Testing |  |  |  | General | High | n/a
99.43 |  | Plant | UI Testing |  |  |  | General | High | n/a
99.44 |  | Payment Term | UI Testing |  |  |  | General | High | n/a
99.45 |  | Payment Term | UI Testing |  |  |  | General | High | n/a
99.46 |  | Payment Term | UI Testing |  |  |  | General | High | n/a
99.47 |  | Payment Ferm | UI Testing |  |  |  | General | High | n/a
99.48 |  | Currency Code | UI Testing |  |  |  | General | High | n/a
99.49 |  | Currency Code | UI Testing |  |  |  | General | High | n/a
99.5 |  | Unit of Measure | UI Testing |  |  |  | General | High | n/a
99.50 |  | Currency Code | UI Testing |  |  |  | General | High | n/a
99.51 |  | Sales Organization | UI Testing |  |  |  | General | High | n/a
99.52 |  | Sales Organization | UI Testing |  |  |  | General | High | n/a
99.53 |  | Sales Organization | UI Testing |  |  |  | General | High | n/a
99.54 |  | Sales Organisation | UI Testing |  |  |  | General | High | n/a
99.55 |  | Material Type | UI Testing |  |  |  | General | High | n/a
99.56 |  | Material Type | UI Testing |  |  |  | General | High | n/a
99.57 |  | Material Type | UI Testing |  |  |  | General | High | n/a
99.58 |  | Storage Location | UI Testing |  |  |  | General | High | n/a
99.59 |  | Storage Location | UI Testing |  |  |  | General | High | n/a
99.6 |  | Unit of Measure | UI Testing |  |  |  | General | High | n/a
99.60 |  | Storage Location | UI Testing |  |  |  | General | High | n/a
99.61 |  | Division | UI Testing |  |  |  | General | High | n/a
99.62 |  | Division | UI Testing |  |  |  | General | High | n/a
99.63 |  | Division | UI Testing |  |  |  | General | High | n/a
99.64 |  | Factory Calendar | UI Testing |  |  |  | General | High | n/a
99.65 |  | Factory Calendar | UI Testing |  |  |  | General | High | n/a
99.66 |  | Factory Calendar | UI Testing |  |  |  | General | High | n/a
99.67 |  | Distribution Channel | UI Testing |  |  |  | General | High | n/a
99.68 |  | Distribution Channel | UI Testing |  |  |  | General | High | n/a
99.69 |  | Distribution Channel | UI Testing |  |  |  | General | High | n/a
99.7 |  | Unit of Measure | UI Testing |  |  |  | General | High | n/a
99.70 |  | Controlling Area | UI Testing |  |  |  | General | High | n/a
99.71 |  | Controlling Area | UI Testing |  |  |  | General | High | n/a
99.72 |  | Controlling Area | UI Testing |  |  |  | General | High | n/a
99.73 |  | Material Status | UI Testing |  |  |  | General | High | n/a
99.74 |  | Material Status | UI Testing |  |  |  | General | High | n/a
99.75 |  | Material Status | UI Testing |  |  |  | General | High | n/a
99.76 |  | Personnel Area | UI Testing |  |  |  | General | High | n/a
99.77 |  | Personnel Area | UI Testing |  |  |  | General | High | n/a
99.78 |  | Personnel Area | UI Testing |  |  |  | General | High | n/a
99.79 |  | Personal Area | UI Testing |  |  |  | General | High | n/a
99.8 |  | Country | UI Testing |  |  |  | General | High | n/a
99.80 |  | Business Area | UI Testing |  |  |  | General | High | n/a
99.81 |  | Business Area | UI Testing |  |  |  | General | High | n/a
99.82 |  | Business Area | UI Testing |  |  |  | General | High | n/a
99.83 |  | Functional Area | UI Testing |  |  |  | General | High | n/a
99.84 |  | Functional Area | UI Testing |  |  |  | General | High | n/a
99.85 |  | Functional Area | UI Testing |  |  |  | General | High | n/a
99.86 |  | Incoterm | UI Testing |  |  |  | General | High | n/a
99.87 |  | Incoterm | UI Testing |  |  |  | General | High | n/a
99.88 |  | Incoterm | UI Testing |  |  |  | General | High | n/a
99.89 |  | Sales Group | UI Testing |  |  |  | General | High | n/a
99.9 |  | Country | UI Testing |  |  |  | General | High | n/a
99.90 |  | Sales Group | UI Testing |  |  |  | General | High | n/a
99.91 |  | Sales Group | UI Testing |  |  |  | General | High | n/a
99.92 |  | Shipping Type | UI Testing |  |  |  | General | High | n/a
99.93 |  | Shipping Type | UI Testing |  |  |  | General | High | n/a
99.94 |  | Shipping Type | UI Testing |  |  |  | General | High | n/a
99.95 |  | Shipping Conditions | UI Testing |  |  |  | General | High | n/a
99.96 |  | Shipping Conditions | UI Testing |  |  |  | General | High | n/a
99.97 |  | Shipping Conditions | UI Testing |  |  |  | General | High | n/a
99.98 |  | Lab/office | UI Testing |  |  |  | General | High | n/a
99.99 |  | Lab/Office | UI Testing |  |  |  | General | High | n/a
Note on E3: Thomas Marx: C = Code Value List T = Timedependent Code Value List

## Open Topics
Object Type | Issue Number | Goal | Created at (via Makro) | Description | Issue Priority | Status | Folder | Reporter | Responsible
Material Group | 522 | 2512 |  | Material Group Division Value Help Missing | High | NEW | Link | Maren | Mike
Classes | 523 | 2512 |  | Classes missing F4 Help for Doc Type | Low | NEW | Link | Niklas | Dieter
Sales Office | 524 | 2512 |  | Upload Field Error for Sales Office and Location | High | NEW | Link | Niklas | Dieter
| 541 | 2511 |  | Data Export and Import: Add new attributes | High | IN PROCESS | Link | Michael | Niklas
Material Status | 544 | 2512 |  | Material Status - Cross-plant settings aren't saved | High | NEW | Link | Maxi
RDH, Functional Area | 583 | 2512 |  | RDH: Client check erro | High | NEW | Link | Gerd | Frank
Tax Code | 592 | 2512 |  | “Search Criteria” for the tax code object does not display the tax codes from the RDM | Low | NEW | Link | Gerd | Mike
all object types | 613 | 2511 |  | BRF Content in German | Low | IN PROCESS | Link | Michael | Dieter
all object types | 614 | 2511 |  | BRF Content Mismatch | Low | IN PROCESS | Link | Michael | Dieter
| 616 | 2512 |  | Deletion not working with manual replication | Medium | NEW | Link | Michael | Frank
MRP Profile | 620 | 2512 |  | MRP Profile Check Box import is not working correct | Medium | NEW | Link | Niklas | Dieter
Plant and more | 625 | 2511 |  | Allow Changeable Keys | High | IN PROCESS | Link |  | Michael
Payment Term | 626 | 2512 |  | Payment Term Own Explanation deletion | High | NEW | Link | Michael | ?
Payment Term | 627 | 2512 |  | Local Scope Payment Terms and maybe more | High | NEW | Link | Michael | ?
Payment Term | 628 | 2512 |  | Payment Term Avoid non Numeric entry for Daylimit | Medium | NEW | Link | Michael
Payment Term | 629 | 2512 |  | Payment Term avoid higher discount for later payment | Medium | NEW | Link | Michael
all object types | 630 | 2512 |  | Data Model Activation clears NoExistency Check Field | High | NEW | Link | Michael | Frank?
all object types | 638 | 2512 |  | suggestions to improve the user-friendliness of PF4 development | Medium | NEW | Link | Michael | Frank
Payment Term | 657 | 2512 |  | PaymentermDetails_PF4-Checkbox Description not listed | Medium | NEW | Link | Gerd | Frank
| 684 | 2512 |  | Text Fields missing | Medium | NEW | Link | Michael
Planning Scope | 701 | 2511 |  | Planning Scope, Deletion from Sequence not always possible | High | IN PROCESS | Link | Michael | Frank
Payment Term | 702 | 2511 |  | Payment Term Data Replication fails | High | IN PROCESS | Link | Michael | Mike
| 706 | 2512 |  | Automatic Filling Attribut Analysis - all object types | Medium | NEW | Link | Michael | Mike
Material Group | 710 | 2512 |  | Material Group Text Deletion | Medium | NEW | Link | Michael | Frank
Tax Code | 712 | 2512 |  | RDM Object Tax Code-Type requires Must field | Medium | NEW | Link | Gerd | Mike
| 714 | 2512 |  | Text field length limitation | Medium | NEW | Link | Gerd | Grigor
Sales Office | 715 | 2512 |  | Sales Office Data Replication Direct Update and Webservice fails | Medium | NEW | Link | Michael
Personnel Area | 716 | 2512 |  | RDM Object Personnel area missing PF4 search help country code | Low | NEW | Link | Gerd | Mike
Unit of Measure | 722 | 2511 |  | UoM Validation Issue | Medium | IN PROCESS | Link | Frank/Michael | Gerd
| 724 | 2512 |  | Analayze BP adapter classes for single request and create class for land | Medium | NEW | Link | Niklas | Niklas
Chart of Accounts | 729 | 2511 |  | RDM Object Chart Of Accounts PF4 Revise picklists | Medium | IN PROCESS | Link | Gerd | Frank
Exchange Rate | 730 | 2512 |  | RDM Object Currency Exchange Rates PF4 Revise picklists | Medium | NEW | Link | Gerd | Frank
Characteristic | 731 | 2511 |  | RDM Object Characteristics PF4 Revise picklists | Medium | IN PROCESS | Link | Gerd | Frank
Tax Code | 734 | 2511 |  | RDM Object Tax Code PF4 Revise picklists | Medium | IN PROCESS | Link | Gerd | Frank
MRP Controller | 739 | 2512 |  | RDM Object Valuation MRP Controller PF4 Revise picklist Business Area | Medium | NEW | Link | Gerd | Frank
| 743 | 2512 |  | Textfields missing (all object types to be checked) | Medium | NEW | Link |  | Grigor
| 744 | 2512 |  | DataFeed Interface Additional checkbox valid the following day | Medium | NEW | Link | Gerd/Thomas | Frank
Controlling Area | 760 | 2512 |  | Controlling Area Missing Checkbox Values in Receiver Data | High | NEW | Link | Maxi
| 761 | 2511 |  | Not authorized to use Import transactions | Medium | IN PROCESS | Link | Niklas | Günter
Characteristic | 765 | 2511 |  | Characteristics – Issue with parameter of error message | Medium | IN PROCESS | Link | Sabine | Michael
Language | 767 | 2511 |  | Language Key - IR1200 - LSA Report Error | Medium | IN PROCESS | Link | Maxi | Frank
all object types | 773 | 2511 |  | Missing role for MDF configuration | Medium | IN PROCESS | Link | Ulla
Material Group | 786 | 2512 |  | RDM Object Material Group PF4 Revise picklists Language key | Medium | NEW | Link | Gerd | Frank
Country | 787 | 2512 |  | RDM Object Country PF4 Revise picklists Currencies | Medium | NEW | Link | Gerd | Frank
Company Code | 788 | 2512 |  | RDM Object Company Code PF4 Revise picklists Country_Region | Medium | NEW | Link | Gerd | Frank
| 791 | 2511 |  | Interval for source values not evaluated in derivation | Medium | IN PROCESS | Link | Sabine | Michael
Storage Location | 792 | 2512 |  | IR1200 Storage Location Cust table only in cloud edition | Medium | NEW | Link | Ulla | Frank
Translation | 796 | 2511 |  | FR MDF some translations missing in IH1 | Low | IN PROCESS | Link | Ulla | Ulla
Translation | 797 | 2511 |  | ES RDH not translated | Low | IN PROCESS | Link | Ulla | Ulla
MRP Profile | 802 | 2512 |  | MRP Profile - "Reorder level requires MRP type" but it is not Maintainable in Data Screen 1 / 2 | Medium | NEW | Link | Maxi | Mike
MRP Profile | 803 | 2512 |  | MRP Profile - Minimum Safety Stock can be > Safety Stock | High | NEW | Link | Maxi | Dieter
all | 807 | 2511 |  | Classes - wrong CR status after withdrawal | Medium | IN PROCESS | Link | Sabine | Dieter
Characteristic | 809 | 2511 |  | Characteristics – characteristics name of copy overwrites existing characteristic while changing any characteristic | High | IN PROCESS | Link | Sabine | Mike
| 813 | 2511 |  | Issue 763 has also wrong desciptions of table /ITR/LSA_TABST. This ticket has been created to split the two topics into two issues | Medium | IN PROCESS | Link | Frank | Ulla
Translation | 819 | 2512 |  | ES Specific - Missing / Faulty Translations Clustered | Low | NEW | Link | Maxi | Ulla
Location | 820 | 2512 |  | Location - Field Key of transfer structure is unknown | Medium | NEW | Link | Niklas | Dieter
Translation | 821 | 2512 |  | FR /ES - Missing Translations Clustered | Low | NEW | Link | Maxi | Ulla
MRP Profile | 822 | 2512 |  | MRP Profile - Select at leaset one checkbox for MRP Profile creation | Medium | NEW | Link | Niklas | Dieter
Translation | 824 | 2512 |  | FR Specific - Missing / Faulty Translations Clustered | Low | NEW | Link | Maxi
Language | 828 | 2512 |  | RDM Object Shipping Type PF4 Revise picklists Language | Medium | NEW | Link | Gerd | Frank
Customer Account Group | 830 | 2512 |  | Customer Account group to many fields in Upload | Low | NEW | Link | Niklas | Dieter
Sales Organization | 832 | 2512 |  | Sales Organization - Withdrawal of change request does not work | Medium | NEW | Link | Sabine | Dieter
Sales Organization | 836 | 2512 |  | Sales Organization - missing check for combination storage location plant | Medium | NEW | Link | Sabine
Company Code | 838 | 2512 |  | Company Code – mandatory field country not taken over into address screen – results in replication inconsistency | Medium | NEW | Link | Sabine
Company Code | 839 | 2512 |  | Company Code – no check for mandatory field currency – no inconsistency shown | Medium | NEW | Link | Sabine
Operating Concern | 840 | 2512 |  | Operating Concern - Missing Translations in DE / FR / ES | Low | NEW | Link | Maxi
Classes | 842 | 2512 |  | Classes - DE FR ES Translation Issues | Low | NEW | Link | Maxi
MRP Profile | 843 | 2512 |  | DE FR ES Translation -MRP Profile - Missing or Faulty Translations | Medium | NEW | Link | Maxi
Tax Code | 844 | 2512 |  | FR ES Translation - Tax Code - Missing or Faulty Translations | Low | NEW | Link | Maxi
Region | 845 | 2512 |  | RDM Object Region PF4 Revise picklists Language | Medium | NEW | Link | Gerd | Frank
Operating Concern | 846 | 2512 |  | Operating Concern - Missing Field Check for Key | Medium | NEW | Link | Maxi
Sales Organization | 848 | 2512 |  | RDM Object Sales Organization PF4 Revise picklists Storage location | Medium | NEW | Link | Gerd | Frank
several | 849 | 2512 |  | MDF Validation Internal Server Error for Source field interval | Medium | NEW | Link | Ulla
Planning Scope | 850 | 2512 |  | Scope of Planning – incomplete change documents | High | NEW | Link | Sabine
Planning Scope | 851 | 2512 |  | Scope of Planning – search criteria plant and MRP area do not work together | Low | NEW | Link | Sabine
Characteristic | 854 | 2511 |  | Characterstics - Catalog Char. - Plant ERP S4 Help + Set Missing S4 Help | High | IN PROCESS | Link | Maxi | Frank
Functional Area | 856 | 2512 |  | Functional Area - handling of descriptions that are too long - message USMD | Medium | NEW | Link | Sabine
Plant | 859 | 2512 |  | RDM Object Plant PF4 Revise picklists Language Key | Medium | NEW | Link | Gerd | Frank
Tax Code | 862 | 2512 |  | Tax Code FR Translation: some fields in german | Low | NEW | Link | Ulla | Ulla
Language | 864 | 2512 |  | RDM Object Material Type PF4 Revise picklists Language Key | Medium | NEW | Link | Gerd | Frank
Classes | 865 | 2512 |  | RDM Object Material Type PF4 Revise picklists CLASS | Medium | NEW | Link | Gerd | Frank
MRP Profile | 867 | 2512 |  | IH1400 (other systems to be tested) - MRP Profile -Direct Table - Not replicated Fields | High | NEW | Link | Maxi | Frank
Factory Calendar | 868 | 2512 |  | IH1100 - Factory Calendar - Validity Area Maintainable outside 2000 - 2050 | Medium | NEW | Link | Maxi
Unit of Measure | 869 | 2512 |  | RDM Object Unit of Measure PF4- Unit of Measure Picklist UoM ExtTexts | Medium | NEW | Link | Gerd | Frank
Factory Calendar | 870 | 2512 |  | IH1100 - Factory Calendar - Holiday Calendar maintainable even though no free days | Medium | NEW | Link | Maxi
Unit of Measure | 871 | 2511 |  | IH1100 - Unit of Meassure - Small Description Name Issue | Low | IN PROCESS | Link | Maxi | Maxi / Mike
Unit of Measure | 875 | 2512 |  | ALL RECEIVER - Unit of Meassure - Direct Table | Medium | NEW | Link | Maxi | Frank
several | 876 | 2512 |  | ALL RECIEVER - Operating Concern - Direct Table | Medium | NEW | Link | Maxi | Frank
Material Type | 879 | 2511 |  | Material Type Replication - Some fields not replicated | Medium | IN PROCESS | Link | Ulla | Mike
Material Type | 880 | 2512 |  | Material Type Translation ES missing fields | Low | NEW | Link | Ulla | Ulla
Tax Code | 881 | 2512 |  | Tax Code – direct table – field tol.per.rate not written | Medium | NEW | Link | Sabine
Payment Term | 882 | 2512 |  | Payment term details - percentage values not correctly transferred | High | NEW | Link | Sabine | Dieter
Exchange Rate | 886 | 2512 |  | Exchange Rates roles and authorizations | Low | NEW | Link | Thomas | Günter
Public Holiday | 887 | 2512 |  | Public Holiday - EN DE FR ES - Missing or Faulty Translations | Medium | NEW | Link | Maxi
MRP Area | 889 | 2511 |  | MRP Area Count field missing on UI | Low | IN PROCESS | Link | Niklas | Frank, Dieter
several | 895 | 2512 |  | Field descriptions DE for Objects Classification, Character and Holiday must be revised | Medium | NEW | Link | Thomas | Dieter
Characteristic | 898 | 2512 |  | Itego RDM - Itego - IH1100 - Characterstics - Request is not initialized | HIgh | NEW | Link | Gerd | Mike
Unit of Measure | 900 | 2512 |  | Itego RDM - Itego - UoM Validation - additional language version | High | NEW | Link | Gerd | Mike
several | 910 | 2511 |  | Upload Material Group - 2x division attribute | Low | IN PROCESS | Link | Niklas | Mike
Tax Code | 911 | 2512 |  | Tax code incorrect process and assign tax calculation schema (Process) | High | NEW | Link | Thomas | Frank
several | 915 | 2511 |  | Itego RDM - Itego - IH100 Text translation of the entity types in language DE | Low | IN PROCESS | Link | Gerd | Ulla
several | 918 | 2511 |  | Itego RDM - Itego - IH2100 - several objects – incorrect search screen | Low | IN PROCESS | Link | Gerd | Mike
Work Breakdown Structure | 920 | 2511 |  | Itego RDM - Itego - IH200 - WBS Elements Download Role missing | Low | IN PROCESS | Link | Niklas | Michael
Classes | 921 | 2511 |  | Itego RDM - Itego - IH200 - Classes – value help for Organizational area field | Medium | IN PROCESS | Link | Gerd | Mike
MRP Area | 925 | 2511 |  | MRP Area submit not possible | Very High | NEW | Link | Ulla | Mike
Factory Calendar | 929 | 2512 |  | FR Translation Factory Cal. Not the right translation | Low | NEW | Link | Ulla | Ulla
Work Breakdown Structure | 930 | 2512 |  | Itego RDM - Itego - ID1100 - WBS - wrong value help for project definition | High | NEW | Link | Sabine | Frank/Mike
Holiday calendar | 931 | 2512 |  | Itego RDM - Itego - IH1100 - Public Calendar - Missing validation in the description | Medium | NEW | Link | Gerd | Mike
Holiday calendar | 932 | 2512 |  | Itego RDM - Itego - IH1100 - Holiday Calendar - Missing validation in the description | Medium | NEW | Link | Gerd | Mike
Work Breakdown Structure | 938 | 2509 |  | Itego RDM - Itego - ID1100 - WBS - wrong value help for time unit | Medium | SOLUTION PROPOSAL | Link | Sabine | Farida
Classes | 939 | 2512 |  | Itego RDM - Itego - IH1100 - Classes - copy of classes with assigned characteristics does not work | Low | NEW | Link | Sabine
Classes | 940 | 2512 |  | Itego RDM - Itego - IH100 - Classes - wrong title on search screen | Medium | NEW | Link | Sabine | Ulla
Characteristic | 943 | 2511 |  | Itego RDM - Itego - IH100 - Upload Characteristics internal error - Objects_objref_not_assigned | Very High | NEW | Link | Niklas | Mike
Work Breakdown Structure | 947 | 2509 |  | Itego RDM - Itego - ID1100 - WBS – Changing parent type in hierarchy assignment leads to inconsistent situation | Medium | SOLUTION PROPOSAL | Link | Sabine | Farida
Sales Office | 956 | 2512 |  | sales office - Field Country needs to be maintained | High | NEW | Link | Niklas
Classes | 957 | 2512 |  | characteristics of a class authorization missing | High | NEW | Link | Niklas
Characteristic | 958 | 2512 |  | Upload char head without mandatory description field | High | NEW | Link | Niklas
Work Breakdown Structure | 962 | 2509 |  | Itego RDM - Itego - ID1100 - Validation for creation of WBS elements with the same name | High | SOLUTION PROPOSAL | Link | Gerd/Sabine | Farida
Work Breakdown Structure | 964 | 2509 |  | Create WBS element from the maintenance hierarchy | High | SOLUTION PROPOSAL | Link | Gerd | Farida
Payment Term | 968 | 2512 |  | " 9" and "09" is an issue (916 follow up) | High | NEW | Link | Gerd | Mike
all | 969 | 2512 |  | No CR type found if you want to add an attachment to an existing object | Medium | NEW | Link | Sabine
Work Breakdown Structure | 970 | 2512 |  | IH2100 - WBS Element Fiori - FPM application USMD_SEARCH was started with an invalid or without configuration | Very High | NEW | Link | Niklas | Sabine/Niklas
all | 973 | 2512 |  | Search UI Configuration in ITU MDFIMG not functional | High | NEW | Link | Michael
all | 974 | 2512 |  | Usage of ITU MDFIMG and ITR RDM IMG is confusing | High | NEW | Link | Michael
Work Breakdown Structure | 975 | 2509 |  | Itego RDM - Itego - ID1100 - Distribution WBS-Hierarchy to Backend | Very high | SOLUTION PROPOSAL | Link | Gerd | Farida
Work Breakdown Structure | 979 | 2509 |  | Itego RDM - Itego - ID1 100 - WBS - key of element cannot be changed during creation | High | SOLUTION PROPOSAL | Link | Sabine | Michael
Work Breakdown Structure | 981 | 2509 |  | Itego RDM - Itego - ID1100 - WBS - applicant No of WBS element is overwritten with project definition applicant No | High | SOLUTION PROPOSAL | Link | Sabine | Farida
Product Hierarchy | 992 | 2512 |  | Direct display of error messages without creating a CR | High | NEW | Link | Gerd | Michael
Product Hierarchy | 993 | 2512 |  | Hierarchy Tree View in Search not possible | Medium | NEW | Link | Michael | Mike
Product Hierarchy | 1002 | 2510 |  | External Number not changed after moving node and replication (/ITR/T179 del) and direct table update not del T0179 | High | IN PROCESS | Link | Ulla | Frank
Product Hierarchy | 1003 | 2512 |  | ProdH - wrong error message | High | NEW | Link | Sabine | Mike
Product Hierarchy | 1006 | 2512 |  | Limitation of field length Current Level | High | NEW | Link | Gerd | Mike
Work Breakdown Structure | 1009 | 2509 |  | project definition – value help for profit center not working | Medium | SOLUTION PROPOSAL | Link | Sabine | Farida
Product Hierarchy | 1012 | 2510 |  | Deletion of hierarchy assignments and reassignment | High | IN PROCESS | Link | Gerd | Mike
Product Hierarchy | 1018 | 2512 |  | Manual selection of Parent Node in Hierarchy Assignment via External Number | Medium | NEW | Link | Michael | Mike
Product Hierarchy | 1019 | 2512 |  | More convenient File Upload | Medium | NEW | Link | Michael | Mike
Product Hierarchy | 1020 | 2512 |  | Copy Button for nodes | Low | NEW | Link | Michael | Mike
Product Hierarchy | 1021 | 2512 |  | Replication not correct - different nodes for external numbers | High | NEW | Link | Ulla | Mike
Product Hierarchy | 1027 | 2512 |  | Searching in Hierarchy – no jump to record | Medium | NEW | Link | Ulla | Mike
Product Hierarchy | 1036 | 2512 |  | Dump when uploading without file selection | Medium | NEW | Link | Gerd | Mike
Product Hierarchy | 1037 | 2512 |  | zeros missing to reupload exported nodes | High | NEW | Link | Niklas | Niklas
Product Hierarchy | 1040 | 2510 |  | Assignment deleted, but the external number remains in the node | High | IN PROCESS | Link | Gerd | Mike
Sales Office | 1051 | 2510 |  | Sales Office Upload not possible - country field is missing | Very High | NEW | Link | Niklas | Niklas
MRP Controller | 1052 | 2512 |  | MRP Controller - Upload invalid profit center is possible | High | NEW | Link | Niklas
Customer Account Group | 1053 | 2512 |  | Cust.Acc.Group not found in Search | High | NEW | Link | Sabine
MRP Area | 1055 | 2512 |  | MRP Area Supplier with 1-4-digits blocks creation process | Medium | NEW | Link | Niklas
MRP Area | 1056 | 2512 |  | MRP Area Subcontract - Data was not saved | High | NEW | Link | Niklas
MRP Area | 1057 | 2512 |  | MRP Area- Plant F4 help | Medium | NEW | Link | Niklas | Frank
Storage Location | 1058 | 2509 |  | Storage Location Address not replicated | High | SOLUTION PROPOSAL | Link | Ulla | Frank
Material Type | 1059 | 2511 |  | Material Type Quantity value not replicated | High | IN PROCESS | Link | Ulla | Frank
Material Group | 1060 | 2509 |  | Material Group not replicated | High | SOLUTION PROPOSAL | Link | Ulla | Frank
Sales Office | 1061 | 2509 |  | Street Address not replicated | High | SOLUTION PROPOSAL | Link | Ulla | Frank
MRP Type | 1062 | 2511 |  | MRP-Type Description XML Transformation Error | Medium | IN PROCESS | Link | Niklas | Niklas
Company Code | 1064 | 2512 |  | Addresses are not being found in SPRO on Receiver | High | NEW | Link | Maxi | Maxi
Product Hierarchy | 1065 | 2510 |  | Data is not in System after replication | High | IN PROCESS | Link | Niklas | Frank
Classes | 1066 | 2512 |  | Assignment of characteristic to class does not work | High | NEW | Link | Sabine
Functional Area | 1067 | 2512 |  | Valid to can be earlier than valid from | Medium | NEW | Link | Ulla
Characteristic | 1068 | 2512 |  | Value help for change number missing | Medium | NEW | Link | Sabine
Classes | 1069 | 2512 |  | Value for class deleted after “enter” | Medium | NEW | Link | Sabine
Classes | 1070 | 2511 |  | Description missing in Header download | Very High | NEW | Link | Niklas | Mike
Sales Office | 1072 | 2512 |  | XML transformation Error | High | NEW | Link | Niklas | Niklas
Classes | 1073 | 2512 |  | Descriptions for Class download data missing | Very High | NEW | Link | Niklas | Mike
Factory Calendar | 1074 | 2512 |  | special rules outside validation period | Medium | NEW | Link | Niklas
Payment Term | 1075 | 2509 |  | Payment Terms not replicated | High | SOLUTION PROPOSAL | Link | Ulla | Frank
Classes | 1076 | 2512 |  | search fields - some are not working and default setting must be adjusted | Medium | NEW | Link | Sabine
Classes | 1077 | 2512 |  | Administrative data: created by is overwritten with changed by | Medium | NEW | Link | Sabine
G/L Account Group | 1078 | 2512 |  | no replication to IH1/400 | High | NEW | Link | Sabine | Maxi
Sales Organization | 1079 | 2512 |  | no entry check for reference sales organ. and movement type | High | NEW | Link | Sabine | Mike
Plants/Branches | 1081 | 2511 | 11.09.2025 09:39:20 | Plant Address: Country needs to be mandatory | Medium | NEW | Link | Gerd | Frank/Mike
Plant | 1101 |  | 08.10.2025 11:57:51 | Multiple Obj CR - MRP Area not editable | High | NEW | Link | Ulla
Payment Terms Details | 1102 |  | 08.10.2025 13:23:48 | Description Texts (Own Explenation) are not recieved when replicating via. Direct Table | Medium | NEW | Link | Maxi | Maxi
Company Code | 1103 |  |  | MDF Validation null reference error | High | NEW | Link | Ulla
Sales Organization | 1104 |  | 08.10.2025 15:15:53 | Description not being replicated via. Direct Table | Medium | NEW | Link | Maxi | Maxi
| 1107 |  | 13.10.2025 13:25:50 | RDH Online Selection Texttables not working | High | NEW | Link | Ulla

## Metadata
Steplist | Prioritylist | Statuslist
1-Step | Low | done
2-Step | Medium | n/a
3-Step | High | in progress
General | Very High | open
error
retest