## Tabelle1
Page | Objekte | Objekt ID | Target System | Status | Comment | File | done
|  | IH1 | IR1 |  |  |  | error
Financials | Business Area | ? | ? | done |  |  | open
Financials | Chart of Accounts | ? | ? | done |  |  | not available
Financials | Company Code | ? | ? | done
Financials | Controlling Area | ? | ? | done
Financials | Customer Account Group | ? | ? | done
Financials | Currency Key | ? | ? | done
Financials | Document type | ? | ? | done
Financials | Exchange Rate | ? | ? | done
Financials | Functional Area | ? | ? | done
Financials | G/L Accoung Group | ? | ? | done
Financials | Operating Concern | ? | ? | done
Financials | Tax Code | ? | ? | done
Financials | Valuation Class | ? | ? | done
Financials | Vendor Account Group | VAG1 |  | done
Logistics | BOM Usage | U | X | done
Logistics | Division | 00 | 11 | done
Logistics | Factory Calender | F3 | K3 | done | 277 | \\intern.itego.de\Public\Itego Reference Data Management\Testing\Defect Details\277 Itego RDM - Itego - IR1 Test - Staging not working correct - Factory Calendar.docx
Logistics | Laboratory/Office | L1 | O1 | done
Logistics | Location | KM01 KM02 | KM10 KM20 | error | Repeat - wrong mapping … I1 not L1 => issue 278 => now 294+295 RDM Prefix? Wird nicht bzw falsch übertragen => Nochmal Prüfen | \\intern.itego.de\Public\Itego Reference Data Management\Testing\Defect Details\294 Itego RDM - Itego - IR1 Test - Key Mapping not working correct - Location.docx \\intern.itego.de\Public\Itego Reference Data Management\Testing\Defect Details\295 Itego RDM - Itego - IR1 Test - Replication 500 Error - Location.docx
Logistics | Material Group | u2 | uu | done
Logistics | Material Status | M1 | MM | done
Logistics | Material Type | - | - | error | Niklas will create Material Types … 270 | \\intern.itego.de\Public\Itego Reference Data Management\Testing\Defect Details\270 Itego RDM - Itego - ITR Test - Can't create Material Type.docx
Logistics | MRP Profile | MP1 | MP4 | done | Repeat - should not be possible to create two entries 279 and 290 | \\intern.itego.de\Public\Itego Reference Data Management\Testing\Defect Details\279 Itego RDM - Itego - IR1 Test - Staging not working correct - MRP Profile.docx \\intern.itego.de\Public\Itego Reference Data Management\Testing\Defect Details\290 Itego RDM - Itego - IR1 Test - Key Mapping creates 2 StageEntries - MRP Profile.docx
Logistics | MRP Type | M4 | N4 | done
Logistics | MRP Area | BH01 | HB01 | done
Logistics | Plant | WS02 | SW20 | done
Logistics | Storage Location | ST01 | SL01 | done
Logistics | Unit Of Measure | cmh | HCM | done
Sales and Distribution | Incotrems | I1 | IC1 | done
Sales and Distribution | Distirbution Channel | U2 | DC | done
Sales and Distribution | Payment Terms | U2 | X2 | done
Sales and Distribution | Payment Terms Details | 000222 | 004232 | done
Sales and Distribution | Product Hierachy Nodes | 100 | 100a | done | External Number 116919
Sales and Distribution | Product Hierachy Sub Nodes | 10000000000000 | 101 | done | Product Hierachy 305084 / RDH as a prefix?
Sales and Distribution | Product Hierachy Name | 10 | 10a | done | External Number 180068
Sales and Distribution | Sales Group | UL1 | IK1 | done
Sales and Distribution | Sales Organization | U5 | O5 | done
Sales and Distribution | Shipping Conditions | S2 | C2 | done
Sales and Distribution | Shipping Type | S4 | T4 | done
Human Ressources | Personnel Areas | P1 | A1 | done
General Settings | Country | CM | MC | done
General Settings | Language key |  |  | error | Michael schaut 285 | \\intern.itego.de\Public\Itego Reference Data Management\Testing\Defect Details\285 Itego RDM - Itego - IR1 Test - Staging not working correct - Language Keys.docx
General Settings | Regions | AA KM | AA KM1 | done | Niklas testet nochmal | \\intern.itego.de\Public\Itego Reference Data Management\Testing\Defect Details
Classification | Classes | MBC1 |  | not available in Key Mapping? | Michael schaut - noch kein Fehler erfasst => auch schauen: immer mit RDM Prefix??
Classification | Characteristics |  |  | not available in Key Mapping? | Michael schaut - noch kein Fehler erfasst
Purchasing | Purchasing Group | P3 | PG3 | done
Purchasing | Purchasing Organization | 0001 | 1000 | done