## Itego MDG RDM Test Cases 2503
Test Case | Description | 3-step | 2-step | 1-step | General | Load/Mass | Priority | Status | Remaining Test Priority | Tester | Short Comment | Issue Link | Issue Link | Issue Link | New attr./obj | Test ID1 100 | Test IG1 200 | Test ID1 400 LSA | Test ID1 400 Direct and manual | Test IH2 | Test IH1 | Retest IH2 | Retest IH1 | Test IH1 100 (direct) | Rcv: IH1 400 | Rcv: IH1 400 (direct) | Rcv: IR1 200 | Rcv: IR2 200 | Rcv: S03 400 | Snd: S03 / Rcv IH1 400 | Smoke Test | Comment | topics from last test (2407) | more
01.0 RDG | ****************************************** | [5 empty] | *********
01.1 | Change Material Group | test | test | test | n/a |  | Very High | error | n/a | Sabine |  | 799 | [12 empty] | done |  | done | done | open | open
01.2 | Create Material Group | test | test | test | n/a |  | Very High | error | n/a | Sabine |  | 799 | [8 empty] | open |  |  | open | done |  | done | done | open | open
01.4 | Load Material Group (Data Export / Import) | skip | test | skip | n/a | x | High | done | n/a | Niklas | [5 empty] | open |  | open | open | open | open | open | open |  | n/a |  | n/a | n/a | n/a | n/a |  |  |  | Please test all attributes!! New ones probably have not been added by Felix last time
01.5 | Load Material Group (File Download / Upload) |  |  | n/a | test | x | Very High | done | n/a | Niklas | issue fixed |  |  |  |  | open |  | open | open | open | open | open | open |  | n/a |  | n/a | n/a | n/a | n/a |  |  |  | Please test all attributes!! New ones probably have not been added by Felix last time
01.6 | Local Customizing for Material Group (incl UoM) | n/a | n/a | n/a | test |  | Medium | done | n/a | Niklas | [14 empty] | n/a |  | n/a | n/a | n/a | n/a
01.7 | Material Group Language Test (DE/EN) | n/a | n/a | n/a | test |  | Medium | done | n/a | Ulla | [5 empty] | n/a |  | n/a | n/a | n/a | n/a | n/a | open |  | n/a |  | n/a | n/a | n/a | n/a
01.8 | Material Group Language Test (FR) | n/a | n/a | n/a | test |  | Medium | done | n/a | Ulla | [5 empty] | open |  | open | open | open | open | open | open |  | n/a |  | n/a | n/a | n/a | n/a
01.9 | Material Group Language Test (ES)/grupo de materiales | test | test | test | test |  | Medium | open / not tested | n/a | Ulla
01.10 | Material Group Delete Text | [5 empty] | Very High | error | n/a | Michael | only for lang dep txt |  |  |  |  | done |  | done | error
02.1 | Change Unit of Measure | skip | skip | test | n/a |  | High | open / not tested | n/a | Sabine | [5 empty] | open |  | open | open | open | open | open | open |  | open |  | open | open | open | n/a |  |  | 494 | open has been resolved! -> not for Snd S01! -> which is ok … because this is not 2404
02.2 | Create Unit of Measure | skip | skip | test | n/a |  | High | open / not tested | n/a | Sabine | [5 empty] | open |  | open | open | open | open | open | open | open | open |  | open | open | open | n/a |  |  | 496 | open has been resolved! -> not for Snd S01! -> which is ok … because this is not 2404
02.3 | Load Unit of Measure (File Download / Upload) | n/a | n/a | n/a | test | x | Very High | done | n/a | Niklas | [14 empty] | n/a |  | n/a | n/a | n/a | n/a |  |  | 573 | 10.07. Here we do need three upload files … attributes / text / techn./business text … not documented yet
02.4 | Load Unit of Measure (Data Export / Import) | n/a | n/a | n/a | test | x | High | done | n/a | Niklas | ? | [13 empty] | n/a |  | n/a | n/a | n/a | n/a |  |  |  | open has been resolved!
02.5 | Unit of Measure Language Test (DE/EN) | n/a | n/a | n/a | test |  | High | done | n/a | Ulla | [5 empty] | n/a |  | n/a | n/a | n/a | n/a | n/a | open |  | n/a |  | n/a | n/a | n/a | n/a
02.6 | Unit of Measure Language Test (FR/ES/ES) | n/a | n/a | n/a | test |  | High | in progress | n/a | Ulla | FR OK, ES missing in IH1 |  |  |  |  | open |  | open | open | open | open | open | open |  | n/a |  | n/a | n/a | n/a | n/a |  |  | 555
02.7 | Unit of Measure Language Test (ES)/Unidad de medida | n/a | n/a | n/a | test |  | Medium | retest | n/a | Michael | tested in ID1
03.1 | Change Country | test | skip | skip | n/a |  | Very High | error | n/a | Maxi | Fully Tested with limitations | 793 | 794 |  |  | open |  | open | open | open | done | open | open | retest | error |  | error | error | open | open |  |  | 495 | open has been resolved in IH1 and IH2 -> S01 still has divergent Keys -> this is ok as this is 2311
03.2 | Create Country | test | skip | skip | n/a |  | Very High | error | n/a | Maxi | Fully Tested with limitations |  |  |  |  | open |  | open | open | open | done | open | open | retest | error | open | error | error | open | open |  |  | 495 | open has been resolved!
03.3 | Load Country (File Download / Upload) | n/a | n/a | n/a | test | x | Very High | done | n/a | Niklas | [14 empty] | n/a |  | n/a | n/a | n/a | n/a
03.4 | Load Country (Data Export / Import) | n/a | n/a | n/a | test | x | High | done | n/a | Niklas | [14 empty] | n/a |  | n/a | n/a | n/a | n/a
03.5 | Country Language Test (DE/EN/FR/ES/ES) | n/a | n/a | n/a | test |  | Medium | error | n/a | Maxi |  | 821 FR / ES |  |  |  | n/a |  | n/a | n/a | n/a | error | n/a | open |  | n/a |  | n/a | n/a | n/a | n/a
03.6 | Country Language Test (FR/ES/ES) | n/a | n/a | n/a | test |  | Medium | in progress | n/a | Ulla | FR OK, ES missing in IH1 |  |  |  |  | open |  | open | open | open | open | open | open |  | n/a |  | n/a | n/a | n/a | n/a
03.7 | Country Test (ES)/país | n/a | n/a | n/a | test |  | Medium | retest | n/a | Michael | tested in ID1
04.1 | Change Region | skip | test | skip | n/a |  | High | done | n/a | Maxi | Fully Tested (LSA/DT) |  |  |  |  | open |  | open | open | open | done | open | open | done | done |  | done | done | open | open
04.2 | Create Region | skip | test | skip | n/a |  | High | done | n/a | Maxi | Fully Tested (LSA/DT) |  |  |  |  | open |  | open | open | open | done | open | open | done | done | done | done | done | open | open
04.3 | Load Region (File Download / Upload) | n/a | n/a | n/a | test | x | Low | done | n/a | Niklas | [14 empty] | n/a |  | n/a | n/a | n/a | n/a
04.4 | Load Region (Data Export / Import) | n/a | n/a | n/a | test | x | Very High | done | n/a | Niklas | [14 empty] | n/a |  | n/a | n/a | n/a | n/a
04.5 | Region Language Test (DE/EN) | n/a | n/a | n/a | test |  | Low | error | n/a | Maxi | [5 empty] | n/a |  | n/a | n/a | n/a | error | n/a | open |  | n/a |  | n/a | n/a | n/a | n/a
04.6 | Region Language Test (FR/ES/ES) | n/a | n/a | n/a | test |  | Low | in progress | n/a | Ulla | FR OK, ES missing in IH1 |  |  |  |  | open |  | open | open | open | open | open | open |  | n/a |  | n/a | n/a | n/a | n/a
04.7 | Region Test (ES)/región | n/a | n/a | n/a | test |  | Medium | retest | n/a | Michael | tested in ID1
05.1 | Change Purchasing Group | skip | test | skip | n/a |  | High | error | n/a | Sabine |  | 798 | [8 empty] | open |  |  |  | error |  | open | open | open | open |  |  |  | open has been resolved!
05.2 | Create Purchasing Group | skip | test | skip | n/a |  | High | error | n/a | Sabine |  | 798 | [8 empty] | open |  |  | open | error |  | open / open with limitations | open / open with limitations | open | open
05.3 | Load Purchasing Group (File Download / Upload) | n/a | n/a | n/a | test | x | High | done | n/a | Niklas | [14 empty] | n/a |  | n/a | n/a | n/a | n/a |  |  |  | 17.6. only remaining open: missing Icon
05.4 | Load Purchasing Group (Data Export / Import) | n/a | n/a | n/a | test | x | Very High | done | n/a | Niklas | issue fixed | 761 | [12 empty] | n/a |  | n/a | n/a | n/a | n/a
05.5 | Purchasing Group Language Test (DE/EN) | n/a | n/a | n/a | test |  | Low | done | n/a | Ulla | [14 empty] | n/a |  | n/a | n/a | n/a | n/a
05.6 | Purchasing Group Language Test (FR/ES) | n/a | n/a | n/a | test |  | High | in progress | n/a | Ulla | FR OK, ES missing in IH1 |  |  |  |  | open |  | open | open | open | open | open | open |  | n/a |  | n/a | n/a | n/a | n/a |  |  | 553
05.7 | Purchaing Group Test (ES)/grupo de compras | n/a | n/a | n/a | test |  | Medium | retest | n/a | Michael | tested in ID1
06.1 | Change Purchasing Organization | skip | skip | test | n/a |  | Low | open / not tested | n/a | Ulla | [14 empty] | open |  | open | open | open | open
06.2 | Create Purchasing Organization | skip | skip | test | n/a |  | Low | open / not tested | n/a | Ulla | [10 empty] | open |  |  | open | open |  | open | open | open | open
06.3 | Load Purchasing Organization (File Download / Upload) | n/a | n/a | n/a | test | x | Low | done | n/a | Niklas | [14 empty] | n/a |  | n/a | n/a | n/a | n/a |  |  |  | opens still persists
06.4 | Load Purchasing Organization (Data Export / Import) | n/a | n/a | n/a | test | x | Low | done | n/a | Niklas | [14 empty] | n/a |  | n/a | n/a | n/a | n/a |  |  |  | opens still persists
06.5 | Purchasing Organization Language Test (DE/EN) | n/a | n/a | n/a | test |  | Low | done | n/a | Ulla | [14 empty] | n/a |  | n/a | n/a | n/a | n/a
06.6 | Purchasing Organization Language Test (FR/ES/ES) | n/a | n/a | n/a | test |  | High | in progress | n/a | Ulla | FR OK, ES missing in IH1 |  |  |  |  | open |  | open | open | open | open | open | open |  | n/a |  | n/a | n/a | n/a | n/a |  |  | 554
06.7 | Purchasing Organizsation Test (ES)/organización de compras | n/a | n/a | n/a | test |  | Medium | retest | n/a | Michael | tested in ID1
07.1 | Change Account Group G/L | skip | test | skip | n/a |  | High | done | n/a | Ulla | [14 empty] | done |  | done | open | open | open
07.2 | Create Account Group G/L | skip | test | skip | n/a |  | High | done | n/a | Ulla | [10 empty] | open |  |  | open | n/a |  | n/a | open | open | open
07.3 | Load Account Group G/L (File Download / Upload) | n/a | n/a | n/a | test | x | High | done | n/a | Niklas | [14 empty] | n/a |  | n/a | n/a | n/a | n/a
07.4 | Load Account Group G/L (Data Export / Import) | n/a | n/a | n/a | test | x | High | done | n/a | Niklas | [14 empty] | n/a |  | n/a | n/a | n/a | n/a
07.5 | Change Account Group G/L - Scheduled LSA Subscriber | skip | test | skip | n/a |  | Low | on hold | n/a | Michael | [14 empty] | n/a |  | n/a | n/a | n/a | n/a
07.6 | Account Group GL Language Test (DE/EN) | n/a | n/a | n/a | test |  | High | done | n/a | Ulla | [14 empty] | n/a |  | n/a | n/a | n/a | n/a
07.7 | Account Group GL Language Test (FR/ES/ES) | n/a | n/a | n/a | test |  | Medium | in progress | n/a | Ulla | FR OK, ES missing in IH1 |  |  |  |  | open |  | open | open | open | open | open | open |  | open |  | open | open | open | n/a
07.7 | Account Group Test (ES)/grupo de cuentas | n/a | n/a | n/a | test |  | Medium | retest | n/a | Michael | tested in ID1
08.1 | Change Account Group Vendor | test | skip | skip | n/a |  | Low | open / not tested | n/a | Ulla | [14 empty] | open |  | open | open | open | open
08.2 | Create Account Group Vendor | test | skip | skip | n/a |  | Low | open / not tested | n/a | Ulla | [10 empty] | open |  |  | open | open |  | open | open | open | open
08.3 | Load Account Group Vendor (File Download / Upload) | n/a | n/a | n/a | test | x | Low | error | n/a | Niklas |  |  |  |  | 829 | [9 empty] | n/a |  | n/a | n/a | n/a | n/a
08.4 | Load Account Group Vendor (Data Export / Import) | n/a | n/a | n/a | test | x | Low | done | n/a | Niklas | [14 empty] | n/a |  | n/a | n/a | n/a | n/a
08.5 | Account Group Vendor Language Test (DE/EN) | n/a | n/a | n/a | test |  | Low | done | n/a | Ulla | [14 empty] | n/a |  | n/a | n/a | n/a | n/a
08.6 | Account Group Vendor Language Test (FR/ES/ES) | n/a | n/a | n/a | test |  | Medium | in progress | n/a | Ulla | FR OK, ES missing in IH1 |  |  |  |  | open |  | open | open | open | open | open | open |  | n/a |  | n/a | n/a | n/a | n/a |  |  | 520
08.7 | Vendor Account Group Test (ES)/Grupo de Cuentas de Proveedor | n/a | n/a | n/a | test |  | Medium | retest | n/a | Michael | tested in ID1
09.1 | Change Account Group Customer | skip | test | skip | n/a |  | Low | open / not tested | n/a | Ulla | [14 empty] | open |  | open | open | open | open
09.2 | Create Account Group Customer | skip | test | skip | n/a |  | Low | open / not tested | n/a | Ulla | [10 empty] | open |  |  | open | open |  | open | open | open | open
09.3 | Load Account Group Customer (File Download / Upload) | n/a | n/a | n/a | test | x | Low | done | n/a | Niklas |  |  |  |  | 830 | [9 empty] | n/a |  | n/a | n/a | n/a | n/a
09.4 | Load Account Group Customer (Data Export / Import) | n/a | n/a | n/a | test | x | Low | done | n/a | Niklas | [14 empty] | n/a |  | n/a | n/a | n/a | n/a |  |  |  | open has been resolved!
09.5 | Account Group Customer Language Test (DE/EN) | n/a | n/a | n/a | test |  | Medium | done | n/a | Ulla | [14 empty] | n/a |  | n/a | n/a | n/a | n/a |  |  |  | open has been resolved!
09.6 | Account Group Customer Language Test (FR/ES/ES) | n/a | n/a | n/a | test |  | High | in progress | n/a | Ulla | FR OK, ES missing in IH1 |  |  |  |  | open |  | open | open | open | open | open | open |  | open |  | open | open | open | open
09.7 | Customer Account Group Test (ES)/Grupo de Cuentas de Cliente | n/a | n/a | n/a | test |  | Medium | retest | n/a | Michael | tested in ID1
10.1 | Change Product Hierarchy | test | skip | skip | n/a |  | Very High | in progress | n/a | Michael | [14 empty] | open |  | open | open | open | open |  |  | 615
10.2 | Create Product Hierarchy | test | skip | skip | n/a |  | Very High | in progress | n/a | Michael | 756 solved | 756 | [8 empty] | done |  |  | open | open |  | open | open | open | open
10.3 | Load Product Hierarchy (File Download / Upload) | n/a | n/a | n/a | test | x | Very High | in progress | n/a | Michael | [14 empty] | n/a |  | n/a | n/a | n/a | n/a
10.4 | Product Hierarchy Language Test (DE/EN) | n/a | n/a | n/a | test |  | Very High | in progress | n/a | Michael | [14 empty] | n/a |  | n/a | n/a | n/a | n/a
10.5 | Product Hierarchy Language Test (FR) | n/a | n/a | n/a | test |  | Very High | in progress | n/a | Michael | [5 empty] | open |  | open | open | open | open | open | open |  | n/a |  | n/a | n/a | n/a | n/a |  |  | 556
10.6 | Producty Hierarchy Test (ES)/jerarquía de productos | n/a | n/a | n/a | test |  | Medium | retest | n/a | Michael | tested in ID1
10.7 | Product Hierarchy Remove Subnode |  |  |  | test |  | High | in progress | n/a | Michael
10.8 | Product Hierarchy Remove Node |  |  |  | test |  | High | in progress | n/a | Michael
10.9 | Product Hierarchy Delete Subnode |  |  |  | test |  | High | in progress | n/a | Michael
10.10 | Product Hierarchy Delete Node |  |  |  | test |  | High | in progress | n/a | Michael
10.11 | Product Hierarchy Move Node |  |  |  | test |  | High | in progress | n/a | Michael
10.12 | Product Hierarchy Move Node with Subtree |  |  |  | test |  | High | in progress | n/a | Michael
11.1 | Change Company Code | skip | test | skip | n/a |  | Very High | done | n/a | Sabine | [10 empty] | open |  |  |  | done |  | done | done | open | open |  |  | 587 | 11.07.: not clear - ready to test or not?
11.2 | Create Company Code | skip | test | skip | n/a |  | Very High | error | n/a | Sabine |  | 838 | 839 | [7 empty] | open |  |  | open | done |  | done | done | open | open
11.3 | Load Company Code (File Download / Upload) | n/a | n/a | n/a | test | x | High | done | n/a | Niklas | [14 empty] | n/a |  | n/a | n/a | n/a | n/a |  |  |  | Topic Document 478 has been updated
11.4 | Load Company Code (Data Export / Import) | n/a | n/a | n/a | test | x | Very High | done | n/a | Niklas | nochmal anschauen |  |  |  |  | open |  | open | open | open | open | open | open |  | n/a |  | n/a | n/a | n/a | n/a |  |  | new attributes | Topic Document 478 has been updated
11.5 | Company Code Language Test (DE/EN) | n/a | n/a | n/a | test |  | Medium | error | n/a | Maxi |  | 821 FR / ES |  |  |  | open |  | open | open | open | error | open | open |  | n/a |  | n/a | n/a | n/a | n/a |  |  | 504
11.6 | Company Code Language Test (EN/DE) | n/a | n/a | n/a | test |  | Medium | done | n/a | Ulla | [5 empty] | open |  | open | open | open | open | open | open |  | n/a |  | n/a | n/a | n/a | n/a
11.7 | Company code Test (ES)/sociedad | n/a | n/a | n/a | test |  | Medium | retest | n/a | Michael | tested in ID1
12.1 | Change Plant | test | test | test | n/a |  | Very High | in progress | n/a | Michael |  |  |  |  | x Comp Code | [9 empty] | open |  | open | open | open | open
12.2 | Create Plant | test | test | test | n/a |  | Very High | in progress | n/a | Michael |  |  |  |  | x Comp Code | [5 empty] | open |  |  | open | open |  | open | open | open | open |  |  | 537
12.3 | Load Plant (File Download / Upload) | n/a | n/a | n/a | test | x | High | done | n/a | Niklas | [14 empty] | n/a |  | n/a | n/a | n/a | n/a
12.4 | Load Plant (Data Export / Import) | n/a | n/a | n/a | test | x | High | done | n/a | Niklas | [14 empty] | n/a |  | n/a | n/a | n/a | n/a |  |  |  | 17.6. Ulla should check - open still persists
12.6 | Plant Language Test (DE/EN) | n/a | n/a | n/a | test |  | Very High | done | n/a | Ulla | [5 empty] | n/a |  | n/a | n/a | n/a | n/a | n/a | open |  | n/a |  | n/a | n/a | n/a | n/a |  |  | 492 (DE)
12.7 | Plant Language Test (FR/ES/ES) | n/a | n/a | n/a | test |  | Very High | in progress | n/a | Ulla | FR OK, ES missing in IH1 |  |  |  |  | open |  | open | open | open | open | open | open |  | n/a |  | n/a | n/a | n/a | n/a
12.8 | Plant Test (ES)/Fábrica | n/a | n/a | n/a | test |  | Medium | retest | n/a | Michael | tested in ID1
13.1 | Change Payment Term | skip | skip | test | n/a |  | High | open / not tested | n/a | Sabine | [14 empty] | n/a |  | n/a | n/a | n/a | open |  |  | 618 | Retest 2311
13.2 | Create Payment Term | skip | skip | test | n/a |  | High | open / not tested | n/a | Sabine | [10 empty] | open |  |  | open | n/a |  | n/a | n/a | n/a | open
13.3 | Load Payment Term (File Download / Upload) | n/a | n/a | n/a | test | x | Very High | done | n/a | Niklas | [14 empty] | n/a |  | n/a | n/a | n/a | open
13.4 | Load Payment Term (Data Export / Import) | n/a | n/a | n/a | test | x | Very High | done | n/a | Niklas | [14 empty] | n/a |  | n/a | n/a | n/a | open
13.5 | Payment Term Language Test (DE/EN) | n/a | n/a | n/a | test |  | Very High | done | n/a | Ulla | [5 empty] | n/a |  | n/a | n/a | n/a | n/a | n/a | open |  | n/a |  | n/a | n/a | n/a | n/a |  |  | 493 (DE)
13.6 | Payment Term Language Test (FR/ES/ES) | n/a | n/a | n/a | test |  | Very High | in progress | n/a | Ulla | FR OK, ES missing in IH1 |  |  |  |  | open |  | open | open | open | open | open | open |  | n/a |  | n/a | n/a | n/a | n/a
13.7 | Payment Ferm Test (ES)/condiciones de pago | n/a | n/a | n/a | test |  | Medium | retest | n/a | Michael | tested in ID1
13.8 | Create Payment Term (Multiple Obj CR Type) | n/a | n/a | n/a | test |  | Very High | open / not tested | n/a | Michael | [10 empty] | open |  |  | open
14.1 | Change Currency Code | test | skip | skip | n/a |  | High | done | n/a | Maxi | Fully Tested (LSA/DT) |  |  |  |  | open |  | open | open | open | done | open | open | done | done |  | done | done | open | open
14.2 | Create Currency Code | test | skip | skip | n/a |  | High | done | n/a | Maxi | Fully Tested (LSA/DT) |  |  |  |  | open |  | open | open | open | done | open | open | done | done | done | done | done | open | open
14.3 | Load Currency Code (File Download / Upload) | n/a | n/a | n/a | test | x | High | done | n/a | Niklas | [14 empty] | n/a |  | n/a | n/a | n/a | n/a
14.4 | Load Currency Code (Data Export / Import) | n/a | n/a | n/a | test | x | Very High | done | n/a | Niklas | [14 empty] | n/a |  | n/a | n/a | n/a | n/a
14.5 | Currency Code Language Test (DE/EN) | n/a | n/a | n/a | test |  | Medium | done | n/a | Maxi | [5 empty] | n/a |  | n/a | n/a | n/a | done | n/a | open |  | n/a |  | n/a | n/a | n/a | n/a
14.6 | Currency Code Language Test (FR/ES/ES) | n/a | n/a | n/a | test |  | Medium | in progress | n/a | Ulla | FR OK, ES missing in IH1 |  |  |  |  | open |  | open | open | open | open | open | open |  | n/a |  | n/a | n/a | n/a | n/a
14.7 | Currency Code Test (ES)/abreviatura de moneda | n/a | n/a | n/a | test |  | Medium | retest | n/a | Michael | tested in ID1
15.1 | Change Sales Organization | skip | test | test | n/a |  | Very High | error | n/a | Sabine |  | 832 | 836 | [7 empty] | open |  |  |  | done |  | done | done | open | open |  |  | 481 | 19.6. Sol Proposal
15.2 | Create Sales Organization | skip | test | test | n/a |  | Very High | error | n/a | Sabine |  | 837 | [8 empty] | open |  |  | open | done |  | done | done | open | open |  |  | 480 | 19.6. Sol Proposal
15.3 | Load Sales Organization (File Download / Upload) | n/a | n/a | n/a | test | x | High | done | n/a | Niklas | [14 empty] | n/a |  | n/a | n/a | n/a | n/a
15.4 | Load Sales Organization (Data Export / Import) | n/a | n/a | n/a | test | x | Very High | done | n/a | Niklas | [14 empty] | n/a |  | n/a | n/a | n/a | n/a
15.5 | Sales Organization Language Test (DE/EN) | n/a | n/a | n/a | test |  | Very High | done | n/a | Ulla | [14 empty] | n/a |  | n/a | n/a | n/a | n/a
15.6 | Sales Organization Language Test (FR/ES) | n/a | n/a | n/a | test |  | Very High | in progress | n/a | Ulla | FR OK, ES missing in IH1 |  |  |  |  | open |  | open | open | open | open | open | open |  | n/a |  | n/a | n/a | n/a | n/a |  |  | 558
15.7 | Sales Organisation Test (ES)/Organización de ventas | n/a | n/a | n/a | test |  | Medium | retest | n/a | Michael | tested in ID1
16.1 | Change Material Type | skip | test | skip | n/a |  | Low | open / not tested | n/a | Ulla | [10 empty] | open |  |  | open | open / open with limitations |  | open | open | open | open
16.2 | Create Material Type | skip | test | skip | n/a |  | Low | open / not tested | n/a | Ulla | [10 empty] | open |  |  | open | open / open with limitations |  | open | open | open | open
16.3 | Load Material Type (File Download / Upload) | n/a | n/a | n/a | test | x | Low | done | n/a | Niklas |  |  |  |  | 831 | [9 empty] | n/a |  | n/a | n/a | n/a | n/a
16.4 | Load Material Type (Data Export / Import) | n/a | n/a | n/a | test | x | Low | done | n/a | Niklas | [14 empty] | n/a |  | n/a | n/a | n/a | n/a |  |  | 516
16.5 | Material Type Language Test (DE/EN) | n/a | n/a | n/a | test |  | Low | error | n/a | Maxi |  | 821 FR / ES |  |  |  | open |  | open | open | open | error | open | open |  | n/a |  | n/a | n/a | n/a | n/a |  |  | 505 | open has been resolved!
16.6 | Material Type Language Test (FR/ES) | n/a | n/a | n/a | test |  | Low | open / not tested | n/a | Ulla | [5 empty] | open |  | open | open | open | open | open | open |  | n/a |  | n/a | n/a | n/a | n/a |  |  | 559
16.7 | Material Type Test (ES)/tipo de material | n/a | n/a | n/a | test |  | Medium | retest | n/a | Michael | tested in ID1
17.1 | Change Storage Location | skip | test | skip | n/a |  | Very High | error | n/a | Ulla |  | 792 | [12 empty] | done / done with limitations |  | open | open | open | open |  | 795
17.2 | Create Storage Location | skip | test | skip | n/a |  | Very High | error | n/a | Ulla |  | 792 | [8 empty] | open |  |  | error | done / done with limitations |  | open | open | open | open |  | 795 | 547 | 23.07.: Resolved, complete retest in IH1 and all systems open 11.07.: UI can be changed now, LSA processing does not work … Mike will exchange the entry in local scope
17.3 | Load Storage Location (File Download / Upload) | n/a | n/a | n/a | test | x | High | done | n/a | Niklas | [5 empty] | open |  | open | open | open | open | open | open |  | n/a |  | n/a | n/a | n/a | n/a
17.4 | Load Storage Location (Data Export / Import) | n/a | n/a | n/a | test | x | High | done | n/a | Niklas | [5 empty] | open |  | open | open | open | open | open | open |  | n/a |  | n/a | n/a | n/a | n/a |  |  | new attributes
17.5 | Storage Location Language Test (DE/EN) | n/a | n/a | n/a | test |  | Very High | done | n/a | Ulla | [14 empty] | n/a |  | n/a | n/a | n/a | n/a
17.6 | Storage Location Language Test (FR/ES) | n/a | n/a | n/a | test |  | Very High | in progress | n/a | Ulla | FR OK, ES missing in IH1 |  |  |  |  | open |  | open | open | open | open | open | open |  | n/a |  | n/a | n/a | n/a | n/a
17.7 | Storage Location Test (ES)/almacén | n/a | n/a | n/a | test |  | Medium | retest | n/a | Michael | tested in ID1
18.1 | Change Division | skip | skip | test | n/a |  | Medium | error | n/a | Sabine |  | 855 | [8 empty] | open |  |  |  | done |  | error | error | open | open
18.2 | Create Division | skip | skip | test | n/a |  | Medium | error | n/a | Sabine |  | 853 | [8 empty] | open |  |  | open | done |  | done | done | open | open
18.3 | Load Division (File Download / Upload) | skip | skip | test | n/a | x | High | done | n/a | Niklas | [14 empty] | n/a |  | n/a | n/a | n/a | n/a
18.4 | Load Division/Sparte (Data Export / Import) | n/a | n/a | n/a | test | x | High | done | n/a | Niklas | [14 empty] | n/a |  | n/a | n/a | n/a | n/a
18.5 | Division Language Test (DE/EN) | n/a | n/a | n/a | test |  | Medium | done | n/a | Maxi | [5 empty] | n/a |  | n/a | n/a | n/a | done | n/a | open |  | n/a |  | n/a | n/a | n/a | n/a
18.6 | Division Language Test (FR/ES) | n/a | n/a | n/a | test |  | Medium | in progress | n/a | Ulla | FR OK, ES missing in IH1 |  |  |  |  | open |  | open | open | open | open | open | open |  | n/a |  | n/a | n/a | n/a | n/a
18.7 | Division Test (ES)/sector | n/a | n/a | n/a | test |  | Medium | retest | n/a | Michael | tested in ID1
19.1 | Change Factory Calendar | skip | test | skip | n/a |  | Very High | open / not tested | n/a | Maxi | [5 empty] | open |  | open | open | open | open | open | open |  | open |  | open | open | open | open |  |  | 473 | 17.6. only remaining open: missing Icon
19.2 | Create Factory Calendar | skip | test | skip | n/a |  | Very High | open / not tested | n/a | Maxi | [5 empty] | open |  | open | open | open | open | open | open | open | open |  | open | open | open | open
19.3 | Load Factory Calendar (File Download / Upload) | n/a | n/a | n/a | test | x | Very High | done | n/a | Niklas
19.4 | Load Factory Calendar (Data Export / Import) | n/a | n/a | n/a | test | x | High | done | n/a | Niklas | [14 empty] | n/a |  | n/a | n/a | n/a | n/a |  |  | 499
19.5 | Factory Calendar Language Test (DE/EN) | n/a | n/a | n/a | test |  | Very High | done | n/a | Ulla | [5 empty] | n/a |  | n/a | n/a | n/a | n/a | n/a | open |  | n/a |  | n/a | n/a | n/a | n/a
19.6 | Factory Calendar Language Test (FR/ES) | n/a | n/a | n/a | test |  | Very High | in progress | n/a | Ulla | FR OK, ES missing in IH1 |  |  |  |  | open |  | open | open | open | open | open | open |  | n/a |  | n/a | n/a | n/a | n/a |  |  | 560
19.7 | Factory Calendar Test (ES)/calendario de fábrica | n/a | n/a | n/a | test |  | Medium | retest | n/a | Michael | tested in ID1
20.1 | Change Distribution Channel | skip | test | skip | n/a |  | Low | open / not tested | n/a | Thomas | [5 empty] | open |  | open | open | open | open | open | open |  | open |  | open | open | open | open
20.2 | Create Distribution Channel | skip | test | skip | n/a |  | Low | in progress | n/a | Thomas | [5 empty] | open |  | open | open | open | open | open | open | open | open |  | open | open | open | open
20.3 | Load Distribution Channel (File Download / Upload) | n/a | n/a | n/a | test | x | Very High | done | n/a | Niklas | [14 empty] | n/a |  | n/a | n/a | n/a | n/a
20.4 | Load Distribution Channel (Data Export / Import) | n/a | n/a | n/a | test | x | High | done | n/a | Niklas | [14 empty] | n/a |  | n/a | n/a | n/a | n/a
20.5 | Distribution Channel Language Test (DE/EN) | n/a | n/a | n/a | test |  | Low | done | n/a | Ulla | [5 empty] | n/a |  | n/a | n/a | n/a | n/a | n/a | open |  | n/a |  | n/a | n/a | n/a | n/a
20.6 | Distribution Channel Language Test (FR/ES) | n/a | n/a | n/a | test |  | Low | in progress | n/a | Ulla | FR OK, ES missing in IH1 |  |  |  |  | open |  | open | open | open | open | open | open |  | n/a |  | n/a | n/a | n/a | n/a
20.7 | Distribution Channel Test (ES)/canal de distribución | n/a | n/a | n/a | test |  | Medium | retest | n/a | Michael | tested in ID1
21.1 | Change Controlling Area | skip | skip | skip | n/a |  | Medium | done with limitations | n/a | Maxi | Done w. lim. Bc only issue is regarding checkboxes | 760 | 763 solved | 781 solved |  | open |  | open | open | open | done | open | open |  | done with limitations |  | done with limitations | done with limitations | open | open |  |  | 527 528 529 530 | opens have been resolved!
21.2 | Create Controlling Area | skip | skip | skip | n/a |  | Medium | done with limitations | n/a | Maxi | [5 empty] | open |  | open | open | open | done | open | open | done with limitations | done with limitations | done with limitations | done with limitations | done with limitations | open | open |  |  | 527 528 529 530 | opens have been resolved!
21.3 | Load Controlling Area (File Download / Upload) | n/a | n/a | n/a | test | x | High | done | n/a | Niklas
21.4 | Load Controlling Area (Data Export / Import) | n/a | n/a | n/a | test | x | Medium | done | n/a | Niklas | [14 empty] | n/a |  | n/a | n/a | n/a | n/a
21.5 | Controlling Area Language Test (DE/EN) | n/a | n/a | n/a | test |  | Medium | error | n/a | Ulla | [5 empty] | n/a |  | n/a | n/a | n/a | n/a | n/a | open |  | n/a |  | n/a | n/a | n/a | n/a
21.6 | Controlling Area Language Test (FR/ES) | n/a | n/a | n/a | test |  | Medium | in progress | n/a | Ulla | FR OK, ES missing in IH1 |  |  |  |  | open |  | open | open | open | open | open | open |  | n/a |  | n/a | n/a | n/a | n/a
21.7 | Controlling Area Test (ES)/sociedad CO | n/a | n/a | n/a | test |  | Medium | retest | n/a | Michael | tested in ID1
22.1 | Change Material Status | skip | skip | test | n/a |  | Low | done | n/a | Maxi | Fully Tested (LSA/DT) |  |  |  |  | open |  | open | open | open | done | open | open | done with limitations | done |  | done | done | open | open |  |  | 544
22.2 | Create Material Status | skip | skip | test | n/a |  | Low | done | n/a | Maxi | Fully Tested (LSA/DT) |  |  |  |  | open |  | open | open | open | done | open | open | done | done | done | done | done | open | open |  |  | 544
22.3 | Load Material Status (File Download / Upload) | n/a | n/a | n/a | test | x | Low | done | n/a | Niklas | [14 empty] | n/a |  | n/a | n/a | n/a | n/a
22.4 | Load Material Status (Data Export / Import) | n/a | n/a | n/a | test | x | Low | done | n/a | Niklas | [14 empty] | n/a |  | n/a | n/a | n/a | n/a
22.5 | Material Status Language Test (DE/EN) | n/a | n/a | n/a | test |  | Medium | error | n/a | Maxi |  | 821 FR / ES |  |  |  | n/a |  | n/a | n/a | n/a | error | n/a | open |  | n/a |  | n/a | n/a | n/a | n/a
22.6 | Material Status Language Test (FR/ES) | n/a | n/a | n/a | test |  | Medium | in progress | n/a | Ulla | FR OK, ES missing in IH1 |  |  |  |  | open |  | open | open | open | open | open | open |  | n/a |  | n/a | n/a | n/a | n/a
22.7 | Material Status Test (ES)/estado del material | n/a | n/a | n/a | test |  | Medium | retest | n/a | Michael | tested in ID1
23.1 | Change Personnel Area | test | skip | skip | n/a |  | Low | done | n/a | Maxi | Fully Tested (LSA/DT) |  |  |  |  | open |  | open | open | open | done | open | open |  | done |  | done | done | open | open
23.2 | Create Personnel Area | test | skip | skip | n/a |  | Low | done | n/a | Maxi | Fully Tested (LSA/DT) |  |  |  |  | open |  | open | open | open | done | done | done | done | done | done | done | done | open | open
23.3 | Load Personnel Area (File Download / Upload) | n/a | n/a | n/a | test | x | Low | done | n/a | Niklas
23.4 | Load Personnel Area (Data Export / Import) | n/a | n/a | n/a | test | x | Low | done | n/a | Niklas | [14 empty] | n/a |  | n/a | n/a | n/a | n/a
23.5 | Personnel Area Language Test (DE/EN) | n/a | n/a | n/a | test |  | Low | error | n/a | Maxi |  | 821 FR / ES | 819 ES |  |  | n/a |  | n/a | n/a | n/a | error | n/a | open |  | n/a |  | n/a | n/a | n/a | n/a
23.6 | Personnel Area Language Test (FR/ES) | n/a | n/a | n/a | test |  | Low | in progress | n/a | Ulla | FR OK, ES missing in IH1 |  |  |  |  | open |  | open | open | open | open | open | open |  | n/a |  | n/a | n/a | n/a | n/a |  |  | 561
23.7 | Personal Area Test (ES)/área personal | n/a | n/a | n/a | test |  | Medium | retest | n/a | Michael | tested in ID1
24.1 | Change Business Area | skip | test | skip | n/a |  | High | done | n/a | Maxi | Fully Tested (LSA/DT) |  |  |  |  | open |  | open | open | open | done | open | open | done | done |  | done | done | open | open |  |  | 487
24.2 | Create Business Area | skip | test | skip | n/a |  | High | done | n/a | Maxi | Fully Tested (LSA/DT) |  |  |  |  | open |  | open | open | open | done | open | open | done | done | done | done | done | open | open |  |  | 487
24.3 | Load Business Area (File Download / Upload) | n/a | n/a | n/a | test | x | Low | done | n/a | Niklas
24.4 | Load Business Area (Data Export / Import) | n/a | n/a | n/a | test | x | Low | done | n/a | Niklas | [14 empty] | n/a |  | n/a | n/a | n/a | n/a
24.5 | Business Area Language Test (DE/EN) | n/a | n/a | n/a | test |  | Low | error | n/a | Maxi |  |  |  | FR |  | n/a |  | n/a | n/a | n/a | error | n/a | open |  | n/a |  | n/a | n/a | n/a | n/a
24.6 | Business Area Language Test (FR/ES) | n/a | n/a | n/a | test |  | Low | in progress | n/a | Ulla | FR OK, ES missing in IH1 |  |  |  |  | open |  | open | open | open | open | open | open |  | n/a |  | n/a | n/a | n/a | n/a
24.7 | Business Area Test (ES)/área empresarial | n/a | n/a | n/a | test |  | Medium | retest | n/a | Michael | tested in ID1
25.1 | Change Functional Area | skip | skip | test | n/a |  | Medium | error | n/a | Sabine |  | 858 | [8 empty] | open |  |  |  | error |  | error | error | open | open
25.2 | Create Functional Area | skip | skip | test | n/a |  | Medium | done | n/a | Sabine | [10 empty] | open |  |  | open | done |  | done | done | open | open
25.3 | Load Functional Area (File Download / Upload) | n/a | n/a | n/a | test | x | Low | done | n/a | Niklas
25.4 | Load Functional Area (Data Export / Import) | n/a | n/a | n/a | test | x | Low | done | n/a | Niklas | [14 empty] | n/a |  | n/a | n/a | n/a | n/a
25.5 | Functional Area Language Test (DE/EN) | n/a | n/a | n/a | test |  | Medium | done with limitations | n/a | Maxi |  |  |  | FR |  | n/a |  | n/a | n/a | n/a | done with limitations | n/a | open |  | n/a |  | n/a | n/a | n/a | n/a
25.6 | Functional Area Language Test (FR/ES) | n/a | n/a | n/a | test |  | Medium | in progress | n/a | Ulla | FR OK, ES missing in IH1 |  |  |  |  | open |  | open | open | open | open | open | open |  | n/a |  | n/a | n/a | n/a | n/a
25.7 | Functional Area Test (ES)/área funcional | n/a | n/a | n/a | test |  | Medium | retest | n/a | Michael | tested in ID1
26.1 | Change Incoterm | skip | test | skip | n/a |  | High | done | n/a | Ulla | [14 empty] | open |  | open | open | open | open
26.2 | Create Incoterm | skip | test | skip | n/a |  | High | done | n/a | Ulla | [10 empty] | open |  |  | open | done |  | done | open | open | open
26.3 | Load Incoterm (File Download / Upload) | n/a | n/a | n/a | test | x | High | done | n/a | Niklas
26.4 | Load Incoterm (Data Export / Import) | n/a | n/a | n/a | test | x | High | done | n/a | Niklas | [14 empty] | n/a |  | n/a | n/a | n/a | n/a
26.5 | Incoterm Language Test (DE/EN) | n/a | n/a | n/a | test |  | High | done | n/a | Maxi | [5 empty] | n/a |  | n/a | n/a | n/a | done | n/a | open |  | n/a |  | n/a | n/a | n/a | n/a
26.6 | Incoterm Language Test (FR/ES) | n/a | n/a | n/a | test |  | High | in progress | n/a | Ulla | FR OK, ES missing in IH1 |  |  |  |  | open |  | open | open | open | open | open | open |  | n/a |  | n/a | n/a | n/a | n/a
26.7 | Incoterm Test (ES)/incoterm | n/a | n/a | n/a | test |  | Medium | retest | n/a | Michael | tested in ID1
27.1 | Change Sales Group | skip | test | skip | n/a |  | Medium | done | n/a | Maxi | Fully Tested (LSA/DT) |  |  |  |  | open |  | open | open | open | done | open | open | done | done |  | done | done | open | open
27.2 | Create Sales Group | skip | test | skip | n/a |  | Medium | done | n/a | Maxi | Fully Tested (LSA/DT) |  |  |  |  | open |  | open | open | open | done | open | open | done | done | done | done | done | open | open
27.3 | Load Sales Group (File Download / Upload) | n/a | n/a | n/a | test | x | Medium | done | n/a | Niklas
27.4 | Load Sales Group (Data Export / Import) | n/a | n/a | n/a | test | x | Medium | done | n/a | Niklas | [14 empty] | n/a |  | n/a | n/a | n/a | n/a
27.5 | Sales Group Language Test (DE/EN) | n/a | n/a | n/a | test |  | Medium | done | n/a | Maxi | [5 empty] | n/a |  | n/a | n/a | n/a | done | n/a | open |  | n/a |  | n/a | n/a | n/a | n/a
27.6 | Sales Group Language Test (FR/ES) | n/a | n/a | n/a | test |  | Medium | error | n/a | Ulla |  | 861 |  |  |  | open |  | open | open | open | open | open | open |  | n/a |  | n/a | n/a | n/a | n/a |  |  | 562
27.7 | Sales Group Test (ES)/grupo de vendedores | n/a | n/a | n/a | test |  | Medium | retest | n/a | Michael | tested in ID1
28.1 | Change Shipping Type | skip | test | skip | n/a |  | Low | done | n/a | Maxi | Fully Tested (LSA/DT) |  |  |  |  | open |  | open | open | open | done | open | open | done | done |  | done | done | open | open
28.2 | Create Shipping Type | skip | test | skip | n/a |  | Low | done | n/a | Maxi | Fully Tested (LSA/DT) |  |  |  |  | open |  | open | open | open | done | open | open | done | done | done | done | done | open | open
28.3 | Load Shipping Type (File Download / Upload) | n/a | n/a | n/a | test | x | Low | done | n/a | Niklas
28.4 | Load Shipping Type (Data Export / Import) | n/a | n/a | n/a | test | x | Low | done | n/a | Niklas | [14 empty] | n/a |  | n/a | n/a | n/a | n/a
28.5 | Shipping Type Language Test (DE/EN) | n/a | n/a | n/a | test |  | Low | done | n/a | Ulla | [5 empty] | n/a |  | n/a | n/a | n/a | n/a | n/a | open |  | n/a |  | n/a | n/a | n/a | n/a
28.6 | Shipping Type Language Test (FR/ES) | n/a | n/a | n/a | test |  | Low | in progress | n/a | Ulla | FR OK, ES missing in IH1 |  |  |  |  | open |  | open | open | open | open | open | open |  | n/a |  | n/a | n/a | n/a | n/a |  |  | 564
28.7 | Shipping Type Test (ES)/clase de expedición | n/a | n/a | n/a | test |  | Medium | retest | n/a | Michael | tested in ID1
29.1 | Change Shipping Conditions | skip | skip | test | n/a |  | Low | done | n/a | Maxi | Fully Tested (LSA/DT) |  |  |  |  | open |  | open | open | open | done | open | open | done | done |  | done | done | open | open |  |  | 486 | open has been resolved! -> But not for Snd S01 --> this is ok as this is 2311
29.2 | Create Shipping Conditions | skip | skip | test | n/a |  | Low | done | n/a | Maxi | Fully Tested (LSA/DT) |  |  |  |  | open |  | open | open | open | done | open | open | done | done | done | done | done | open | open |  |  | 486 | open has been resolved! -> But not for Snd S01 --> this is ok as this is 2311
29.3 | Load Shipping Conditions (File Download / Upload) | n/a | n/a | n/a | test | x | Low | done | n/a | Niklas
29.4 | Load Shipping Conditions (Data Export / Import) | n/a | n/a | n/a | test | x | Low | done | n/a | Niklas | [14 empty] | n/a |  | n/a | n/a | n/a | n/a
29.5 | Shipping Conditions Language Test (DE/EN) | n/a | n/a | n/a | test |  | Low | done | n/a | Ulla | [5 empty] | n/a |  | n/a | n/a | n/a | n/a | n/a | open |  | n/a |  | n/a | n/a | n/a | n/a
29.6 | Shipping Conditions Language Test (FR/ES) | n/a | n/a | n/a | test |  | Low | in progress | n/a | Ulla | FR OK, ES missing in IH1 |  |  |  |  | open |  | open | open | open | open | open | open |  | n/a |  | n/a | n/a | n/a | n/a |  |  | 563
29.7 | Shipping Conditions Test (ES)/condiciones de expedición | n/a | n/a | n/a | test |  | Medium | retest | n/a | Michael | tested in ID1
30.1 | Change Lab/office | test | test | test | n/a |  | Low | open / not tested | n/a | Ulla | [14 empty] | open |  | open | open | open | open |  |  | 536
30.2 | Create Lab/office | test | test | test | n/a |  | Low | open / not tested | n/a | Ulla | [10 empty] | open |  |  | open | open |  | open | open | open | open |  |  | 537
30.3 | Load Lab/Office (File Download / Upload) | n/a | n/a | n/a | test | x | Low | done | n/a | Niklas
30.4 | Load Lab/Office (Data Export / Import) | n/a | n/a | n/a | test | x | Low | error | n/a | Niklas | Open Topic fehlt - xml transformation error, fixe ich selbst | [13 empty] | n/a |  | n/a | n/a | n/a | n/a
30.5 | Lab/Office Language Test (DE/EN) | n/a | n/a | n/a | test |  | Medium | done | n/a | Maxi | [5 empty] | n/a |  | n/a | n/a | n/a | done | n/a | open |  | n/a |  | n/a | n/a | n/a | n/a
30.6 | Lab/Office Language Test (FR/ES) | n/a | n/a | n/a | test |  | Medium | in progress | n/a | Ulla | FR OK, ES missing in IH1 |  |  |  |  | open |  | open | open | open | open | open | open |  | n/a |  | n/a | n/a | n/a | n/a
30.7 | Lab/Office Test (ES)/laboratorio/oficina | n/a | n/a | n/a | test |  | Medium | retest | n/a | Michael | tested in ID1
31.1 | Change BOM Usage | test | test | test | n/a |  | Low | done | n/a | Ulla | [14 empty] | open |  | open | open | open | open
31.2 | Create BOM Usage | test | test | test | n/a |  | Low | done | n/a | Ulla | [10 empty] | open |  |  | open | open |  | open | open | open | open
31.3 | Load BOM Usage (File Download / Upload) | n/a | n/a | n/a | test | x | Low | done | n/a | Niklas
31.4 | Load BOM Usage (Data Export / Import) | n/a | n/a | n/a | test | x | Low | done | n/a | Niklas | [14 empty] | n/a |  | n/a | n/a | n/a | n/a
31.5 | BOM Usage Language Test (DE/EN) | n/a | n/a | n/a | test |  | Low | done | n/a | Ulla | [5 empty] | n/a |  | n/a | n/a | n/a | n/a | n/a | open |  | n/a |  | n/a | n/a | n/a | n/a
31.6 | BOM Usage Language Test (FR/ES) | n/a | n/a | n/a | test |  | Low | in progress | n/a | Ulla | FR OK, ES missing in IH1 |  |  |  |  | open |  | open | open | open | open | open | open |  | n/a |  | n/a | n/a | n/a | n/a
31.7 | BOM Usage Test (ES)/utilización de la lista de materiales | n/a | n/a | n/a | test |  | Medium | retest | n/a | Michael | tested in ID1
32.1 | Create Document Type | skip | test | skip | n/a |  | Very High | done | n/a | Maxi | Fully Tested (LSA/DT) | [9 empty] | done |  |  | done | done | done | done | done | open | open
32.2 | Change Document Type | skip | test | skip | n/a |  | Very High | done | n/a | Maxi | Fully Tested (LSA/DT) | [9 empty] | done | done | done | done | done |  | done | done | open | open |  |  | 548 | Resolved: 465 and 548 and also missing Highlighting, now: retest in IH1, but: new UI Config and new BC Set to be delivered to IH1 and to be retested again
32.3 | Load Document Type (File Download / Upload) | skip | skip | skip | n/a |  | High | done | n/a | Niklas | [5 empty] | open |  | open | open | open | open | open | open |  | n/a |  | n/a | n/a | n/a | n/a
32.4 | Load Document Type (Data Export / Import) | n/a | n/a | n/a | test | x | Very High | open / not tested | n/a | Niklas | [5 empty] | open |  | open | open | open | open | open | open |  | n/a |  | n/a | n/a | n/a | n/a
32.5 | Document Type Language Test (DE/EN) | n/a | n/a | n/a | test |  | Very High | error | n/a | Ulla | [5 empty] | n/a |  | n/a | n/a | n/a | n/a | n/a | open |  | n/a |  | n/a | n/a | n/a | n/a
32.6 | Document Type Language Test (FR/ES) | n/a | n/a | n/a | test |  | Very High | in progress | n/a | Ulla | FR OK, ES missing in IH1 |  |  |  |  | open |  | open | open | open | open | open | open |  | n/a |  | n/a | n/a | n/a | n/a |  |  | 565
32.7 | Document Type Test (ES)/tipo de documento | n/a | n/a | n/a | test |  | Medium | retest | n/a | Michael |  | tested in ID1
33.1 | Create Chart of Account | skip | skip | test | n/a |  | Very High | done | n/a | Ulla | [10 empty] | open |  |  | open | open |  | open | open | open | open |  |  | 482 | 19.6. Low open Remaining. Replication to be tested in all systems
33.2 | Change Chart of Account | skip | skip | test | n/a |  | Very High | done | n/a | Ulla | [14 empty] | open |  | open | open | open | open |  |  | 483 | 19.6 Replication to be tested in all systems
33.3 | Load Chart of Account (File Download / Upload) | n/a | n/a | n/a | test | x | Very High | done | n/a | Niklas
33.4 | Load Chart of Account (Data Export / Import) | n/a | n/a | n/a | test | x | Very High | done | n/a | Niklas | [14 empty] | n/a |  | n/a | n/a | n/a | n/a
33.5 | Chart of Account Language Test (DE/EN) | n/a | n/a | n/a | test |  | Very High | done | n/a | Ulla | [5 empty] | n/a |  | n/a | n/a | n/a | n/a | n/a | open |  | n/a |  | n/a | n/a | n/a | n/a
33.6 | Chart of Account Language Test (FR) | n/a | n/a | n/a | test |  | Very High | done | n/a | Ulla | [5 empty] | open |  | open | open | open | open | open | open |  | n/a |  | n/a | n/a | n/a | n/a
33.7 | Chart of Account Test (ES)/gráfico de la cuenta | n/a | n/a | n/a | test |  | Medium | retest | n/a | Michael |  | tested in ID1
34.1 | Create Operating Concern | test | skip | skip | n/a |  | Low | error | n/a | Maxi | TODO | 846 | 847 WIP |  |  | open |  | open | open | open | error | open | open | open | error | open | error | error | open | open |  |  | 487 | open has been resolved!
34.2 | Change Operating Concern | test | skip | skip | n/a |  | Low | error | n/a | Maxi | TODO | 846 | 847 WIP |  |  | open |  | open | open | open | error | open | open |  | error |  | error | error | open | open |  |  | 487 | open has been resolved!
34.3. | Load Operating Concern (File Download / Upload) | n/a | n/a | n/a | test | x | Low | done | n/a | Niklas
34.4. | Load Operating Concern (Data Export / Import) | n/a | n/a | n/a | test | x | Low | done | n/a | Niklas | [5 empty] | open |  | open | open | open | open | open | open |  | n/a |  | n/a | n/a | n/a | n/a |  |  | 535 | 04.07. XML Transformation / Niklas will check
34.5 | Operating Concern Language Test (DE/EN) | n/a | n/a | n/a | test |  | Low | error | n/a | Maxi |  | 840 |  |  |  | open |  | open | open | open | error | open | open |  | n/a |  | n/a | n/a | n/a | n/a |  |  | 508 (DE) | opens still persists
34.6 | Operating Concern Language Test (FR/ES) | n/a | n/a | n/a | test |  | Low | open / not tested | n/a | Ulla | [5 empty] | open |  | open | open | open | open | open | open |  | n/a |  | n/a | n/a | n/a | n/a |  |  | 566
34.7 | Operating Concern Test (ES)/sociedad PA | n/a | n/a | n/a | test |  | Medium | retest | n/a | Michael |  | tested in ID1
35.1. | Create Language | test | skip | skip | n/a |  | Low | in progress | n/a | Maxi | TODO After Fix | 764 |  |  |  | open |  | open | open | open | error | open | open | open | open | open | open | open | open | open |  |  | 478 | Topic Document 478 has been updated
35.2 | Change Language | test | skip | skip | n/a |  | Low | in progress | n/a | Maxi | TODO |  |  |  |  | open |  | open | open | open | in progress | in progress | in progress |  | in progress |  | in progress | in progress | open | open |  |  | 478 | Topic Document 478 has been updated
35.3 | Load Language (File Download / Upload) | n/a | n/a | n/a | test | x | Very High | done | n/a | Niklas
35.4 | Load Language (Data Export / Import) | n/a | n/a | n/a | test | x | Very High | done | n/a | Niklas | [14 empty] | n/a |  | n/a | n/a | n/a | n/a
35.5 | Language / Language Test (DE/EN) | n/a | n/a | n/a | test |  | Low | done | n/a | Ulla | [5 empty] | n/a |  | n/a | n/a | n/a | n/a | n/a | open |  | n/a |  | n/a | n/a | n/a | n/a
35.6 | Language / Language Test (FR) | n/a | n/a | n/a | test |  | Low | in progress | n/a | Ulla | FR OK, ES missing in IH1 |  |  |  |  | open |  | open | open | open | open | open | open |  | n/a |  | n/a | n/a | n/a | n/a
35.7 | Language Test (ES)/idioma | n/a | n/a | n/a | test |  | Medium | retest | n/a | Michael | tested in ID1
36.1 | Change Location | skip | test | skip | n/a |  | Medium | done | n/a | Maxi | Fully Tested (LSA/DT) |  |  |  |  | open |  | open | open | open | done | open | open | done | done |  | done | done | open | open
36.2 | Create Location | skip | test | skip | n/a |  | Medium | done | n/a | Maxi | Fully Tested (LSA/DT) |  |  |  |  | open |  | open | open | open | done | open | open | done | done | done | done | done | open | open
36.3 | Load Location (File Download / Upload) | n/a | n/a | n/a | test | x | Medium | error | n/a | Niklas |  | 820 | [12 empty] | n/a |  | n/a | n/a | n/a | n/a |  |  | 524 | 04.07. Dieter
36.4 | Load Location (Data Export / Import) | n/a | n/a | n/a | test | x | Medium | done | n/a | Niklas | [14 empty] | n/a |  | n/a | n/a | n/a | n/a
36.5 | Location Language Test (DE/EN) | n/a | n/a | n/a | skip |  | Medium | error | n/a | Maxi |  | 822 |  |  |  | n/a |  | n/a | n/a | n/a | error | n/a | open |  | n/a |  | n/a | n/a | n/a | n/a
36.6 | Location Language Test (FR/ES) | n/a | n/a | n/a | test |  | Medium | in progress | n/a | Ulla | FR OK, ES missing in IH1 | 818 |  |  |  | open |  | open | open | open | open | open | open |  | n/a |  | n/a | n/a | n/a | n/a |  |  | 567
36.7 | Language Test (ES)/ubicación | n/a | n/a | n/a | test |  | Medium | retest | n/a | Michael | tested in ID1
37.1 | Create Exchange Rate (via User Interface) | skip | test | skip | n/a |  | Very High | done | n/a | Gerd | see Test_docu | [9 empty] | done |  |  | open | done |  | done | done | open | open |  |  | 484
37.2 | Change Exchange Rate (via User Interface) | skip | test | skip | n/a |  | Very High | open / not tested | n/a | Thomas | [14 empty] | open |  | open | open | open | open |  |  | 485
37.2 | Change Exchange Rate (via external service) | skip | skip | skip | test |  | Very High | open / not tested | n/a | Thomas | [14 empty] | open |  | open | open | open | open |  |  | 534
37.3 | Load Exchange Rate (initial Load) | n/a | n/a | n/a | test | x | Very High | in progress | n/a | Thomas | [14 empty] | n/a |  | n/a | n/a | n/a | n/a
37.4 | Data Feed | n/a | test | n/a | test |  | Very High | open / not tested | n/a | Thomas | [14 empty] | n/a |  | n/a | n/a | n/a | n/a
37.5 | Exchange Rate Language Test (DE/EN) | n/a | test | n/a | test |  | Medium | error | n/a | Ulla |  | 800 |  |  |  | n/a |  | n/a | n/a | n/a | n/a | n/a | open |  | n/a |  | n/a | n/a | n/a | n/a
37.6 | Exchange Rate Language Test (FR/ES) | n/a | n/a | n/a | test |  | Medium | done | n/a | Ulla | [5 empty] | open |  | open | open | open | open | open | open |  | n/a |  | n/a | n/a | n/a | n/a
37.7 | Exchange Rate Test (ES)/tipo de cambio | n/a | n/a | n/a | test |  | Medium | retest | n/a | Michael | tested in ID1
38.1 | Change Characteristics | test | test | test | test |  | Very High | in progress | n/a | Maxi | TODO | [9 empty] | open |  |  |  | open |  | open | open | open | open
38.2 | Create Characteristics | skip | test | test | test |  | Very High | in progress | n/a | Maxi | TODO | [9 empty] | open |  |  | open | open | open | open | open | open | open |  |  | 580 (Typo) | 581 (Replication)
38.3 | Copy Characteristics |  | test | test | test |  | Very High | error | n/a | Sabine |  | 809 | [8 empty] | open |  |  |  | n/a |  | n/a | n/a | n/a | n/a |  |  | 582
38.4 | Load Characteristics (File Download / Upload) | n/a | n/a | n/a | test | x | High | done | n/a | Niklas | [14 empty] | n/a |  | n/a | n/a | n/a | n/a |  |  | 507 | 17.6. Mike working on it (also for Arcelor Mittal). In general it works
38.5 | Load Characteristics (IDocs) | n/a | n/a | n/a | test | x | Low | open / not tested | n/a | Michael | [14 empty] | n/a |  | n/a | n/a | n/a | n/a
38.6 | Characteristics - Language Test (DE/EN) | n/a | n/a | n/a | test |  | Very High | error | n/a | Ulla |  | 783 |  |  |  | open |  | open | open | open | open | open | open |  | n/a |  | n/a | n/a | n/a | n/a |  |  | 509 (DE) | 17.6. Ulla should check - open still persists
38.7 | Characteristics - Language Test (FR/ES) | n/a | n/a | n/a | test |  | Very High | in progress | n/a | Ulla | FR OK, ES missing in IH1 |  |  |  |  | open |  | open | open | open | open | open | open |  | n/a |  | n/a | n/a | n/a | n/a |  |  | 568
38.8 | Characteristics Test (ES)/características | n/a | n/a | n/a | test |  | Medium | retest | n/a | Michael | tested in ID1
39.1 | Change Classes | test | test | test | test |  | Very High | error | n/a | Sabine |  | 805 | 807 | [7 empty] | open |  |  |  | open |  | open | open | open | open |  |  | 586 | open from Exxon
39.2 | Create Classes | test | test | test | test |  | Very High | error | n/a | Sabine |  | 805 | 807 | [7 empty] | open |  |  | open | open |  | open | open | open | open
39.3 | Copy Classes |  | skip | test | test |  | Very High | error | n/a | Sabine |  | 808 | [8 empty] | open |  |  |  | n/a |  | n/a | n/a | n/a | n/a
39.4 | Load Classes (File Download / Upload) | n/a | n/a | n/a | test | x | High | error | n/a | Niklas |  | 815 | [12 empty] | n/a |  | n/a | n/a | n/a | n/a |  |  | 507 | 17.6. Mike working on it (also for Arcelor Mittal). In general it works
39.5 | Load Classes (IDocs) | n/a | n/a | n/a | test | x | Low | open / not tested | n/a | Michael | [14 empty] | n/a |  | n/a | n/a | n/a | n/a
39.6 | Classes - Language Test (DE/EN) | n/a | n/a | n/a | test |  | High | error | n/a | Maxi |  | 842 |  |  |  | n/a |  | n/a | n/a | n/a | error | n/a | open |  | n/a |  | n/a | n/a | n/a | n/a
39.7 | Classes - Language Test (FR/ES) | n/a | n/a | n/a | test |  | Very High | in progress | n/a | Ulla | FR OK, ES missing in IH1 |  |  |  |  | open |  | open | open | open | open | open | open |  | n/a |  | n/a | n/a | n/a | n/a |  |  | 519 | 20.06. asked Mike to change it (needs investigation)
39.8 | Classes Test (ES)/clases | n/a | n/a | n/a | test |  | Medium | retest | n/a | Michael | tested in ID1
40.1 | Change MRP Type | skip | test | skip | n/a |  | Medium | done | n/a | Maxi | Fully Tested (LSA/DT) |  |  |  |  | open |  | open | open | open | done | open | open | done | done |  | done | done | open | open
40.2 | Create MRP Type | skip | test | skip | n/a |  | Medium | done | n/a | Maxi | Fully Tested (LSA/DT) |  |  |  |  | open |  | open | open | open | done | open | open | done | done | done | done | done | open | open
40.3 | Load MRP Type (File Download / Upload) | n/a | n/a | n/a | test | x | Medium | done | n/a | Niklas | [14 empty] | n/a |  | n/a | n/a | n/a | n/a
40.4 | Load MRP Type (Data Export / Import) | n/a | n/a | n/a | test | x | Medium | error | n/a | Niklas |  | 826 |  |  |  | open |  | open | open | open | open | open | open |  | n/a |  | n/a | n/a | n/a | n/a |  |  | 526 | 04.07. XML Transformation / Niklas will check
40.5 | MRP Type - Language Test (DE/EN) | n/a | n/a | n/a | test |  | Medium | done with limitations | n/a | Maxi | [5 empty] | n/a |  | n/a | n/a | n/a | done with limitations | n/a | open |  | n/a |  | n/a | n/a | n/a | n/a
40.6 | MRP Type - Language Test (FR/ES) | n/a | n/a | n/a | test |  | Medium | in progress | n/a | Ulla | FR OK, ES missing in IH1 |  |  |  |  | open |  | open | open | open | open | open | open |  | n/a |  | n/a | n/a | n/a | n/a
40.7 | MRP Type Test (ES)/tipo de planificación de necesidades | n/a | n/a | n/a | test |  | Medium | retest | n/a | Michael | tested in ID1
41.1 | Change MRP Profile | test | skip | skip | n/a |  | Medium | error | n/a | Maxi | TODO After Fix | 802 | 803 | 804 |  | open |  | open | open | open | error | open | open |  | error |  | error | error | open | open |  |  | 489 | open(?) still persists -> Mike
41.2 | Create MRP Profile | test | skip | skip | n/a |  | Medium | error | n/a | Maxi | TODO After Fix | 802 | 803 | 804 |  | open |  | open | open | open | error | open | open | open | error | open | error | error | open | open |  |  | 489 | open(?) still persists -> Mike
41.3 | Load MRP Profile (File Download / Upload) | n/a | n/a | n/a | test | x | Medium | error | n/a | Niklas |  | 822 | [12 empty] | n/a |  | n/a | n/a | n/a | n/a |  |  | 525 | 04.07. Dieter
41.4 | Load MRP Profile (Data Export / Import) | n/a | n/a | n/a | test | x | Medium | done | n/a | Niklas | [14 empty] | n/a |  | n/a | n/a | n/a | n/a
41.5 | MRP Profile - Language Test (DE/EN) | n/a | n/a | n/a | test |  | Medium | error | n/a | Maxi |  | 843 |  |  |  | open |  | open | open | open | error | open | open |  | n/a |  | n/a | n/a | n/a | n/a |  |  | 510 (DE)
41.6 | MRP Profile - Language Test (FR/ES) | n/a | n/a | n/a | test |  | Medium | in progress | n/a | Ulla | FR OK, ES missing in IH1 |  |  |  |  | open |  | open | open | open | open | open | open |  | n/a |  | n/a | n/a | n/a | n/a |  |  | 569
41.7 | MRP Profile Test (ES)/perfil de planificación de necesidades | n/a | n/a | n/a | test |  | Medium | retest | n/a | Michael | tested in ID1
42.1 | Change MRP Area | skip | test | skip | test |  | Very High | error | n/a | Ulla |  | 860 | [12 empty] | open |  | open | open | open | open
42.2 | Create MRP Area | skip | test | skip | test |  | Very High | done | n/a | Ulla |  | 782 | [8 empty] | done |  |  | done | done |  | done | open | open | open
42.3 | Load MRP Area (File Download / Upload) | n/a | n/a | n/a | test | x | High | error | n/a | Niklas |  | 810 | [12 empty] | n/a |  | n/a | n/a | n/a | n/a |  |  |  | *upload funktioniert
42.4 | Load MRP Area (Data Export / Import) | n/a | n/a | n/a | test | x | High | done | n/a | Niklas | [14 empty] | n/a |  | n/a | n/a | n/a | n/a
42.5 | MRP Area - Language Test (DE/EN) | n/a | n/a | n/a | test |  | Very High | done | n/a | Ulla | [5 empty] | n/a |  | n/a | n/a | n/a | n/a | n/a | open |  | n/a |  | n/a | n/a | n/a | n/a
42.5 | MRP Area - Language Test (FR/ES) | n/a | n/a | n/a | test |  | Very High | in progress | n/a | Ulla | FR OK, ES missing in IH1 |  |  |  |  | open |  | open | open | open | open | open | open |  | n/a |  | n/a | n/a | n/a | n/a |  |  | 546
42.7 | MRP Area Test (ES)/área de planificación MRP | n/a | n/a | n/a | test |  | Medium | retest | n/a | Michael | tested in ID1
43.1 | Change Tax Code | skip | test | skip | test |  | Very High | in progress | n/a | Sabine | [5 empty] | open |  | open | open | open | open | open | open |  | open |  | open | open | open | open |  |  | 490 | 11.07.: After the distribution fields in IR1/200, IR2/200 and S01/400 have been activated with transaction /ITR/RDM_LSA_FIELDS, the changes in the update work. 10.07.: drei Feldinhalte müssen noch im Local Scope aktiviert werden 02.07.: 1) Die Feldinhalte Destination tax code, EU code/code, Tol.pro.rate , Inactive werden durch den LSA-Report nicht in der Tabelle T007A in den Zielsystemen IR1/200, IR2/200 und S01/400 aktualisiert. In der RDM-Tabelle /ITR/T007A ist der Änderung korrekt upgedated.
43.2 | Create Tax Code | skip | test | skip | test |  | Very High | in progress | n/a | Sabine | [5 empty] | open |  | open | open | open | open | open | open | open | open |  | open | open | open | open | solved |  | 488
43.3 | Load Tax Code(File Download / Upload) | skip | test | skip | test | x | High | done | n/a | Niklas | [14 empty] | n/a |  | n/a | n/a | n/a | n/a
43.4 | Load Tax Code (Data Export / Import) | skip | test | skip | test | x | High | done | n/a | Niklas | tax code is working but the error is still relevant | 811 | [12 empty] | n/a |  | n/a | n/a | n/a | n/a |  |  | 516
43.5 | Tax Code - Language Test (DE/EN) | n/a | n/a | n/a | test |  | Medium | error | n/a | Maxi |  | 844 |  |  |  | n/a |  | n/a | n/a | n/a | error | n/a | open |  | n/a |  | n/a | n/a | n/a | n/a
43.6 | Tax Code - Language Test (FR/ES) | n/a | n/a | n/a | test |  | Medium | error | n/a | Ulla |  | 862 |  |  |  | open |  | open | open | open | open | open | open |  | n/a |  | n/a | n/a | n/a | n/a |  |  | 518 + 577 | 20.06. Christine needs to find a good translation of the abbreviations
43.7 | Tax Code Test (ES)/código de impuesto | n/a | n/a | n/a | test |  | Medium | retest | n/a | Michael | tested in ID1
44.1 | Change Valuation Class | skip | test | skip | n/a |  | High | done | n/a | Maxi | Fully Tested (LSA/DT) |  |  |  |  | open |  | open | open | open | done | open | open | done | done |  | done | done | open | open
44.2 | Create Valuation Class | skip | test | skip | n/a |  | High | done | n/a | Maxi | Fully Tested (LSA/DT) |  |  |  |  | open |  | open | open | open | done | open | open | done | done | done | done | done | open | open
44.3 | Load Valuation Class (File Download / Upload) | n/a | n/a | n/a | test | x | Low | in progress | n/a | Niklas | [14 empty] | n/a |  | n/a | n/a | n/a | n/a
44.4 | Load Valuation Class (Data Export / Import) | n/a | n/a | n/a | test | x | Low | done | n/a | Niklas | [14 empty] | n/a |  | n/a | n/a | n/a | n/a |  |  | 516
44.5 | Valuation Class - Language Test (DE/EN) | n/a | n/a | n/a | test |  | Low | open / not tested | n/a | Ulla | [14 empty] | n/a |  | n/a | n/a | n/a | n/a
44.6 | Valuation Class - Language Test (FR/ES) | n/a | n/a | n/a | test |  | Low | open / not tested | n/a | Ulla | [5 empty] | open |  | open | open | open | open | open | open |  | n/a |  | n/a | n/a | n/a | n/a |  |  | 578
44.7 | Valuation Class Test (ES)/cateogoría de valuación | n/a | n/a | n/a | test |  | Medium | retest | n/a | Michael | tested in ID1
45.1 | Change Sales Office | skip | skip | test | test |  | Medium | open / not tested | n/a | Sabine | [5 empty] | open |  | open | open | open | open | open | open |  | open |  | open | open | open | open | solved |  | 511 | 11.07.: ok - language not replicated / strange behaviour 09.07.: should be fixed 03.07.: Adapterclass missing … not in Software Component ITO
45.2 | Create Sales Office | skip | skip | test | test |  | Medium | open / not tested | n/a | Sabine | [10 empty] | open |  |  | open | open |  | open | open | open | open |  |  | 438 | 11.07.: Selly should start to work on it next week There are still 6 points to be completed in the Sales Organization object
45.3 | Load Sales Office (File Download / Upload) | skip | skip | test | test | x | Medium | error | n/a | Niklas |  | 818 |  |  |  | open |  | open | open | open | open | open | open |  | n/a |  | n/a | n/a | n/a | n/a |  |  | 524 | 04.07. : create new variant should do the job -> Niklas -> open but not transported
45.4 | Load Sales Office (Data Export / Import) | skip | skip | test | test | x | Medium | in progress | n/a | Niklas | [14 empty] | n/a |  | n/a | n/a | n/a | n/a
45.5 | Sales Office - Language Test (DE/EN) | n/a | n/a | n/a | test |  | Medium | done | n/a | Ulla | [14 empty] | n/a |  | n/a | n/a | n/a | n/a
45.6 | Sales Office - Language Test (FR/ES) | n/a | n/a | n/a | test |  | Medium | in progress | n/a | Ulla | FR OK, ES missing in IH1 |  |  |  |  | open |  | open | open | open | open | open | open |  | n/a |  | n/a | n/a | n/a | n/a
45.7 | Sales Office Test (ES)/oficina de ventas | n/a | n/a | n/a | test |  | Medium | retest | n/a | Michael | tested in ID1
46.1 | Change Scope of Planning | skip | test | skip | test |  | Very High | error | n/a | Sabine |  | 850 | 851 | [7 empty] | open |  |  |  | done |  | done | done | open | open | solved openTopics |  | 521
46.2 | Create Scope of Planning | skip | test | skip | test |  | Very High | done | n/a | Sabine | [5 empty] | open |  | open | open | open | open | open | open | open | done |  | done | done | open | open |  |  | 513 | Field translation “Plant Description” to “Beschreibung Werk” and “MRP Aera Description” to "Beschreibung Dispobereich"
46.3 | Load Scope of Planning (File Download / Upload) | skip | test | skip | test | x | High | done | n/a | Niklas |  | 812 |  |  |  | open |  | open | open | open | open | open | open |  | n/a |  | n/a | n/a | n/a | n/a | proposal openTopics |  | 502
46.4 | Load Scope of Planning (Data Export / Import) | skip | test | skip | test | x | High | error | n/a | Niklas | nicht vorhanden | [13 empty] | n/a |  | n/a | n/a | n/a | n/a |  |  | 517 | not able to export
46.5 | Scope of Planning - Language Test (DE/EN) | n/a | n/a | n/a | test |  | Very High | done | n/a | Ulla | [5 empty] | open |  | open | open | open | open | open | open |  | n/a |  | n/a | n/a | n/a | n/a |  |  | 552 (DE)
46.6 | Scope of Planning - Language Test (FR/ES) | n/a | n/a | n/a | test |  | Very High | in progress | n/a | Ulla | FR OK, ES missing in IH1 |  |  |  |  | open |  | open | open | open | open | open | open |  | n/a |  | n/a | n/a | n/a | n/a
46.7 | Scope of Planning for MRP Unit Test (ES)/ámbito de planificación | n/a | n/a | n/a | test |  | Medium | retest | n/a | Michael | tested in ID1
47.1 | Change MRP Controller | skip | test | skip | test |  | Very High | done | n/a | Maxi | Fully Tested (LSA/DT) | [9 empty] | done |  |  | done | done |  | done | done | open | open |  |  | 500 | 17.6. Low opens remaining
47.2 | Create MRP Controller | skip | test | skip | test |  | Very High | done | n/a | Maxi | Fully Tested (LSA/DT) | [9 empty] | done |  |  | done | done | done | done | done | open | open |  |  | 491 | 17.6. Low opens remaining
47.3 | Load MRP Controller File Download / Upload) | n/a | test | skip | n/a | x | High | done | n/a | Niklas | [14 empty] | n/a |  | n/a | n/a | n/a | n/a |  |  | 516
47.4 | Load MRP Controller (Data Export / Import) | n/a | n/a | n/a | test | x | High | done | n/a | Niklas | [14 empty] | n/a |  | n/a | n/a | n/a | n/a
47.5 | MRP Controller - Language Test (DE/EN) | n/a | n/a | n/a | test |  | Very High | done | n/a | Ulla | [5 empty] | n/a |  | n/a | n/a | n/a | n/a | n/a | open |  | n/a |  | n/a | n/a | n/a | n/a
47.6 | MRP Controller - Language Test (FR/ES) | n/a | n/a | n/a | test |  | Very High | in progress | n/a | Ulla | FR OK, ES missing in IH1 |  |  |  |  | open |  | open | open | open | open | open | open |  | n/a |  | n/a | n/a | n/a | n/a
47.7 | MRP Controller Test (ES)/planificador de necesidades | n/a | n/a | n/a | test |  | Medium | retest | n/a | Michael | tested in ID1
48.1 | Change Holiday Calendar | [5 empty] | Very High | open / not tested | n/a | Maxi | [10 empty] | open | open | open |  | open |  | open | open | open | n/a
48.2 | Create Holiday Calendar | [5 empty] | Very High | open / not tested | n/a | Maxi | [10 empty] | open | open | open | open | open |  | open | open | open | n/a
48.3 | Load Holiday Calendar File Download / Upload) | [5 empty] | Very High | open / not tested | n/a | Niklas
48.4 | Load Holiday Calendar (Data Export / Import) | [5 empty] | Very High | on hold | n/a | Niklas
48.5 | Holiday Calendar - Language Test (DE/EN/FR/ES) | [5 empty] | Very High | open / not tested | n/a | Maxi
49.1 | Change Public Holiday | [5 empty] | Very High | open / not tested | n/a | Maxi | [10 empty] | open | open | open |  | open |  | open | open | open | n/a
49.2 | Create Public Holiday | [5 empty] | Very High | open / not tested | n/a | Maxi | [10 empty] | open | open | open | open | open |  | open | open | open | n/a
49.3 | Load Public Holiday File Download / Upload) | [5 empty] | Very High | open / not tested | n/a | Niklas
49.4 | Load Public Holiday (Data Export / Import) | [5 empty] | Very High | on hold | n/a | Niklas
49.5 | Public Holiday - Language Test (DE/EN/FR/ES) | [5 empty] | Very High | open / not tested | n/a | Maxi
750.0 MDF | ******************************************* | [5 empty] | *********
750.1 RULE | Configuration (Rule) Management | n/a | n/a | n/a | test |  | Very High | error | n/a | Ulla | 752 - same issue | 762 | [21 empty] | 773
751.1 MDF | ValueMapping | n/a | n/a | n/a | test |  | High | in progress | n/a | Maxi | TODO | [21 empty] | 551
752.1 MDF | KeyMapping | n/a | n/a | n/a | test |  | High | open / not tested | n/a | Maxi | TODO
753.1 MDF | Webservice | n/a | n/a | n/a | test |  | Low | on hold | n/a | Michael | [14 empty] | open |  | open | open | open | open |  |  | 535 | Check after IH1 Refresh
754.1 MDF | Deletions | n/a | n/a | n/a | test |  | Very High | open / not tested | n/a | Thomas
755.1 MDF | Searchhelps | n/a | n/a | n/a | test |  | Very High | open / not tested | n/a | Gerd
800.0 RDH | ******************************************* | [5 empty] | *********
800.1 RDH | Reference Data Harmonization | n/a | n/a | n/a | test |  | Very High | open / not tested | n/a | Gerd
850.0 Install & Upgrade | ******************************************* | [5 empty] | *********
851.1 INST | Install (S03 Smoketest) | n/a | n/a | n/a | test |  | Very High | on hold | n/a | Dieter
852.1 OLD Release Check | Check Replication to older (and newer RDM Release (S01) | n/a | n/a | n/a | test |  | Very High | open / not tested | n/a | Michael
853.1 UPGR | Upgrade | n/a | n/a | n/a | test |  | Very High | on hold | n/a | Dieter
900.0 Special Tests | ******************************************* | [5 empty] | *********
901.1 DRF | Data Replication | n/a | n/a | n/a | test |  | Very High | open / not tested | n/a | Michael | [22 empty] | 535
902.1 ENH | Enhancements and Upgrade | n/a | n/a | n/a | test |  | Very High | on hold | n/a | Mike | [22 empty] | 585 | 11.07. SAP Ticket created in order to ask if a Customer Include needs to be there. Dependency with Frank's coding that avoids the generation of CIs when we enhance objects in the standard? Customer Include not generated
903.1 FR/ES | Translation to FR/ES (MDF, RDH, DRF) | n/a | n/a | n/a | test |  | Medium | error | n/a | Ulla | 796, 797
904.1 SOLMAN | SolManager Tests |  |  |  | test |  | Low | on hold | n/a | Michael
905.1 GTS | GTS Tests |  |  | test |  |  | Very High | retest | n/a | Michael | Tested in IH2/S02 | 737
Testcases | Link to Testcases
Checklist | Checklist Scope of Planning
Open Topics | Excel
Open Topics Details | Topic Details
Status | in progress
done / done with limitations
open / not tested
error
retest