## Itego MDG RDM Test Cases 2509
Test Case | Goal | Description | 3-step | 2-step | 1-step | General | Load/Mass | Priority | Status | Remaining Test Priority | Tester | Short Comment | Issue Link | Issue Link | Issue Link | New attr./obj | Test ID1 100 | Test IG1 200 | Test ID1 400 LSA | Test ID1 400 Direct and manual | Test IH2 | Test IH1 | Retest IH2 | Retest IH1 | Test IH1 100 (direct) | Rcv: IH1 400 | Rcv: IH1 400 (direct) | Rcv: IR1 200 | Rcv: IR2 200 | Rcv: S03 400 | Snd: S03 / Rcv IH1 400
01.0 RDG |  | ****************************************** | [5 empty] | *********
01.1 |  | Change Material Group | test | test | test | n/a |  | Very High |  |  | Sabine
01.2 |  | Create Material Group | test | test | test | n/a |  | Very High |  |  | Sabine
01.4 |  | Load Material Group (Data Export / Import) | skip | test | skip | n/a | x | High |  |  | Niklas | [5 empty] | open |  | open | open | open
01.5 |  | Load Material Group (File Download / Upload) |  |  | n/a | test | x | Very High |  |  | Niklas | [5 empty] | open |  | open | open | open
01.6 |  | Local Customizing for Material Group (incl UoM) | n/a | n/a | n/a | test |  | Medium |  |  | Niklas
01.7 |  | Material Group Language Test (DE/EN) | n/a | n/a | n/a | test |  | Medium |  |  | Ulla | [5 empty] | n/a |  | n/a | n/a | n/a
01.8 |  | Material Group Language Test (FR) | n/a | n/a | n/a | test |  | Medium |  |  | Ulla | [5 empty] | open |  | open | open | open
01.9 |  | Material Group Language Test (ES)/grupo de materiales | test | test | test | test |  | Medium |  |  | Ulla
01.10 |  | Material Group Delete Text | [5 empty] | Very High |  |  | Thomas | [5 empty] | done |  | done | error
02.1 | 2509 | Change Unit of Measure | skip | skip | test | n/a |  | High |  |  | Maxi | [5 empty] | open |  | open | open | open
02.2 | 2509 | Create Unit of Measure | skip | skip | test | n/a |  | High |  |  | Maxi | [5 empty] | open |  | open | open | open
02.3 | 2509 | Load Unit of Measure (File Download / Upload) | n/a | n/a | n/a | test | x | High |  |  | Niklas
02.4 | 2509 | Load Unit of Measure (Data Export / Import) | n/a | n/a | n/a | test | x | High |  |  | Niklas
02.5 | 2509 | Unit of Measure Language Test (DE/EN) | n/a | n/a | n/a | test |  | Low |  |  | Ulla | [5 empty] | n/a |  | n/a | n/a | n/a
02.6 | 2509 | Unit of Measure Language Test (FR/ES/ES) | n/a | n/a | n/a | test |  | Low |  |  | Ulla | [5 empty] | open |  | open | open | open
02.7 | 2509 | Unit of Measure Language Test (ES)/Unidad de medida | n/a | n/a | n/a | test |  | Low |  |  | Ulla
03.1 | 2509 | Change Country | test | skip | skip | n/a |  | High |  |  | Maxi | [5 empty] | open |  | open | open | open
03.2 | 2509 | Create Country | test | skip | skip | n/a |  | High |  |  | Maxi | [5 empty] | open |  | open | open | open
03.3 | 2509 | Load Country (File Download / Upload) | n/a | n/a | n/a | test | x | High |  |  | Niklas
03.4 | 2509 | Load Country (Data Export / Import) | n/a | n/a | n/a | test | x | High |  |  | Niklas
03.5 | 2509 | Country Language Test (DE/EN/FR/ES/ES) | n/a | n/a | n/a | test |  | Low |  |  | Maxi | [5 empty] | n/a |  | n/a | n/a | n/a
03.6 | 2509 | Country Language Test (FR/ES/ES) | n/a | n/a | n/a | test |  | Low |  |  | Ulla | [5 empty] | open |  | open | open | open
03.7 | 2509 | Country Test (ES)/país | n/a | n/a | n/a | test |  | Low |  |  | Ulla
04.1 | 2509 | Change Region | skip | test | skip | n/a |  | High |  |  | Maxi | [5 empty] | open |  | open | open | open
04.2 | 2509 | Create Region | skip | test | skip | n/a |  | High |  |  | Maxi | [5 empty] | open |  | open | open | open
04.3 | 2509 | Load Region (File Download / Upload) | n/a | n/a | n/a | test | x | High |  |  | Niklas
04.4 | 2509 | Load Region (Data Export / Import) | n/a | n/a | n/a | test | x | High |  |  | Niklas
04.5 | 2509 | Region Language Test (DE/EN) | n/a | n/a | n/a | test |  | Low |  |  | Maxi | [5 empty] | n/a |  | n/a | n/a | n/a
04.6 | 2509 | Region Language Test (FR/ES/ES) | n/a | n/a | n/a | test |  | Low |  |  | Ulla | [5 empty] | open |  | open | open | open
04.7 | 2509 | Region Test (ES)/región | n/a | n/a | n/a | test |  | Low |  |  | Ulla
05.1 | 2509 | Change Purchasing Group | skip | test | skip | n/a |  | High |  |  | Sabine
05.2 | 2509 | Create Purchasing Group | skip | test | skip | n/a |  | High |  |  | Sabine
05.3 | 2509 | Load Purchasing Group (File Download / Upload) | n/a | n/a | n/a | test | x | High |  |  | Niklas
05.4 | 2509 | Load Purchasing Group (Data Export / Import) | n/a | n/a | n/a | test | x | High |  |  | Niklas
05.5 | 2509 | Purchasing Group Language Test (DE/EN) | n/a | n/a | n/a | test |  | Low |  |  | Ulla
05.6 | 2509 | Purchasing Group Language Test (FR/ES) | n/a | n/a | n/a | test |  | Low |  |  | Ulla | [5 empty] | open |  | open | open | open
05.7 |  | Purchaing Group Test (ES)/grupo de compras | n/a | n/a | n/a | test |  | Medium |  |  | Michael
06.1 | 2509 | Change Purchasing Organization | skip | skip | test | n/a |  | High |  |  | Ulla
06.2 | 2509 | Create Purchasing Organization | skip | skip | test | n/a |  | High |  |  | Ulla
06.3 | 2509 | Load Purchasing Organization (File Download / Upload) | n/a | n/a | n/a | test | x | High |  |  | Niklas
06.4 | 2509 | Load Purchasing Organization (Data Export / Import) | n/a | n/a | n/a | test | x | High |  |  | Niklas
06.5 | 2509 | Purchasing Organization Language Test (DE/EN) | n/a | n/a | n/a | test |  | Low |  |  | Ulla
06.6 | 2509 | Purchasing Organization Language Test (FR/ES/ES) | n/a | n/a | n/a | test |  | Low |  |  | Ulla | [5 empty] | open |  | open | open | open
06.7 | 2509 | Purchasing Organizsation Test (ES)/organización de compras | n/a | n/a | n/a | test |  | Low |  |  | Ulla
07.1 | 2509 | Change Account Group G/L | skip | test | skip | n/a |  | High |  |  | Ulla
07.2 | 2509 | Create Account Group G/L | skip | test | skip | n/a |  | High |  |  | Ulla
07.3 | 2509 | Load Account Group G/L (File Download / Upload) | n/a | n/a | n/a | test | x | High |  |  | Niklas
07.4 | 2509 | Load Account Group G/L (Data Export / Import) | n/a | n/a | n/a | test | x | High |  |  | Niklas
07.5 | 2509 | Change Account Group G/L - Scheduled LSA Subscriber | skip | test | skip | n/a |  | Medium |  |  | Gerd
07.6 | 2509 | Account Group GL Language Test (DE/EN) | n/a | n/a | n/a | test |  | Low |  |  | Ulla
07.7 | 2509 | Account Group GL Language Test (FR/ES/ES) | n/a | n/a | n/a | test |  | Low |  |  | Ulla | [5 empty] | open |  | open | open | open
07.7 | 2509 | Account Group Test (ES)/grupo de cuentas | n/a | n/a | n/a | test |  | Low |  |  | Ulla
08.1 | 2509 | Change Account Group Vendor | test | skip | skip | n/a |  | High |  |  | Ulla
08.2 | 2509 | Create Account Group Vendor | test | skip | skip | n/a |  | High |  |  | Ulla
08.3 | 2509 | Load Account Group Vendor (File Download / Upload) | n/a | n/a | n/a | test | x | High |  |  | Niklas
08.4 | 2509 | Load Account Group Vendor (Data Export / Import) | n/a | n/a | n/a | test | x | High |  |  | Niklas
08.5 | 2509 | Account Group Vendor Language Test (DE/EN) | n/a | n/a | n/a | test |  | Low |  |  | Ulla
08.6 | 2509 | Account Group Vendor Language Test (FR/ES/ES) | n/a | n/a | n/a | test |  | Low |  |  | Ulla | [5 empty] | open |  | open | open | open
08.7 | 2509 | Vendor Account Group Test (ES)/Grupo de Cuentas de Proveedor | n/a | n/a | n/a | test |  | Low |  |  | Ulla
09.1 | 2509 | Change Account Group Customer | skip | test | skip | n/a |  | High |  |  | Ulla
09.2 | 2509 | Create Account Group Customer | skip | test | skip | n/a |  | High |  |  | Ulla
09.3 | 2509 | Load Account Group Customer (File Download / Upload) | n/a | n/a | n/a | test | x | High |  |  | Niklas
09.4 | 2509 | Load Account Group Customer (Data Export / Import) | n/a | n/a | n/a | test | x | High |  |  | Niklas
09.5 | 2509 | Account Group Customer Language Test (DE/EN) | n/a | n/a | n/a | test |  | Low |  |  | Ulla
09.6 | 2509 | Account Group Customer Language Test (FR/ES/ES) | n/a | n/a | n/a | test |  | Low |  |  | Ulla | [5 empty] | open |  | open | open | open
09.7 | 2509 | Customer Account Group Test (ES)/Grupo de Cuentas de Cliente | n/a | n/a | n/a | test |  | Low |  |  | Ulla
10.1 |  | Change Product Hierarchy | test | skip | skip | n/a |  | Very High |  |  | Michael
10.2 |  | Create Product Hierarchy | test | skip | skip | n/a |  | Very High |  |  | Michael
10.3 |  | Load Product Hierarchy (File Download / Upload) | n/a | n/a | n/a | test | x | Very High |  |  | Michael
10.4 |  | Product Hierarchy Language Test (DE/EN) | n/a | n/a | n/a | test |  | Very High |  |  | Michael
10.5 |  | Product Hierarchy Language Test (FR) | n/a | n/a | n/a | test |  | Very High |  |  | Michael | [5 empty] | open |  | open | open | open
10.6 |  | Producty Hierarchy Test (ES)/jerarquía de productos | n/a | n/a | n/a | test |  | Medium |  |  | Michael
10.7 |  | Product Hierarchy Remove Subnode |  |  |  | test |  | High |  |  | Michael
10.8 |  | Product Hierarchy Remove Node |  |  |  | test |  | High |  |  | Michael
10.9 |  | Product Hierarchy Delete Subnode |  |  |  | test |  | High |  |  | Michael
10.10 |  | Product Hierarchy Delete Node |  |  |  | test |  | High |  |  | Michael
10.11 |  | Product Hierarchy Move Node |  |  |  | test |  | High |  |  | Michael
10.12 |  | Product Hierarchy Move Node with Subtree |  |  |  | test |  | High |  |  | Michael
11.1 | 2509 | Change Company Code | skip | test | skip | n/a |  | High |  |  | Sabine
11.2 | 2509 | Create Company Code | skip | test | skip | n/a |  | High |  |  | Sabine
11.3 | 2509 | Load Company Code (File Download / Upload) | n/a | n/a | n/a | test | x | High |  |  | Niklas
11.4 | 2509 | Load Company Code (Data Export / Import) | n/a | n/a | n/a | test | x | High |  |  | Niklas | [5 empty] | open |  | open | open | open
11.5 | 2509 | Company Code Language Test (DE/EN) | n/a | n/a | n/a | test |  | Low |  |  | Maxi | [5 empty] | open |  | open | open | open
11.6 | 2509 | Company Code Language Test (EN/DE) | n/a | n/a | n/a | test |  | Low |  |  | Ulla | [5 empty] | open |  | open | open | open
11.7 | 2509 | Company code Test (ES)/sociedad | n/a | n/a | n/a | test |  | Low |  |  | Ulla
12.1 | 2509 | Change Plant | test | test | test | n/a |  | High |  |  | Gerd
12.2 | 2509 | Create Plant | test | test | test | n/a |  | High |  |  | Gerd
12.3 | 2509 | Load Plant (File Download / Upload) | n/a | n/a | n/a | test | x | High |  |  | Niklas
12.4 | 2509 | Load Plant (Data Export / Import) | n/a | n/a | n/a | test | x | High |  |  | Niklas
12.6 | 2509 | Plant Language Test (DE/EN) | n/a | n/a | n/a | test |  | Low |  |  | Ulla | [5 empty] | n/a |  | n/a | n/a | n/a
12.7 | 2509 | Plant Language Test (FR/ES/ES) | n/a | n/a | n/a | test |  | Low |  |  | Ulla | [5 empty] | open |  | open | open | open
12.8 | 2509 | Plant Test (ES)/Fábrica | n/a | n/a | n/a | test |  | Low |  |  | Ulla
13.1 | 2509 | Change Payment Term | skip | skip | test | n/a |  | High |  |  | Sabine
13.2 | 2509 | Create Payment Term | skip | skip | test | n/a |  | High |  |  | Sabine
13.3 | 2509 | Load Payment Term (File Download / Upload) | n/a | n/a | n/a | test | x | High |  |  | Niklas
13.4 | 2509 | Load Payment Term (Data Export / Import) | n/a | n/a | n/a | test | x | High |  |  | Niklas
13.5 | 2509 | Payment Term Language Test (DE/EN) | n/a | n/a | n/a | test |  | Low |  |  | Ulla | [5 empty] | n/a |  | n/a | n/a | n/a
13.6 | 2509 | Payment Term Language Test (FR/ES/ES) | n/a | n/a | n/a | test |  | Low |  |  | Ulla | [5 empty] | open |  | open | open | open
13.7 | 2509 | Payment Ferm Test (ES)/condiciones de pago | n/a | n/a | n/a | test |  | Low |  |  | Ulla
13.8 | 2509 | Create Payment Term (Multiple Obj CR Type) | n/a | n/a | n/a | test |  | Medium |  |  | Gerd
14.1 |  | Change Currency Code | test | skip | skip | n/a |  | High |  |  | Maxi | [5 empty] | open |  | open | open | open
14.2 |  | Create Currency Code | test | skip | skip | n/a |  | High |  |  | Maxi | [5 empty] | open |  | open | open | open
14.3 |  | Load Currency Code (File Download / Upload) | n/a | n/a | n/a | test | x | High |  |  | Niklas
14.4 |  | Load Currency Code (Data Export / Import) | n/a | n/a | n/a | test | x | Very High |  |  | Niklas
14.5 |  | Currency Code Language Test (DE/EN) | n/a | n/a | n/a | test |  | Medium |  |  | Maxi | [5 empty] | n/a |  | n/a | n/a | n/a
14.6 |  | Currency Code Language Test (FR/ES/ES) | n/a | n/a | n/a | test |  | Medium |  |  | Ulla | [5 empty] | open |  | open | open | open
14.7 |  | Currency Code Test (ES)/abreviatura de moneda | n/a | n/a | n/a | test |  | Medium |  |  | Michael
15.1 | 2509 | Change Sales Organization | skip | test | test | n/a |  | High |  |  | Sabine
15.2 | 2509 | Create Sales Organization | skip | test | test | n/a |  | High |  |  | Sabine
15.3 | 2509 | Load Sales Organization (File Download / Upload) | n/a | n/a | n/a | test | x | High |  |  | Niklas
15.4 | 2509 | Load Sales Organization (Data Export / Import) | n/a | n/a | n/a | test | x | High |  |  | Niklas
15.5 | 2509 | Sales Organization Language Test (DE/EN) | n/a | n/a | n/a | test |  | Low |  |  | Ulla
15.6 | 2509 | Sales Organization Language Test (FR/ES) | n/a | n/a | n/a | test |  | Low |  |  | Ulla | [5 empty] | open |  | open | open | open
15.7 | 2509 | Sales Organisation Test (ES)/Organización de ventas | n/a | n/a | n/a | test |  | Low |  |  | Ulla
16.1 | 2509 | Change Material Type | skip | test | skip | n/a |  | High |  |  | Ulla
16.2 | 2509 | Create Material Type | skip | test | skip | n/a |  | High |  |  | Ulla
16.3 | 2509 | Load Material Type (File Download / Upload) | n/a | n/a | n/a | test | x | High |  |  | Niklas
16.4 | 2509 | Load Material Type (Data Export / Import) | n/a | n/a | n/a | test | x | High |  |  | Niklas
16.5 | 2509 | Material Type Language Test (DE/EN) | n/a | n/a | n/a | test |  | Low |  |  | Maxi | [5 empty] | open |  | open | open | open
16.6 | 2509 | Material Type Language Test (FR/ES) | n/a | n/a | n/a | test |  | Low |  |  | Ulla | [5 empty] | open |  | open | open | open
16.7 | 2509 | Material Type Test (ES)/tipo de material | n/a | n/a | n/a | test |  | Low |  |  | Ulla
17.1 | 2509 | Change Storage Location | skip | test | skip | n/a |  | High |  |  | Ulla
17.2 | 2509 | Create Storage Location | skip | test | skip | n/a |  | High |  |  | Ulla
17.3 | 2509 | Load Storage Location (File Download / Upload) | n/a | n/a | n/a | test | x | High |  |  | Niklas | [5 empty] | open |  | open | open | open
17.4 | 2509 | Load Storage Location (Data Export / Import) | n/a | n/a | n/a | test | x | High |  |  | Niklas | [5 empty] | open |  | open | open | open
17.5 | 2509 | Storage Location Language Test (DE/EN) | n/a | n/a | n/a | test |  | Low |  |  | Ulla
17.6 | 2509 | Storage Location Language Test (FR/ES) | n/a | n/a | n/a | test |  | Low |  |  | Ulla | [5 empty] | open |  | open | open | open
17.7 | 2509 | Storage Location Test (ES)/almacén | n/a | n/a | n/a | test |  | Low |  |  | Ulla
18.1 | 2509 | Change Division | skip | skip | test | n/a |  | High |  |  | Sabine
18.2 | 2509 | Create Division | skip | skip | test | n/a |  | High |  |  | Sabine
18.3 | 2509 | Load Division (File Download / Upload) | skip | skip | test | n/a | x | High |  |  | Niklas
18.4 | 2509 | Load Division/Sparte (Data Export / Import) | n/a | n/a | n/a | test | x | High |  |  | Niklas
18.5 | 2509 | Division Language Test (DE/EN) | n/a | n/a | n/a | test |  | Low |  |  | Ulla | [5 empty] | n/a |  | n/a | n/a | n/a
18.6 | 2509 | Division Language Test (FR/ES) | n/a | n/a | n/a | test |  | Low |  |  | Ulla | [5 empty] | open |  | open | open | open
18.7 | 2509 | Division Test (ES)/sector | n/a | n/a | n/a | test |  | Low |  |  | Ulla
19.1 |  | Change Factory Calendar | skip | test | skip | n/a |  | Very High |  |  | Maxi | [5 empty] | open |  | open | open | open
19.2 |  | Create Factory Calendar | skip | test | skip | n/a |  | Very High |  |  | Maxi | [5 empty] | open |  | open | open | open
19.3 |  | Load Factory Calendar (File Download / Upload) | n/a | n/a | n/a | test | x | Very High |  |  | Niklas
19.4 |  | Load Factory Calendar (Data Export / Import) | n/a | n/a | n/a | test | x | High |  |  | Niklas
19.5 |  | Factory Calendar Language Test (DE/EN) | n/a | n/a | n/a | test |  | Very High |  |  | Ulla | [5 empty] | n/a |  | n/a | n/a | n/a
19.6 |  | Factory Calendar Language Test (FR/ES) | n/a | n/a | n/a | test |  | Very High |  |  | Ulla | [5 empty] | open |  | open | open | open
19.7 |  | Factory Calendar Test (ES)/calendario de fábrica | n/a | n/a | n/a | test |  | Medium |  |  | Michael
20.1 | 2509 | Change Distribution Channel | skip | test | skip | n/a |  | High |  |  | Sabine | [5 empty] | open |  | open | open | open
20.2 | 2509 | Create Distribution Channel | skip | test | skip | n/a |  | High |  |  | Sabine | [5 empty] | open |  | open | open | open
20.3 | 2509 | Load Distribution Channel (File Download / Upload) | n/a | n/a | n/a | test | x | High |  |  | Niklas
20.4 | 2509 | Load Distribution Channel (Data Export / Import) | n/a | n/a | n/a | test | x | High |  |  | Niklas
20.5 | 2509 | Distribution Channel Language Test (DE/EN) | n/a | n/a | n/a | test |  | Low |  |  | Ulla | [5 empty] | n/a |  | n/a | n/a | n/a
20.6 | 2509 | Distribution Channel Language Test (FR/ES) | n/a | n/a | n/a | test |  | Low |  |  | Ulla | [5 empty] | open |  | open | open | open
20.7 | 2509 | Distribution Channel Test (ES)/canal de distribución | n/a | n/a | n/a | test |  | Low |  |  | Ulla
21.1 | 2509 | Change Controlling Area | skip | skip | skip | n/a |  | High |  |  | Maxi | [5 empty] | open |  | open | open | open
21.2 | 2509 | Create Controlling Area | skip | skip | skip | n/a |  | High |  |  | Maxi | [5 empty] | open |  | open | open | open
21.3 | 2509 | Load Controlling Area (File Download / Upload) | n/a | n/a | n/a | test | x | High |  |  | Niklas
21.4 | 2509 | Load Controlling Area (Data Export / Import) | n/a | n/a | n/a | test | x | High |  |  | Niklas
21.5 | 2509 | Controlling Area Language Test (DE/EN) | n/a | n/a | n/a | test |  | Low |  |  | Ulla | [5 empty] | n/a |  | n/a | n/a | n/a
21.6 | 2509 | Controlling Area Language Test (FR/ES) | n/a | n/a | n/a | test |  | Low |  |  | Ulla | [5 empty] | open |  | open | open | open
21.7 | 2509 | Controlling Area Test (ES)/sociedad CO | n/a | n/a | n/a | test |  | Low |  |  | Ulla
22.1 | 2509 | Change Material Status | skip | skip | test | n/a |  | High |  |  | Maxi | [5 empty] | open |  | open | open | open
22.2 | 2509 | Create Material Status | skip | skip | test | n/a |  | High |  |  | Maxi | [5 empty] | open |  | open | open | open
22.3 | 2509 | Load Material Status (File Download / Upload) | n/a | n/a | n/a | test | x | High |  |  | Niklas
22.4 | 2509 | Load Material Status (Data Export / Import) | n/a | n/a | n/a | test | x | High |  |  | Niklas
22.5 | 2509 | Material Status Language Test (DE/EN) | n/a | n/a | n/a | test |  | Low |  |  | Maxi | [5 empty] | n/a |  | n/a | n/a | n/a
22.6 | 2509 | Material Status Language Test (FR/ES) | n/a | n/a | n/a | test |  | Low |  |  | Ulla | [5 empty] | open |  | open | open | open
22.7 | 2509 | Material Status Test (ES)/estado del material | n/a | n/a | n/a | test |  | Low |  |  | Ulla
23.1 |  | Change Personnel Area | test | skip | skip | n/a |  | Low |  |  | Maxi | [5 empty] | open |  | open | open | open
23.2 |  | Create Personnel Area | test | skip | skip | n/a |  | Low |  |  | Maxi | [5 empty] | open |  | open | open | open
23.3 |  | Load Personnel Area (File Download / Upload) | n/a | n/a | n/a | test | x | Low |  |  | Niklas
23.4 |  | Load Personnel Area (Data Export / Import) | n/a | n/a | n/a | test | x | Low |  |  | Niklas
23.5 |  | Personnel Area Language Test (DE/EN) | n/a | n/a | n/a | test |  | Low |  |  | Maxi | [5 empty] | n/a |  | n/a | n/a | n/a
23.6 |  | Personnel Area Language Test (FR/ES) | n/a | n/a | n/a | test |  | Low |  |  | Ulla | [5 empty] | open |  | open | open | open
23.7 |  | Personal Area Test (ES)/área personal | n/a | n/a | n/a | test |  | Medium |  |  | Michael
24.1 |  | Change Business Area | skip | test | skip | n/a |  | High |  |  | Maxi | [5 empty] | open |  | open | open | open
24.2 |  | Create Business Area | skip | test | skip | n/a |  | High |  |  | Maxi | [5 empty] | open |  | open | open | open
24.3 |  | Load Business Area (File Download / Upload) | n/a | n/a | n/a | test | x | Low |  |  | Niklas
24.4 |  | Load Business Area (Data Export / Import) | n/a | n/a | n/a | test | x | Low |  |  | Niklas
24.5 |  | Business Area Language Test (DE/EN) | n/a | n/a | n/a | test |  | Low |  |  | Maxi | [5 empty] | n/a |  | n/a | n/a | n/a
24.6 |  | Business Area Language Test (FR/ES) | n/a | n/a | n/a | test |  | Low |  |  | Ulla | [5 empty] | open |  | open | open | open
24.7 |  | Business Area Test (ES)/área empresarial | n/a | n/a | n/a | test |  | Medium |  |  | Michael
25.1 | 2509 | Change Functional Area | skip | skip | test | n/a |  | High |  |  | Sabine
25.2 | 2509 | Create Functional Area | skip | skip | test | n/a |  | High |  |  | Sabine
25.3 | 2509 | Load Functional Area (File Download / Upload) | n/a | n/a | n/a | test | x | High |  |  | Niklas
25.4 | 2509 | Load Functional Area (Data Export / Import) | n/a | n/a | n/a | test | x | High |  |  | Niklas
25.5 | 2509 | Functional Area Language Test (DE/EN) | n/a | n/a | n/a | test |  | Low |  |  | Maxi | [5 empty] | n/a |  | n/a | n/a | n/a
25.6 | 2509 | Functional Area Language Test (FR/ES) | n/a | n/a | n/a | test |  | Low |  |  | Ulla | [5 empty] | open |  | open | open | open
25.7 | 2509 | Functional Area Test (ES)/área funcional | n/a | n/a | n/a | test |  | Low |  |  | Ulla
26.1 | 2509 | Change Incoterm | skip | test | skip | n/a |  | High |  |  | Ulla
26.2 | 2509 | Create Incoterm | skip | test | skip | n/a |  | High |  |  | Ulla
26.3 | 2509 | Load Incoterm (File Download / Upload) | n/a | n/a | n/a | test | x | High |  |  | Niklas
26.4 | 2509 | Load Incoterm (Data Export / Import) | n/a | n/a | n/a | test | x | High |  |  | Niklas
26.5 | 2509 | Incoterm Language Test (DE/EN) | n/a | n/a | n/a | test |  | Low |  |  | Maxi | [5 empty] | n/a |  | n/a | n/a | n/a
26.6 | 2509 | Incoterm Language Test (FR/ES) | n/a | n/a | n/a | test |  | Low |  |  | Ulla | [5 empty] | open |  | open | open | open
26.7 | 2509 | Incoterm Test (ES)/incoterm | n/a | n/a | n/a | test |  | Low |  |  | Ulla
27.1 | 2509 | Change Sales Group | skip | test | skip | n/a |  | High |  |  | Maxi | [5 empty] | open |  | open | open | open
27.2 | 2509 | Create Sales Group | skip | test | skip | n/a |  | High |  |  | Maxi | [5 empty] | open |  | open | open | open
27.3 | 2509 | Load Sales Group (File Download / Upload) | n/a | n/a | n/a | test | x | High |  |  | Niklas
27.4 | 2509 | Load Sales Group (Data Export / Import) | n/a | n/a | n/a | test | x | High |  |  | Niklas
27.5 | 2509 | Sales Group Language Test (DE/EN) | n/a | n/a | n/a | test |  | Low |  |  | Maxi | [5 empty] | n/a |  | n/a | n/a | n/a
27.6 | 2509 | Sales Group Language Test (FR/ES) | n/a | n/a | n/a | test |  | Low |  |  | Ulla | [5 empty] | open |  | open | open | open
27.7 | 2509 | Sales Group Test (ES)/grupo de vendedores | n/a | n/a | n/a | test |  | Low |  |  | Ulla
28.1 | 2509 | Change Shipping Type | skip | test | skip | n/a |  | High |  |  | Maxi | [5 empty] | open |  | open | open | open
28.2 | 2509 | Create Shipping Type | skip | test | skip | n/a |  | High |  |  | Maxi | [5 empty] | open |  | open | open | open
28.3 | 2509 | Load Shipping Type (File Download / Upload) | n/a | n/a | n/a | test | x | High |  |  | Niklas
28.4 | 2509 | Load Shipping Type (Data Export / Import) | n/a | n/a | n/a | test | x | High |  |  | Niklas
28.5 | 2509 | Shipping Type Language Test (DE/EN) | n/a | n/a | n/a | test |  | Low |  |  | Ulla | [5 empty] | n/a |  | n/a | n/a | n/a
28.6 | 2509 | Shipping Type Language Test (FR/ES) | n/a | n/a | n/a | test |  | Low |  |  | Ulla | [5 empty] | open |  | open | open | open
28.7 | 2509 | Shipping Type Test (ES)/clase de expedición | n/a | n/a | n/a | test |  | Low |  |  | Ulla
29.1 | 2509 | Change Shipping Conditions | skip | skip | test | n/a |  | High |  |  | Maxi | [5 empty] | open |  | open | open | open
29.2 | 2509 | Create Shipping Conditions | skip | skip | test | n/a |  | High |  |  | Maxi | [5 empty] | open |  | open | open | open
29.3 | 2509 | Load Shipping Conditions (File Download / Upload) | n/a | n/a | n/a | test | x | High |  |  | Niklas
29.4 | 2509 | Load Shipping Conditions (Data Export / Import) | n/a | n/a | n/a | test | x | High |  |  | Niklas
29.5 | 2509 | Shipping Conditions Language Test (DE/EN) | n/a | n/a | n/a | test |  | Low |  |  | Ulla | [5 empty] | n/a |  | n/a | n/a | n/a
29.6 | 2509 | Shipping Conditions Language Test (FR/ES) | n/a | n/a | n/a | test |  | Low |  |  | Ulla | [5 empty] | open |  | open | open | open
29.7 | 2509 | Shipping Conditions Test (ES)/condiciones de expedición | n/a | n/a | n/a | test |  | Low |  |  | Ulla
30.1 | 2509 | Change Lab/office | test | test | test | n/a |  | High |  |  | Ulla
30.2 | 2509 | Create Lab/office | test | test | test | n/a |  | High |  |  | Ulla
30.3 | 2509 | Load Lab/Office (File Download / Upload) | n/a | n/a | n/a | test | x | High |  |  | Niklas
30.4 | 2509 | Load Lab/Office (Data Export / Import) | n/a | n/a | n/a | test | x | High |  |  | Niklas
30.5 | 2509 | Lab/Office Language Test (DE/EN) | n/a | n/a | n/a | test |  | Low |  |  | Maxi | [5 empty] | n/a |  | n/a | n/a | n/a
30.6 | 2509 | Lab/Office Language Test (FR/ES) | n/a | n/a | n/a | test |  | Low |  |  | Ulla | [5 empty] | open |  | open | open | open
30.7 | 2509 | Lab/Office Test (ES)/laboratorio/oficina | n/a | n/a | n/a | test |  | Low |  |  | Ulla
31.1 |  | Change BOM Usage | test | test | test | n/a |  | Low |  |  | Ulla
31.2 |  | Create BOM Usage | test | test | test | n/a |  | Low |  |  | Ulla
31.3 |  | Load BOM Usage (File Download / Upload) | n/a | n/a | n/a | test | x | Low |  |  | Niklas
31.4 |  | Load BOM Usage (Data Export / Import) | n/a | n/a | n/a | test | x | Low |  |  | Niklas
31.5 |  | BOM Usage Language Test (DE/EN) | n/a | n/a | n/a | test |  | Low |  |  | Ulla | [5 empty] | n/a |  | n/a | n/a | n/a
31.6 |  | BOM Usage Language Test (FR/ES) | n/a | n/a | n/a | test |  | Low |  |  | Ulla | [5 empty] | open |  | open | open | open
31.7 |  | BOM Usage Test (ES)/utilización de la lista de materiales | n/a | n/a | n/a | test |  | Medium |  |  | Michael
32.1 | 2509 | Create Document Type | skip | test | skip | n/a |  | High |  |  | Maxi
32.2 | 2509 | Change Document Type | skip | test | skip | n/a |  | High |  |  | Maxi
32.3 | 2509 | Load Document Type (File Download / Upload) | skip | skip | skip | n/a |  | High |  |  | Niklas | [5 empty] | open |  | open | open | open
32.4 | 2509 | Load Document Type (Data Export / Import) | n/a | n/a | n/a | test | x | High |  |  | Niklas | [5 empty] | open |  | open | open | open
32.5 | 2509 | Document Type Language Test (DE/EN) | n/a | n/a | n/a | test |  | Low |  |  | Ulla | [5 empty] | n/a |  | n/a | n/a | n/a
32.6 | 2509 | Document Type Language Test (FR/ES) | n/a | n/a | n/a | test |  | Low |  |  | Ulla | [5 empty] | open |  | open | open | open
32.7 | 2509 | Document Type Test (ES)/tipo de documento | n/a | n/a | n/a | test |  | Low |  |  | Ulla
33.1 | 2509 | Create Chart of Account | skip | skip | test | n/a |  | High |  |  | Ulla
33.2 | 2509 | Change Chart of Account | skip | skip | test | n/a |  | High |  |  | Ulla
33.3 | 2509 | Load Chart of Account (File Download / Upload) | n/a | n/a | n/a | test | x | High |  |  | Niklas
33.4 | 2509 | Load Chart of Account (Data Export / Import) | n/a | n/a | n/a | test | x | High |  |  | Niklas
33.5 | 2509 | Chart of Account Language Test (DE/EN) | n/a | n/a | n/a | test |  | Low |  |  | Ulla | [5 empty] | n/a |  | n/a | n/a | n/a
33.6 | 2509 | Chart of Account Language Test (FR) | n/a | n/a | n/a | test |  | Low |  |  | Ulla | [5 empty] | open |  | open | open | open
33.7 | 2509 | Chart of Account Test (ES)/gráfico de la cuenta | n/a | n/a | n/a | test |  | Low |  |  | Ulla
34.1 |  | Create Operating Concern | test | skip | skip | n/a |  | Low |  |  | Maxi | [5 empty] | open |  | open | open | open
34.2 |  | Change Operating Concern | test | skip | skip | n/a |  | Low |  |  | Maxi | [5 empty] | open |  | open | open | open
34.3. |  | Load Operating Concern (File Download / Upload) | n/a | n/a | n/a | test | x | Low |  |  | Niklas
34.4. |  | Load Operating Concern (Data Export / Import) | n/a | n/a | n/a | test | x | Low |  |  | Niklas | [5 empty] | open |  | open | open | open
34.5 |  | Operating Concern Language Test (DE/EN) | n/a | n/a | n/a | test |  | Low |  |  | Maxi | [5 empty] | open |  | open | open | open
34.6 |  | Operating Concern Language Test (FR/ES) | n/a | n/a | n/a | test |  | Low |  |  | Ulla | [5 empty] | open |  | open | open | open
34.7 |  | Operating Concern Test (ES)/sociedad PA | n/a | n/a | n/a | test |  | Medium |  |  | Michael
35.1. |  | Create Language | test | skip | skip | n/a |  | Low |  |  | Maxi | [5 empty] | open |  | open | open | open
35.2 |  | Change Language | test | skip | skip | n/a |  | Low |  |  | Maxi | [5 empty] | open |  | open | open | open
35.3 |  | Load Language (File Download / Upload) | n/a | n/a | n/a | test | x | Very High |  |  | Niklas
35.4 |  | Load Language (Data Export / Import) | n/a | n/a | n/a | test | x | Very High |  |  | Niklas
35.5 |  | Language / Language Test (DE/EN) | n/a | n/a | n/a | test |  | Low |  |  | Ulla | [5 empty] | n/a |  | n/a | n/a | n/a
35.6 |  | Language / Language Test (FR) | n/a | n/a | n/a | test |  | Low |  |  | Ulla | [5 empty] | open |  | open | open | open
35.7 |  | Language Test (ES)/idioma | n/a | n/a | n/a | test |  | Medium |  |  | Michael
36.1 |  | Change Location | skip | test | skip | n/a |  | Medium |  |  | Maxi | [5 empty] | open |  | open | open | open
36.2 |  | Create Location | skip | test | skip | n/a |  | Medium |  |  | Maxi | [5 empty] | open |  | open | open | open
36.3 |  | Load Location (File Download / Upload) | n/a | n/a | n/a | test | x | Medium |  |  | Niklas
36.4 |  | Load Location (Data Export / Import) | n/a | n/a | n/a | test | x | Medium |  |  | Niklas
36.5 |  | Location Language Test (DE/EN) | n/a | n/a | n/a | skip |  | Medium |  |  | Maxi | [5 empty] | n/a |  | n/a | n/a | n/a
36.6 |  | Location Language Test (FR/ES) | n/a | n/a | n/a | test |  | Medium |  |  | Ulla | [5 empty] | open |  | open | open | open
36.7 |  | Language Test (ES)/ubicación | n/a | n/a | n/a | test |  | Medium |  |  | Michael
37.1 |  | Create Exchange Rate (via User Interface) | skip | test | skip | n/a |  | Very High |  |  | Gerd
37.2 |  | Change Exchange Rate (via User Interface) | skip | test | skip | n/a |  | Very High |  |  | Thomas
37.2 |  | Change Exchange Rate (via external service) | skip | skip | skip | test |  | Very High |  |  | Thomas
37.3 |  | Load Exchange Rate (initial Load) | n/a | n/a | n/a | test | x | Very High |  |  | Thomas
37.4 |  | Data Feed | n/a | test | n/a | test |  | Very High |  |  | Thomas
37.5 |  | Exchange Rate Language Test (DE/EN) | n/a | test | n/a | test |  | Medium |  |  | Ulla | [5 empty] | n/a |  | n/a | n/a | n/a
37.6 |  | Exchange Rate Language Test (FR/ES) | n/a | n/a | n/a | test |  | Medium |  |  | Ulla | [5 empty] | open |  | open | open | open
37.7 |  | Exchange Rate Test (ES)/tipo de cambio | n/a | n/a | n/a | test |  | Medium |  |  | Michael
38.1 |  | Change Characteristics | test | test | test | test |  | Very High |  |  | Maxi
38.2 |  | Create Characteristics | skip | test | test | test |  | Very High |  |  | Maxi
38.3 |  | Copy Characteristics |  | test | test | test |  | Very High |  |  | Sabine
38.4 |  | Load Characteristics (File Download / Upload) | n/a | n/a | n/a | test | x | High |  |  | Niklas
38.5 |  | Load Characteristics (IDocs) | n/a | n/a | n/a | test | x | Low |  |  | Michael
38.6 |  | Characteristics - Language Test (DE/EN) | n/a | n/a | n/a | test |  | Very High |  |  | Ulla | [5 empty] | open |  | open | open | open
38.7 |  | Characteristics - Language Test (FR/ES) | n/a | n/a | n/a | test |  | Very High |  |  | Ulla | [5 empty] | open |  | open | open | open
38.8 |  | Characteristics Test (ES)/características | n/a | n/a | n/a | test |  | Medium |  |  | Michael
39.1 |  | Change Classes | test | test | test | test |  | Very High |  |  | Sabine
39.2 |  | Create Classes | test | test | test | test |  | Very High |  |  | Sabine
39.3 |  | Copy Classes |  | skip | test | test |  | Very High |  |  | Sabine
39.4 |  | Load Classes (File Download / Upload) | n/a | n/a | n/a | test | x | High |  |  | Niklas
39.5 |  | Load Classes (IDocs) | n/a | n/a | n/a | test | x | Low |  |  | Michael
39.6 |  | Classes - Language Test (DE/EN) | n/a | n/a | n/a | test |  | High |  |  | Maxi | [5 empty] | n/a |  | n/a | n/a | n/a
39.7 |  | Classes - Language Test (FR/ES) | n/a | n/a | n/a | test |  | Very High |  |  | Ulla | [5 empty] | open |  | open | open | open
39.8 |  | Classes Test (ES)/clases | n/a | n/a | n/a | test |  | Medium |  |  | Michael
40.1 | 2509 | Change MRP Type | skip | test | skip | n/a |  | High |  |  | Maxi | [5 empty] | open |  | open | open | open
40.2 | 2509 | Create MRP Type | skip | test | skip | n/a |  | High |  |  | Maxi | [5 empty] | open |  | open | open | open
40.3 | 2509 | Load MRP Type (File Download / Upload) | n/a | n/a | n/a | test | x | High |  |  | Niklas
40.4 | 2509 | Load MRP Type (Data Export / Import) | n/a | n/a | n/a | test | x | High |  |  | Niklas | [5 empty] | open |  | open | open | open
40.5 | 2509 | MRP Type - Language Test (DE/EN) | n/a | n/a | n/a | test |  | Low |  |  | Maxi | [5 empty] | n/a |  | n/a | n/a | n/a
40.6 | 2509 | MRP Type - Language Test (FR/ES) | n/a | n/a | n/a | test |  | Low |  |  | Ulla | [5 empty] | open |  | open | open | open
40.7 | 2509 | MRP Type Test (ES)/tipo de planificación de necesidades | n/a | n/a | n/a | test |  | Low |  |  | Ulla
41.1 | 2509 | Change MRP Profile | test | skip | skip | n/a |  | High |  |  | Maxi | [5 empty] | open |  | open | open | open
41.2 | 2509 | Create MRP Profile | test | skip | skip | n/a |  | High |  |  | Maxi | [5 empty] | open |  | open | open | open
41.3 | 2509 | Load MRP Profile (File Download / Upload) | n/a | n/a | n/a | test | x | High |  |  | Niklas
41.4 | 2509 | Load MRP Profile (Data Export / Import) | n/a | n/a | n/a | test | x | High |  |  | Niklas
41.5 | 2509 | MRP Profile - Language Test (DE/EN) | n/a | n/a | n/a | test |  | Low |  |  | Maxi | [5 empty] | open |  | open | open | open
41.6 | 2509 | MRP Profile - Language Test (FR/ES) | n/a | n/a | n/a | test |  | Low |  |  | Ulla | [5 empty] | open |  | open | open | open
41.7 | 2509 | MRP Profile Test (ES)/perfil de planificación de necesidades | n/a | n/a | n/a | test |  | Low |  |  | Ulla
42.1 | 2509 | Change MRP Area | skip | test | skip | test |  | High |  |  | Ulla
42.2 | 2509 | Create MRP Area | skip | test | skip | test |  | High |  |  | Ulla
42.3 | 2509 | Load MRP Area (File Download / Upload) | n/a | n/a | n/a | test | x | High |  |  | Niklas
42.4 | 2509 | Load MRP Area (Data Export / Import) | n/a | n/a | n/a | test | x | High |  |  | Niklas
42.5 | 2509 | MRP Area - Language Test (DE/EN) | n/a | n/a | n/a | test |  | Low |  |  | Ulla | [5 empty] | n/a |  | n/a | n/a | n/a
42.5 | 2509 | MRP Area - Language Test (FR/ES) | n/a | n/a | n/a | test |  | Low |  |  | Ulla | [5 empty] | open |  | open | open | open
42.7 | 2509 | MRP Area Test (ES)/área de planificación MRP | n/a | n/a | n/a | test |  | Low |  |  | Ulla
43.1 |  | Change Tax Code | skip | test | skip | test |  | Very High |  |  | Sabine | [5 empty] | open |  | open | open | open
43.2 |  | Create Tax Code | skip | test | skip | test |  | Very High |  |  | Sabine | [5 empty] | open |  | open | open | open
43.3 |  | Load Tax Code(File Download / Upload) | skip | test | skip | test | x | High |  |  | Niklas
43.4 |  | Load Tax Code (Data Export / Import) | skip | test | skip | test | x | High |  |  | Niklas
43.5 |  | Tax Code - Language Test (DE/EN) | n/a | n/a | n/a | test |  | Medium |  |  | Maxi | [5 empty] | n/a |  | n/a | n/a | n/a
43.6 |  | Tax Code - Language Test (FR/ES) | n/a | n/a | n/a | test |  | Medium |  |  | Ulla | [5 empty] | open |  | open | open | open
43.7 |  | Tax Code Test (ES)/código de impuesto | n/a | n/a | n/a | test |  | Medium |  |  | Michael
44.1 | 2509 | Change Valuation Class | skip | test | skip | n/a |  | High |  |  | Maxi | [5 empty] | open |  | open | open | open
44.2 | 2509 | Create Valuation Class | skip | test | skip | n/a |  | High |  |  | Maxi | [5 empty] | open |  | open | open | open
44.3 | 2509 | Load Valuation Class (File Download / Upload) | n/a | n/a | n/a | test | x | High |  |  | Niklas
44.4 | 2509 | Load Valuation Class (Data Export / Import) | n/a | n/a | n/a | test | x | High |  |  | Niklas
44.5 | 2509 | Valuation Class - Language Test (DE/EN) | n/a | n/a | n/a | test |  | Low |  |  | Ulla
44.6 | 2509 | Valuation Class - Language Test (FR/ES) | n/a | n/a | n/a | test |  | Low |  |  | Ulla | [5 empty] | open |  | open | open | open
44.7 | 2509 | Valuation Class Test (ES)/cateogoría de valuación | n/a | n/a | n/a | test |  | Low |  |  | Ulla
45.1 | 2509 | Change Sales Office | skip | skip | test | test |  | High |  |  | Sabine | [5 empty] | open |  | open | open | open
45.2 | 2509 | Create Sales Office | skip | skip | test | test |  | High |  |  | Sabine
45.3 | 2509 | Load Sales Office (File Download / Upload) | skip | skip | test | test | x | High |  |  | Niklas | [5 empty] | open |  | open | open | open
45.4 | 2509 | Load Sales Office (Data Export / Import) | skip | skip | test | test | x | High |  |  | Niklas
45.5 | 2509 | Sales Office - Language Test (DE/EN) | n/a | n/a | n/a | test |  | Low |  |  | Ulla
45.6 | 2509 | Sales Office - Language Test (FR/ES) | n/a | n/a | n/a | test |  | Low |  |  | Ulla | [5 empty] | open |  | open | open | open
45.7 | 2509 | Sales Office Test (ES)/oficina de ventas | n/a | n/a | n/a | test |  | Low |  |  | Ulla
46.1 | 2509 | Change Scope of Planning | skip | test | skip | test |  | High |  |  | Sabine
46.2 | 2509 | Create Scope of Planning | skip | test | skip | test |  | High |  |  | Sabine | [5 empty] | open |  | open | open | open
46.3 | 2509 | Load Scope of Planning (File Download / Upload) | skip | test | skip | test | x | High |  |  | Niklas | [5 empty] | open |  | open | open | open
46.4 | 2509 | Load Scope of Planning (Data Export / Import) | skip | test | skip | test | x | High |  |  | Niklas
46.5 | 2509 | Scope of Planning - Language Test (DE/EN) | n/a | n/a | n/a | test |  | Low |  |  | Ulla | [5 empty] | open |  | open | open | open
46.6 | 2509 | Scope of Planning - Language Test (FR/ES) | n/a | n/a | n/a | test |  | Low |  |  | Ulla | [5 empty] | open |  | open | open | open
46.7 | 2509 | Scope of Planning for MRP Unit Test (ES)/ámbito de planificación | n/a | n/a | n/a | test |  | Low |  |  | Ulla
47.1 | 2509 | Change MRP Controller | skip | test | skip | test |  | High |  |  | Maxi
47.2 | 2509 | Create MRP Controller | skip | test | skip | test |  | High |  |  | Maxi
47.3 | 2509 | Load MRP Controller File Download / Upload) | n/a | test | skip | n/a | x | High |  |  | Niklas
47.4 | 2509 | Load MRP Controller (Data Export / Import) | n/a | n/a | n/a | test | x | High |  |  | Niklas
47.5 | 2509 | MRP Controller - Language Test (DE/EN) | n/a | n/a | n/a | test |  | Low |  |  | Ulla | [5 empty] | n/a |  | n/a | n/a | n/a
47.6 | 2509 | MRP Controller - Language Test (FR/ES) | n/a | n/a | n/a | test |  | Low |  |  | Ulla | [5 empty] | open |  | open | open | open
47.7 | 2509 | MRP Controller Test (ES)/planificador de necesidades | n/a | n/a | n/a | test |  | Low |  |  | Ulla
48.1 |  | Change Holiday Calendar | [5 empty] | Very High |  |  | Maxi
48.2 |  | Create Holiday Calendar | [5 empty] | Very High |  |  | Maxi
48.3 |  | Load Holiday Calendar File Download / Upload) | [5 empty] | Very High |  |  | Niklas
48.4 |  | Load Holiday Calendar (Data Export / Import) | [5 empty] | Very High |  |  | Niklas
48.5 |  | Holiday Calendar - Language Test (DE/EN/FR/ES) | [5 empty] | Very High |  |  | Maxi
49.1 |  | Change Public Holiday | [5 empty] | Very High |  |  | Maxi
49.2 |  | Create Public Holiday | [5 empty] | Very High |  |  | Maxi
49.3 |  | Load Public Holiday File Download / Upload) | [5 empty] | Very High |  |  | Niklas
49.4 |  | Load Public Holiday (Data Export / Import) | [5 empty] | Very High |  |  | Niklas
49.5 |  | Public Holiday - Language Test (DE/EN/FR/ES) | [5 empty] | Very High |  |  | Maxi
750.0 MDF |  | ******************************************* | [5 empty] | *********
750.1 RULE | 2509 | Configuration (Rule) Management | n/a | n/a | n/a | test |  | Very High |  |  | Ulla
751.1 MDF | 2509 | ValueMapping | n/a | n/a | n/a | test |  | High |  |  | Maxi
752.1 MDF | 2509 | KeyMapping | n/a | n/a | n/a | test |  | High |  |  | Maxi
753.1 MDF |  | Webservice | n/a | n/a | n/a | test |  | Low |  |  | Michael
754.1 MDF |  | Deletions | n/a | n/a | n/a | test |  | Very High |  |  | Thomas
755.1 MDF |  | Searchhelps | n/a | n/a | n/a | test |  | Very High |  |  | Gerd
800.0 RDH |  | ******************************************* | [5 empty] | *********
800.1 RDH |  | Reference Data Harmonization | n/a | n/a | n/a | test |  | Very High |  |  | Gerd
850.0 Install & Upgrade |  | ******************************************* | [5 empty] | *********
851.1 INST |  | Install (S03 Smoketest) | n/a | n/a | n/a | test |  | Very High |  |  | Dieter
852.1 OLD Release Check |  | Check Replication to older (and newer RDM Release (S01) | n/a | n/a | n/a | test |  | Very High |  |  | Michael
853.1 UPGR |  | Upgrade | n/a | n/a | n/a | test |  | Very High |  |  | Dieter
900.0 Special Tests |  | ******************************************* | [5 empty] | *********
901.1 DRF | 2509 | Data Replication | n/a | n/a | n/a | test |  | Very High |  |  | Maxi
902.1 ENH |  | Enhancements and Upgrade | n/a | n/a | n/a | test |  | Very High |  |  | Mike
903.1 FR/ES |  | Translation to FR/ES (MDF, RDH, DRF) | n/a | n/a | n/a | test |  | Medium |  |  | Ulla
904.1 SOLMAN |  | SolManager Tests |  |  |  | test |  | Low |  |  | Michael
905.1 GTS | 2509 | GTS Tests |  |  | test |  |  | High |  |  | Michael
Testcases |  | Link to Testcases
Checklist |  | Checklist Scope of Planning
Open Topics |  | Excel
Open Topics Details |  | Topic Details
Status |  | in progress
done / done with limitations
open / not tested
error
retest